## Sheet1
Work to be done to stop Cross contamination on Product at Highbay Equipments
Line No |  | Scope of work | Area | Activity completion Time | Status as on 21/10/16
1 | Line H1 | Soap dropping from simplex plodder Gland | Simplex |  | Completed
2 | Line H1 | Oil leakages issue from mixer Gear box need to be replaced with new Helical Gear box | Sigma Mixer | 2016-10-20
3 | Line H1 | Rerouting/insulation of chilled water line | Simplex | 2016-10-23 | Under progress
4 | Line H1 | Rain Water drop on the H1 Line noodle charging conveyor during rainy season. | Steel Floor | 2016-10-15 | To be checked during rains
5 | Line H1 | Opening under the sigma mixer | Sigma Mixer |  | Ashok to check
6 | Line H1 | Sigma hopper not proper. Always tilted.- Newhopper to be provided | Sigma Mixer | 2016-10-30 | To be checked during operations for leakages
7 | Line H1 | Gate required to sigma mixer hopper for easy cleaning during C/O | Sigma Mixer | 2016-10-30 | To be checked during operations for leakages
8 | Line H2 | Simplex hopper full welding& grinding to be done / | Simplex | - | Decision to be taken for replacement / modification 0n 22/10/16
9 | Line H2 | TRM hopper hook to be provided & New Hopper to be provided to TRM outfeed | Simplex | 2016-10-31
10 | Line H2 | Rerouting/insulation of chilled water line | Simplex | 2016-10-31 | Underprogress
11 | Line H2 | Noodles charging conveyors open, noodle drop under the conveyors. | Steel Floor | 2016-11-15
12 | Line H2 | Oil leakages issue from mixer Gear box need to be replaced with new Helical Gear box | Sigma Mixer |  | Under progress to be completed by 25/10/16
13 | Line H2 | Dump hopper guard damaged to be repaired- Priority 2nd | Steel Floor | 2016-11-30
14 | Line H2 | No border under the dump hopper guard. Resulting in water dropping inside the sigma mixer during cleaning. | Steel Floor | 31/10/2016 (on Diwali ) | Completed
15 | Line H2 | Perfume dozing pump to be removed. | Steel Floor |  | Completed
16 | Line H2 | Bellow cloth is very old , to be replaced - Service Silo. | Steel Floor | 2016-10-23 | Completed
17 | Line H2 | Chute Broken | TRM |  | Completed
18 | Line H3 | Opening from Mixer bottom to be closed | Sigma Mixer | 31/10/2016 (on Diwali ) | Completed
19 | Line H3 | TRM front MS rusted covering plate needs to be replaced with SS | Simplex | 2016-10-28 | Completed
20 | Line H3 | Rerouting/insulation of chilled water line | Simplex | 2016-10-28 | Completed
21 | Line H3 | Oil leakages issue from mixer Gear box need to be replaced with new Helical Gear box | Sigma Mixer | 2016-11-30 | Completed
22 | Line H3 | No border under the dump hopper guard. Resulting HK water drop inside the sigma mixer. | Steel Floor | 31/10/2016 (on Diwali ) | Completed
23 | Line H3 | Perfume dozing pump to be removed. | Steel Floor |  | Completed
24 | Line H3 | SS guard to be arranged to noodle charging conveyors. | Steel Floor | 2016-11-15 | Completed
25 | Line H3 | Bellow cloth is very old. To be replaced. | Steel Floor | 2016-10-23 | Completed
26 | Line H4 | Opening from Mixer bottom to be closed | Sigma Mixer | 2016-10-26 | Completed
27 | Line H4 | Electrical cable dressing & extra cable removal | Simplex | 2016-10-24 | Completed
28 | Line H4 | TRM bottom belt width to be increased to stop soap droppings | Simplex |  | Completed
29 | Line H4 | Rerouting/insulation of chilled water line | Simplex | 2016-10-28 | Completed
30 | Line H4 | No border under the dump hopper guard. Resulting in water dropping inside the sigma mixer during cleaning. | Steel Floor | 2016-11-01 | Completed
31 | Line H4 | Perfume dozing pump to be removed. | Steel Floor |  | Completed
32 | Line H4 | SS guard to be arranged to noodle charging conveyors. | Steel Floor | 2016-11-15
33 | Line H4 | Bellow cloth is very old. To be replaced. | Steel Floor | 2016-10-23 | Completed
34 | Line H4 | Oil leakages. | Sigma Mixer |  | Completed
35 | Line H4 | Gate required for sigma mixer hopper for easy cleaning during C/O - Priority | Sigma Mixer | 2016-11-15 | Completed
36 | Line H4 | Dressing of the cables required of H4 lines. | Sigma Mixer | 2016-10-24 | Completed
37 | Line H5 | Mixer bottom opening to be closed | Sigma Mixer | 2016-10-28 | Completed
38 | Line H5 | Rerouting/insulation of chilled water line | Simplex | 2016-10-28 | completed
39 | Line H5 | No border under the dump hopper guard. Resulting HK water drop inside the sigma mixer. | Steel Floor | 2016-11-01 | Completed
40 | Line H5 | Perfume dozing pump to be removed. | Steel Floor | 2016-10-15 | Completed
41 | Line H5 | Bellow cloth is very old. To be replaced. | Steel Floor | 2016-10-27 | completed