## Baddi shifting summary
Baddi plant shifting from Baddi to Guwahati costing summary
Sr.no. | Description | Amount
|  | Without tax | Tax only | With tax
1 | Fatty acid plant | 104804595.795 | 20564018.0437 | 125368613.8388
Splitting plant
Distillation plant
Sweet water treatment plant
2 | Utility
| Cheema boiler | 9200000 | 1407500 | 10607500
| 2.5 Mkcal heater | 15645000 | 2657025 | 18302025
| Tankfarm | 168050856.5 | 31994484.8375 | 200045341.3375
| New utilities | 23150000 | 5666750 | 28816750
| MP boiler & Fuel feeding | 28200000 | 4173000 | 32373000
3 | Saponification Plant
| Process Plant | 65757641.45 | 10671440.3383 | 76429081.7882
| Saponification tank farm | 10317446.85 | 1644888.9862 | 11962335.8362
| Saponification MP boiler | 7600000 | 1175500 | 8775500
| Total amount | 432725540.595 | 79954607.2057 | 512680147.8007

## Summary
SUMMARY |  |  |  |  | SUMMARY (Tank farm & Utilities)
Sr.no. | Description | Amount | Tax Amount |  | Sr.no. | Description | Amount | Tax Amount
A. | MATERIAL |  |  |  | 1 | Cheema boiler 2 TPH Baddi to Guwahati shifting | 9200000 | 1407500
1 | Total piping Cost (INR) | 13620461.795 | 3405115.4487 |  | 2 | 2.5 Mkcal/Hr.Petcoke boiler shifting baddi to guwahati | 15645000 | 2657025
2 | Valves Cost (INR) | 11497173 | 2874293.25 |  | 3 | New tank farm at guwahati | 168050856.5 | 31994484.8375
3 | Structural material for pipe supports | 1000000 | 250000 |  | 4 | New utilities | 23150000 | 5666750
4 | New Equipment | 23000000 | 5750000 |  | 5 | MP boiler & Fuel feeding system shifting baddi to guwahati | 28200000 | 4173000
5 | Fire fighting system cost | 2000000 | 500000 |  |  | Total tank farm & utilities Mechanical cost | 244245856.5 | 45898759.8375 | 290144616.3375
| Total amount | 51117634.795 | 12779408.6988 |  |  |  | W/O Tax | OnlyTtax | With Tax
B. | SERVICES
1 | Engineering charges | 4000000 | 580000
2 | Mechanical piping services at guwahati | 16249501 | 2356177.645
3 | Transportation (Baddi to Guwahati) | 9450000 | 1370250
4 | Filter press dismantling and re-erection | 1000000 | 145000
5 | Equipment dismantling at baddi | 3031500 | 439567.5
6 | Piping dismantling at baddi plant | 1877480 | 272234.6
7 | Insulation removal charges | 648000 | 93960
8 | Scaffolding charges | 750000 | 108750
9 | Splitting tower/D2/D3 column dismantling | 3000000 | 435000
10 | Structural dismantling at baddi plant for equipment dismantling | 1500000 | 217500
11 | Fire fighting engineering | 500000 | 72500
12 | Chemical cleaning | 1230480 | 178419.6
13 | Refurbishing of equipments/valves/pumps | 2500000 | 362500
14 | Third party inspection | 2400000 | 348000
15 | Splitting tower cutting & welding charges | 750000 | 108750
16 | Column internal removal & fixing charges | 300000 | 43500
17 | IBR services | 2500000 | 362500
18 | Material packaging and handling cost | 1500000 | 217500
19 | Vendor consulting and site visit charges | 500000 | 72500
| Total amount | 53686961 | 7784609.345
Total process plant Mechanical cost |  | 104804595.795 | 20564018.0437 | 125368613.8388
|  | W/O Tax | Only Tax | With Tax

## Comparision Services
Sr.no. | Description | Old cost | Current cost
1 | Filter Press Dismantling to Re erection in all respect | 434400 | 1000000 | INR
2 | Transportation charges Sion/ Taloja To Baddi | 6097800 | 9450000 | INR
3 | Mechanical/ Piping services at Baddi | 19676579.85 | 16249501 | INR
4 | Dismantling equipment at Sion (postcon and S/W treatment plant | 1663000 | 3031500 | INR
5 | IBR services | 3569387.5 | 2500000 | INR
6 | Onsite welding charges of W/S splitting column | 415000 | 750000 | INR
7 | Dismantling of Structures and equipments at Sion | 1906689.54 |  | INR
8 | Electrical and instrumentation services | 2606357.15 |  | INR
9 | Dismantling of utility equipments/ Tanks | 811500 |  | INR
10 | Mechanical Engineering services | 1252500 | 4000000 | INR
11 | Internal fixing charges | 70000 | 300000 | INR
12 | Fire Fighting Engineering | 280000 | 500000 | INR
13 | Electrical Engineering services | 299200 |  | INR
14 | Civil engineering services | 885000 |  | INR
15 | Inspection charges (Third party) | 106750 | 2500000 | INR
16 | Insulation services Equipment/piping/tank at Baddi | 922953 | 3016000 | INR
17 | Insulation removal charges at Sion plant | 219105 | 648000 | INR
18 | Scaffolding charges | 119390 | 750000 | INR
19 | Chemical cleaning | 557122 | 1230480 | INR
20 | Valve/ Control valve/ mechanical refurbishing cost | 1454282.73 | 2500000 | INR
21 | Civil services at Baddi | 35294789.67 |  | INR
|  | 78641806.44 | 48425481 | INR

## Comparison Material
Sr No | Items | Old Cost | New cost | Remarks
1 | New Equipment and accessories | 65590749.67 | 23000000
3 | Pipe, Pipe fittings, fastners | 17849790.59 | 13620461.795
4 | Valves | 8235014 | 11497173
5 | Plate | 6054403
6 | Structural parts | 14050822.25 | 1000000 | Only Pipe support
8 | Civil Material | 4083548
9 | Pump | 3075161.26 | 0
12 | Instrument and Electrical cost | 14887980
13 | Misc | 5982631.49 | 2000000 | Fire fighting system
| TOTAL | 223900304.48 | 51117634.795

## Material
FATTY ACID PLANT BADDI MATERIAL COST
Total piping INM
Sr No. | Item Description | Cost |  |  | Sr.no | MOC | Lurgi | Splitting | Glycerine | Total
1 | Pipe Cost (INR) | 7588001 |  |  | 1 | CS | 7105 | 1144 | 1194.5 | 9443.5
| CS Pipes | 2056010.4 |  |  | 2 | SS | 3645 | 1469.5 | 1721 | 6835.5
| SS Pipes | 7049590.8 |  |  | 3 | IBR | 426 | 363 | 0 | 789
2 | Fittings Cost @ 50% (INR) | 4552800.6 | [5 empty] | Total INM |  | 17068
| CS Fittings | 1028005.2
| SS Fittings | 3524795.4
3 | Gaskets 10 % (INR) | 910560.12
4 | Stud Bolt @ 7.5% (INR) | 569100.075
| Total piping Cost (INR) | 13620461.795
| CS Valves | 1500594
| SS Valves | 9996579
5 | Valves Cost (INR) | 11497173
Sr.no | Description | Qty | Unit | Rate | Amount
1 | Structural material for pipe supports | 20000 | KGS | 50 | 1000000
ISMB
ISMC
ISA
2 | New Equipment |  |  |  | 23000000
| Heat exchanger | 10 | Nos | 1000000 | 10000000
| SM items | 1 | AU | 1000000 | 1000000
| Pumps | 30 | Nos | 250000 | 7500000
| Valves | 1 | AU | 1000000 | 1000000
| Column/vessel internal gaskets/Stud & nuts | 1 | AU | 1000000 | 1000000
| Bellow seal valves | 1 | AU | 2500000 | 2500000
3 | Fire fighting system cost | 1 | AU | 2000000 | 2000000
Pipe/Fittings/gasket/Stud & nut
Valves/Hose box/Hose reel/Cylinders
Misc.
|  | Total |  |  | 49000000
|  | Tax @ 25% |  |  | 12250000
|  | Total amount |  |  | 61250000

## Services
Services | [5 empty] | Insulation
A. | Mechanical/piping services |  |  |  |  | Sr.no. | Description | Qty. | Unit | Rate | Amount
Sr.no | Description | Qty. | Unit | Rate | Amount | 1 | Providing and fixing of 50 MM LRB for CS piping | 1500 | M2 | 780 | 1170000
1 | Engineering charges | 1 | AU | 4000000 | 4000000 | 2 | Providing and fixing of 50 MM LRB for SS piping | 1000 | M2 | 840 | 840000
2 | ISBL -Fab and erection of cs piping | 9443 | INM | 210 | 1983030 | 3 | Providing and fixing of 50 MM LRB for CS Equipment | 700 | M2 | 900 | 630000
3 | modification of cs piping | 1500 | IND | 378 | 567000 | 4 | Providing and fixing of 50 MM LRB for SS Equipment | 400 | M2 | 940 | 376000
4 | fabrication and erection of ss piping | 6836 | INM | 336 | 2296896 |  |  |  | Total |  | 3016000
5 | Modification of ss piping | 2000 | IND | 588 | 1176000
6 | fabrication and fixing of cs shoe support | 2500 | IND | 126 | 315000
7 | fab and Fixing of ss shoe support | 3000 | IND | 147 | 441000
8 | OSBL- Fab and erection of cs piping | 1200 | INM | 140 | 168000
9 | OSBL- Fab and erection of cs piping | 1000 | INM | 140 | 140000
10 | D . P. Test | 10000 | IND | 31.5 | 315000
11 | Radiography | 5000 | IND | 341.25 | 1706250
12 | Erection of spring support-CS | 20 | NOS | 2100 | 42000
13 | Fab and fixing of cs Trunion support piping | 150 | NOS | 4200 | 630000
14 | Valve Fixing | 5000 | IND | 126 | 630000
15 | Fabrication and erection of M.S. pipe support | 20 | MT | 14700 | 294000
16 | Drilling and fixing of Anchor Fastner | 1000 | NOS | 157.5 | 157500
17 | Erection of static equipment | 270 | MT | 4725 | 1275750
18 | Erection of Rotary Equipment | 43 | MT | 5775 | 248325
19 | Material Unloading -Hydra | 700 | MT | 787.5 | 551250
20 | Material unloading-manual | 100 | MT | 525 | 52500
21 | Hydra or material handling cap-14 MT | 50 | SHF | 8925 | 446250
22 | Crane Hyring cap-150-200MT/BOOM 175 for equip.erection at guwahati | 5 | SHF | 165900 | 829500
23 | Splitting tower erection at guwahati plant
| Crane hiring charges 350 MT for splitting tower erection | 1 | AU | 1250000 | 1250000
Splitting tower welding at position
| Crane hiring charges 150 MT | 2 | SFT | 165000 | 330000
24 | MANPOWER SUPPLY FOR COMMISSIONING |  |  |  | 0
| Supervisor | 100 | SHF | 682.5 | 68250
| Pipe Fitter | 100 | SHF | 577.5 | 57750
| Argon Welder | 100 | SHF | 682.5 | 68250
| Rigger | 500 | SHF | 420 | 210000
|  |  | Total |  | 16249501
B. | Transportation (Baddi to Guwahati)
1 | Trailor for (Splitting tower/Distillation columns) | 3 | NOS | 1400000 | 4200000
2 | Open truck (16 Ton capacity/25 FT long) | 30 | NOS | 175000 | 5250000
|  |  | Total |  | 9450000
C. | Filter press dismantling and re-erection | 1 | AU | 1000000 | 1000000
1 | Insulation removal of piping
2 | Piping dismantling
3 | Filter press plates & body dismantling
4 | Filter press reerection at site
D. | Equipment dismantling at baddi | 1 | AU
1 | Equipment dismantling with shifting and loading (Static/Rotary) at baddi | 307 | MT | 4500 | 1381500
2 | Crane hiring charges 150 MT for other equipment dismantling | 10 | SFT | 165000 | 1650000
|  |  | Total |  | 3031500
E. | Piping dismantling at baddi plant | 17068 | INM | 110 | 1877480
F. | Insulation removal charges | 12000 | INM | 54 | 648000
G. | Scaffolding charges | 10000 | M2 | 75 | 750000
H. | Splitting tower/D2/D3 column dismantling | 1 | AU | 3000000 | 3000000
Crane hiring charges 600 MT (Main crane)
Crane hiring charges 350 MT (Trailing crane)
Splitting column shifting & loading
I. | Structural dismantling at baddi plant for equipment dismantling | 1 | AU | 1500000 | 1500000
J. | Fire fighting engineering | 1 | AU | 500000 | 500000
K. | Chemical cleaning | 6836 | INM | 180 | 1230480
L. | Refurbishing of equipments/valves/pumps | 1 | AU | 2500000 | 2500000
M. | Third party inspection | 400 | Visits | 6000 | 2400000
N. | Splitting tower cutting & welding charges | 1 | AU | 750000 | 750000
1 | Splitting tower cutting at baddi
2 | Splitting tower on site welding charges
O. | Column internal removal & fixing charges | 1 | AU | 300000 | 300000
P. | IBR services | 1 | AU | 2500000 | 2500000
1 | IBR piping material/fittings/valves
2 | IBR Accessories
3 | IBR preliminary approval
4 | IBR inspector visits
5 | IBR final approval
Q | Material packeging and handling cost | 1 | AU | 1500000 | 1500000
R. | Vendor consulting and site visit charges | 1 | AU | 500000 | 500000

## Equip.wt
Trailor required
Sr.no. | Description | Weight (MT)
1 | W&S Column | 65
2 | D2 column | 7
3 | D3 column | 8
Total weight |  | 80
No.of trailor required |  |  | 3 Nos
Open truck required (16MT)
Sr.no. | Description | Weight (MT)
|  | Rotary | Static
1 | W&S | 20 | #REF!
2 | Fatty acid | 8.2 | #REF!
3 | Sweet water treatment | 4.565 | 61
4 | Utility | 9.07 | 75.1
5 | Misc. | 1 | 5
6 | Other items |  | 10
Total weight |  | 42.835 | #REF! | #REF!
No.of open trucks required |  |  | #REF!
16 trucks
Note -Due to volume of equipments space required more for that extra 14 nos trucks considered

## pumps
Fatty acid plant pumps data
Tag no. | New tag no. | Description |  | Type | Area | No.of pump
P-101 |  | Crude Oil (Feed) High Pressure Pump | 1 W | R | FS | 1
P-102 |  | Crude oil / water feed High Pressure Pump | 1 S | R | FS | 1
P-103 |  | Water Feed High Pressure Pump | 1 W | R | FS | 1
P-104 A |  | Primary Fat Feed pump Oil to V- 101 | 1 W | R | FS | 1
P-105 |  | DM Water Feed Pump | 1 W | R | FS | 1
P-106 A |  | Split Fatty Acid Transfer Pump | 1 W | R | FS | 1
P-107 |  | Sweet Water Transfer Pump | 1 W | R | FS | 1
P-108 |  | Crude OIl CIrculation Pump | 1 W | R | FS | 1
P-109 |  | Interphase Drum Transfer Pump | 1 W | R | FS | 1
P-110 |  | Pit Transfer Pump | 1 W | R | FS | 1
X-101 |  | vacuum Pumps (Water Ring) | 1 W | R | FS | 1
CWP |  | Cooling Water Circulation pump | 1 W | R | FS | 1
PF-1 |  | Fat/Oil Transfer Pump from fat trap | 1 W | R | FS | 1
PW-1 |  | Water Transfer Pump from fat trap | 1 W | R | FS | 1
P-301 A/B | G-1 A/B | Feed to D1/D2 | 1W+1S | R | Lurgi | 2
P-304 A/B | G-4 A/B | Th.oil circulation to E8 | 1W+1S | R | Lurgi | 2
P-305 A/B | G-5 A/B | D2 bottom to D3 | 1W+1S | R | Lurgi | 2
P-308 A/B | G-8 A/B | Residue transfer pump | 1W+1S | R | Lurgi | 2
P-309 A/B | G-9 A/B | DM water to E12 | 1W+1S | R | Lurgi | 2
P-311 A/B | G-11 A/B | Th.oil circulation to E11 | 1W+1S | R | Lurgi | 2
P-312 A/B | G-12 A/B | Th.oil circulation to D03 | 1W+1S | R | Lurgi | 2
P-314 A/B | G-14 A/B | C.W.circulation to E12 | 1W+1S | R | Lurgi | 2
P-318 A/B | G-18 A/B | Heavy end transfer pump | 1W+1S | R | Lurgi | 2
P-310 A/B | G-10 A/B | Tempered water pump | 1W+1S | R | Lurgi | 2
P-320 A/B | G-20 A/B | C.W.circulation to E20 | 1W+1S | R | Lurgi | 2
P-321 A | G-21 A | Hotwell pump | 1W | R | Lurgi | 1
G-22 | G-22 | Vacuum pump | 1W | R | Lurgi | 1
P-302 A/B | G-2 A/B | Main dist.transfer pump | 1W+1S | R | Lurgi | 2
P-303 A/B | G-3 A/B | L/E transfer pump | 1W+1S | R | Lurgi | 2
P-306 A/B | G-6 A/B | Feed pump to D1 | 1W+1S | R | Lurgi | 2
G-7 | G-7 | Main dist.booster pump | 1W | R | Lurgi | 1
P-313 A/B | G-13 A/B | C.W.Circulation to E-10 | 1W+1S | R | Lurgi | 2
P-319 A/B | G-19 A/B | Th.oil circ.to E03 | 1W+1S | R | Lurgi | 2
P-201 | P- 6 (F-6) | Seperated Oil Transfer Pump ( From Sepeartion tank to Oil Collection tank ) | 1 W | R | SW | 1
P-202 A/B | P7 & P8 | Sweet water Feed Pump to 1st Treatment | 1 W | R | SW | 1
P-203 |  | 1st treated water FP-1 feed pump | 1 W | R | SW | 1
P-204 |  | 2nd treated water FP-2 feed pump | 1 W | R | SW | 1
P-205 | P-C7 | Filtrate Transfering Pump | 1 W | R | SW | 1
P-206 -I |  | Hydraulic Unit Open/Close device for FP-201 | 1 W | R | SW | 1
P-206 - II |  | Hydraulic Unit Open/Close device for FP-202 | 1 W | R | SW | 1
P-207 |  | Skimmed Oil Transfer Pump | 1 W | R | SW | 1
P-208 A/B | P-3 A/B | Sweet Water Circulation Pumps of 2nd Effect (A/B ) evaporators | 2 W | R | SW | 2
P-209 | G-20A | Surface Condenser Cooling Water Pump | 1 W | R | SW | 1
P-210 | P-21 | Vacuum Pump of Post Concentration | 1 W | R | SW | 1
P-211 | P-4 | Condensate Transfer Pump. | 1 W | R | SW | 1
P-212 A/B | P-4 A/B | Crude Glycerine Transfer Pump. | 1 W + 1 S | R | SW | 2
P-213 |  | Dirty Condensate Transfer Pump | 1 W | R | SW | 1
P-214 |  | Clean Condensate Transfer Pump | 1 W | R | SW | 1
P-215 |  | Filter leackage Sweet Water Transfer Pump | 1 W | R | SW | 1
P-9004 |  | a. To Vacuum system Lurgi ( Direct type) | 1 W+1 S | R | Utility | 2
P-9001 |  | b. To Surface Condenser | 1 W | R | Utility | 1
P-9002 A& B or P-9003 |  | c. To Vapor Condenser | 1 W | R | Utility | 1
|  | d. Tempered Water System (Lurgi) | 1 W | R | Utility | 1
|  | e. To E-103 of Splitter | 1 W | R | Utility | 1
|  | Chemical Dosing System | 1W | R | Utility | 1
AC-9101 |  | Air Compressor | 1W | R | Utility | 1
NPP-9203 |  | Neutralisation Pit Transfer Pump | 1W | R | Utility | 1
DMTP-9204 A |  | D.M. Water Transfer Pump | 1W | R | Utility | 1
BFTP-9205 A/B |  | Boiler Feed Transfer Pump | 1W | R | Utility | 1
P-9402 |  | F.O. Transfer pump | 1W | R | Utility | 1
P-9301 |  | Boiler Condensate Transfer pump | 1W | R | Utility | 1
|  | Chemical Dosing system | 1W | R | Utility | 1
Located At ETP |  | Effluent Transfer Pump( P-9801) | 1W | R | Utility | 1
HSDP-9403 |  | HSD Tranfer Pump | 1W | R | Utility | 1
P-9303 |  | Barrel Unloading pump | 1W | R | Utility | 1
MBTP-9206 |  | M.B.Water transfer pump | 1W | R | Utility | 1
THPT-9501 , THP-9502 |  | Thermic Fluid unloading sytem at Tank farm | 1W | R | Utility | 1
P-8007 |  | Tank Form condensate transfer pump | 1W | R | TF | 1
P-8001 A&B |  | Unloading Pumps for Oil / CFA | 1W+ 1W | R | TF | 2
P-8002 |  | Feed Pump for W&S Splitter | 1W | R | TF | 1
P-8003 |  | Feed Pump for Lurgi Distillation | 1W | R | TF | 1
P-8004 |  | Unloading Pumps for Crude Glycerin | 1W | R | TF | 1
P-8005 |  | Residue Unloading pump | 1W | R | TF | 1
P-8006 A |  | DFA Transfer pump to Saponification plant | 1W | R | TF | 1
|  | Condensate Transfer Pump | 1W | R | TF | 1
|  | Effluent Transfer Pump( P-9801) | 1W | R | TF | 1
|  |  |  | total no of pumps |  | 96

## W&S
EQUIPMENT LIST
FAT SPLITTING PLANT( W &S Column)
CAPACITY 5.6-10 TPH
Sr.No | Eqpt No. | Title | Working/Standby | Type | Area Code | Brief Specs. |  |  | Empty Wt. (Tons) | Source of supply | Remarks | Revison
1 | C-101 | Wruster & Sanger Splitting Column | 1 W | S | FS | Type : Column | Opearating press.- 50Bar(a) |  | 65 | Existing | Sion Plant W&S Spiltter to be modified for 48 meters tan to tan Height. | Rev.3
[6 empty] | Capacity : 57 M3 | Design temp - 282°c |  |  |  |  | 30/12/09
[6 empty] | Dimns'n: Ø 1219ID x 48000 shell ht. | Thickness - 38 mm
[6 empty] | MOC : A 240 TP 316 L | Designed pressure:-55 Bar(a)
Water Filled Wt. 122 T
2 | V-101 | Crude Oil Deaerator | 1 W | S | FS | Type : Vessel | Opearating press.- 60 torr |  | 1.2 | Existing | Sion Plant Equipment as it is basis.
[6 empty] | Capacity : 1.878 M3 | operating temp -: 140 °C
Dimension : Ø 1000 x 2120
MOC : SS 316 L
Process fluid - : Oil/Fatty Acid
3 | E-101 A/B/C | Crude Oil / Split Fatty Acid Heat Exchanger | 1 W | S | FS | Type : Shell & Tube (U-tube Bundle) | Design press.- 8 Bar |  | 1.8 | Existing | Sion Plant Equipment as it is basis.
[6 empty] | HTA : 6.15 M2 each | Design temp -125°C
[6 empty] | Dimension : | SFA - : IN-98°C OUT-70°C
[6 empty] | MOC : 316 L | Cr.Oil -: IN-35- 55°C OUT- 82°C
[6 empty] | Crude 0il feed rate | 10000Kg/Hr
[6 empty] | SFA | 10000Kg/Hr
4 | E-102 | Crude Oil Pre-Heater | 1 W | S | FS | Type : Spiral HE | Design press.- 8 Bar |  | 1 | Existing | Sion Plant Equipment as it is basis.
[6 empty] | HTA : * M2 | Design temp -200 °C
[6 empty] | Dimension : | Steam - : IN-140°C.Cond.OUT-140°C
[6 empty] | MOC : 316 L | Cr.Oil -: IN-35- 55°C OUT- 121°C
[6 empty] | Crude 0il feed rate | 10000Kg/Hr
[6 empty] | MP Steam | 1100 Kg/Hr
5 | E-204 B | FA Flash Vapour Condensor | 1 W | S | FS | Type : Shell / Tube |  |  | 1.2 | Existing | Sion Plant Equipment as it is basis.
HTA : 20M2
[6 empty] | Dimension : | SHELL | TUBE
[6 empty] | Length (mm) | 2000 | 2000
[6 empty] | Outer Diameter (mm) | 460 | 25.4
[6 empty] | No. of tubes |  | 130
[6 empty] | No. of passes | 1 | 2
[6 empty] | Thickness (mm) | 5 | 16 BWG
[6 empty] | Pitch |  | 1.25 od ,Triangular
[6 empty] | Operating temp (°C) | 100 | 50
[6 empty] | Operating Pressure ( Kg/cm2) | FULL VACUUM | 8
[6 empty] | MOC | SA 312 TP 316L | SA 213 TP 316L
6 | E-103 | Split Fatty Acid Cooler | 1 W | S | FS | Type : Shell &Tube |  |  | 1.1 | Existing | Sion Plant Equipment as it is basis
[6 empty] | Tube pass: 4 Nos. | Design press.- 8 Bar
[6 empty] | HTA : 15 m^2 | Design temp :-125° C
[6 empty] | Dimension: Dia.0.261X 5.4M Length | SFA - : IN-98°C OUT-68°C
[6 empty] | MOC : 316 L | Water -: IN- 35°C OUT- 43°C
[6 empty] | Cooling Water | 28000__Kg/Hr
[6 empty] | SFA | 10000Kg/Hr
7 | E-205 A | Sweet Water Flash Vapor Cooler | 1 W | S | FS | Type : Shell / Tube |  |  | 1.2 | Existing | Sion Plant Equipment as it is basis.
HTA : 20M2
[6 empty] | Dimension : | SHELL | TUBE
[6 empty] | Length (mm) | 2000 | 2000
[6 empty] | Outer Diameter (mm) | 460 | 25.4
[6 empty] | No. of tubes |  | 130
[6 empty] | No. of passes | 1 | 2
[6 empty] | Thickness (mm) | 5 | 16 BWG
[6 empty] | Pitch |  | 1.25 od ,Triangular
[6 empty] | Operating temp (°C) | 100 | 50
[6 empty] | Operating Pressure ( Kg/cm2) | FULL VACUUM | 8
[6 empty] | MOC | SA 312 TP 316L | SA 213 TP 316L
8 | V-105 ( C2 ) | Feed Water Tank | 1 W | S | FS | Type : Cylindrical Tank | Operating pressure -: ATMS |  | 1.8 | Existing | Sion Plant Equipment as it is basis.
[6 empty] | Capacity : 17 M3 | Operating temp- 85°C
Dimension : Ø 2100 x 5000 mm
Thickness - : mm
MOC : SS 304
9 | V-103 | Fatty Acid Dehydrator | 1 W | S | FS | Type : Vessel |  |  | 0.8 | Existing | Sion Plant Equipment as it is basis
Capacity : 1.96 M3
[6 empty] | Dimension : Ø 1.02 x 2.0 m | Shell | Limpet Coil
[6 empty] | Thickness (mm) | 6 | sch 40
[6 empty] | Diameter | 1020 | 25
[6 empty] | Height | 2000
[6 empty] | Operating pressure (Kg/Cm2 a) | 0.12 | 4
[6 empty] | Operating temp ( °C) | 110 | 144
[6 empty] | MOC | SS 316 L | SS 316 L
10 | V-104 | Sweet Water Flash Vessel | 1 W | S | FS | Type : Vessel | Operating pressure -: 1 Kg/cm2(g) |  | 0.8 | Existing | Sion Plant Equipment as it is basis
[6 empty] | Capacity : 3.2 M3 | Operating temp- 150°C
Dimension : Ø 1.35 X 1.84 M
Thickness - : 6 mm
MOC : SS 316L
11 | INT. Drum | Interphase Drum | 1 W | S | FS | Type : | Operating pressure -: Atm. |  | 0.2 | Existing | Sion Plant dimensions as it is basis
[6 empty] | Capacity : M3 | Operating temp-
Dimension :
MOC :
12 | PIT | Underground Pit | 1 W | S | FS | Dimension : 1000 L X 500 W X 500 H mm | To be made in W&S area |  |  | New | Civil Work
Civil Work
13 | V-106 | Steam Separator (V-106) IBR | 1 W | S |  | Type : |  |  | 0.2 | Existing | Sion Plant Equipment.
Capacity : 3 T / Hr.
Pressure : 58 Bar g
MOC : CS /Boiler grade
14 | F-101 A/B | Duplex Filter | 1 W | R | FS | Type : Basket Type | Operating pressure -: 4 Kg/cm2(g) |  | 1 | Existing | Sion Plant Equipment as it is basis
[6 empty] | Capacity : 10 TPH | Operating temp- 150°C
Mesh Size :
Pressure drop -: 0.5 Kg/Cm2
MOC : 316 L
15 | P-101 | Crude Oil (Feed) High Pressure Pump | 1 W | R | FS | Type : Reciprocating |  |  | 4 | Existing | W & S Plant Equipment P-101 of Sion will be used as it is basis.
Capacity : MT / Hr
Diff. Head : 58 Kg/Cm2
MOC : SS 316L
16 | P-102 | Crude oil / water feed High Pressure Pump | 1 S | R | FS | Type : Reciprocating |  |  | 4 | Existing | W & S Plant Equipment P-102 of Sion will be used as it is basis.
Capacity : MT / Hr
Diff. Head : 58 Kg/Cm2
MOC : SS 316L
17 | P-103 | Water Feed High Pressure Pump | 1 W | R | FS | Type : Reciprocating |  |  | 4 | Existing | W & S Plant Equipment P-103 of Sion will be used as it is basis.
Capacity : 8.5 MT / Hr
Diff. Head : 58 Kg/Cm2
MOC : SS 316L
18 | P-104 A | Primary Fat Feed pump Oil to V- 101 | 1 W | R | FS | Type : Centrifugal |  |  | 1 | Existing | TO be arranged from Sion Plant. Pump near R1/R2 . Considered in Tank farm area.
Capacity : 30 M3 / Hr
Diff. Head : 60 MLC
MOC : SS 316L
19 | P-105 | DM Water Feed Pump | 1 W | R | FS | Type : Centrifugal |  |  | 1 | Existing | W&S Plant Equipment P-105A of Sion will be used for this duty.
Capacity : 9 M3/Hr
Diff. Head : 15 MLC
MOC : SS 316
20 | P-106 A | Split Fatty Acid Transfer Pump | 1 W | R | FS | Type : Centrifugal |  |  | 1 | Existing | W&S Plant Equipment P-106A of Sion will be used for this duty.
Capacity : M3/Hr
Diff. Head : MLC
MOC : SS 316L
21 | P-107 | Sweet Water Transfer Pump | 1 W | R | FS | Type : Centrifugal |  |  | 0.6 | Existing | Existing P-106 B of Sion plant will be used for this duty.
Capacity : M3/Hr
Diff. Head : MLC
MOC : SS 316L
22 | P-108 | Crude OIl CIrculation Pump | 1 W | R | FS | Type : Centrifugal |  |  | 0.6 | Existing | W&S Plant Equipment P-108 of Sion will be used for this duty.
Capacity : M3/Hr
Diff. Head : MLC
MOC : SS 316L
23 | P-109 | Interphase Drum Transfer Pump | 1 W | R | FS | Type : Centrifugal |  |  | 0.5 | Existing | Sion Plant Equipment as it is basis
Capacity : M3/Hr
Diff. Head : MLC
MOC : SS 316
24 | P-110 | Pit Transfer Pump | 1 W | R | FS | Type : Centrifugal |  |  | 0.4 | Existing | Sion Plant Equipment as it is basis
Capacity : M3/Hr
Diff. Head : MLC
MOC : SS 316
25 | X-101 | vacuum Pumps (Water Ring) | 1 W | R | FS | Type : Vacuum |  |  | 0.5 | Existing | Sion Plant Equipment as it is basis
Air suction Capacity : M3/Hr
Suction Temp - : 45°C
System volume - : m^3
MOC : SS 316L
26 | CWP | Cooling Water Circulation pump | 1 W | R | FS | Type : Centrifugal |  |  | 1 | Existing | Cooling water from cooling tower pump.
Capacity : 65 M3/Hr
Diff. Head : 40 MLC
MOC : CS
27 | FT | Fat trap | 1 W | S | FS | Type : Underground pit |  |  |  | New | Drwg. is made for Civil work
Civil Work
Dimension : 3500 L X1750W X1750 H mm
28 | PF-1 | Fat/Oil Transfer Pump from fat trap | 1 W | R | FS | Type : Centrifugal |  |  | 0.2 | New | Pump ordered
Capacity : 3 M3/Hr
Diff. Head : 30 MLC( With negative suction)
MOC : CS
29 | PW-1 | Water Transfer Pump from fat trap | 1 W | R | FS | Type : Centrifugal |  |  | 0.2 | New | Pump ordered
Capacity : 3 M3/Hr
Diff. Head : 30 MLC( With negative suction)
MOC : CS
[8 empty] | TOTAL WEIGHT | 74.2 MT
Note on C6: Author: REV.3 30/12/2009

## Fatty acid
|  | EQUIPEMENT LIST OF LURGI F.A DISTILLATION UNIT AT BADDI ( SHIFTED FROM SION ) | [9 empty] | Date: 30/ 12 / 2009 . Rev.02
DOC.NO- VVF-BADDI-PE-002
| ITEM Tag. No |  | DESCRIPTION | QTY. | PRESSURE | TEMP | MATERIAL | DRG.NO | REV. | VENDOR | SOURCE OF | Remarks | Revision | TYPE | WEIGHT (mt)
Sr.No | NEW | OLD |  | NO | ABS.(BAR) | * C |  |  |  |  | SUPLLY
1 | D-301 | D1 | DRIER | 1 | VAC | 120 | 1.4571/316L | 1PC-D-615 | D | GANSON | Existing From Sion | Sion plant eqpt. as it is basis |  | S | 0.7
[8 empty] | 1PC-D-615/1 | D
|  |  | INCLUDING SPRAY NOZZLE | 1
|  |  | CERAMIC SADDLES | 1 |  |  | CERAMIC
|  |  | DEMISTER |  |  |  | 1.4571
2 | C-301 | D2 | PRECUT-COLUMN | 1 | VAC | 275 | 1.4571/316L | 6PC-D-613 | B | GANSON | Existing From Sion | Sion plant eqpt. as it is basis with modification for structured packing. | Rev.2 | S | 6
[8 empty] | 6PC-D-613/1 | B |  |  |  | 30/12/09
|  |  | THORMANN-TRAYS | 24 |  |  | 1.4435/1.4571 | [7 empty] | 1
3 | C-302 | D3 | DISTILLATION-STILL | 1 | VAC | 275 | 1.4571/316L | 1PC-D-614 | B | GANSON | Existing From Sion | Sion plant eqpt. as it is basis |  | S | 8
|  |  | WITH HEAVY ENDS SEPARATION |  |  |  |  | 1PC-D-614/1 | B
[8 empty] | 1PC-D-614/2 | B
|  |  | THORMANN-TRAY | 1 |  |  | 1.4571/316L
|  |  | DEMISTER PACKING | 1 |  |  | CERAMIC
|  |  | HEATING ELEMENTS | 2 |  |  | 1.4571/317L | 7PC-D-610/1 | G/E | GANSON
4 | D-302 | D4 | DEMISTER WITH COOLER | 1 | VAC/6 | 120 | 1.4571/316L | 7PC-D-624 | A | GANSON | Existing From Sion | Sion plant eqpt. as it is basis |  | S | 1.5
5 | D-303 | E13 (old) | FINAL CONDENSER(U-TUBE TYPE) | 1 | VAC/4 | 220 | 1.4571/316L | 7PC-D-608 | B | GANSON | Existing Old E-13 From Sion | Sion plant eqpt. as it is basis | Rev.2 30/12/09
6 | E-301 | E1 | HEATER(SHELL / TUBE) | 1 | 5 | 150 |  | 7PC-D-626 | B | GANSON | Existing From Sion | Sion plant eqpt. as it is basis |  | S | 2.5
|  |  | SHELL |  |  |  | C-STEEL | 7PC-D-626/1 | D
|  |  | TUBE |  |  |  | 1.4571/316L
7 | E-302 | E2 | HEAT-EXCHANGER(SPIRAL TYPE) | 1 | VAC/4 | 220 | 1.4571 | NU-2034 | 0 | L&T | Existing From Sion | Sion plant eqpt. as it is basis |  | S | 2.5
8 | E-303 | E3 | PRE-HEATER(SHELL / TUBE) | 1 | VAC/6 | 250 |  | 7PC-D-627 | B | GANSON | Existing From Sion | Sion plant eqpt. as it is basis |  | S | 3
|  |  | SHELL |  |  |  | C-STEEL
|  |  | TUBE |  |  |  | 1.4571/316L
9 | E-304 | E4 | HEAT-EXCHANGER(PLATE TYPE) | 1 | 6 | 150 | 1.4401 | 280762 | 1 | ALFA-LAVAL | Existing From Sion | Sion plant eqpt. as it is basis |  | S | 0.152
10 | E-305 | E5 | HEAT-EXCHANGER(SPIRAL TYPE) | 1 | VAC/4 | 275 | 1.4571 | NU-2035 | 0 | L&T | Existing From Sion | Sion plant eqpt. as it is basis |  | S | 1
11 | E-306 | E6 | COOLING BUNDLE FOR RESIDUE | 1 | 6 | 275 | 1.4571 | 7PC-D-619 | D | GANSON | Existing From Sion | Sion plant eqpt. as it is basis |  | S | 0.74
|  |  | RECEIVER |  |  |  |  | 7PC-D-619/1 | C
[8 empty] | 7PC-D-619/2 | B
12 | E-307 | E7 | CONDENSER/STEAM GENERATOR | 1 | VAC/6 | 250 | 1.4571/316L | 7PC-D-621 | B | GANSON | Existing From Sion | Sion plant eqpt. as it is basis |  | S | 2.5
FOR HEAVY ENDS(U-TUBE TYPE)
13 | E-308 | E8 | REBOILER FOR D2 | 1 | VAC/6 | 300 |  | 7PC-D-611 | D | GANSON | Existing From Sion | Sion plant eqpt. as it is basis |  | S | 2.44
|  |  | SHELL |  |  |  | 1.4571/316L
|  |  | TUBE |  |  |  | 1.4435/317L
14 | E-310 | E12 (Old) | CONDENSER/STEAM GENERATOR | 1 | VAC/6 | 250 |  | 7PC-D-609 | B | GANSON | Existing Old E-12 From Sion | Sion plant eqpt. as it is basis | Rev.2 | S | 2.1
|  |  | SHELL |  |  |  | C-STEEL | [5 empty] | 30/12/09
|  |  | TUBE |  |  |  | 1.4571/316L
15 | E-311 | E11 | REBOILER FOR D3 | 1 | VAC/6 | 300 |  | 7PC-D-612 | B | GANSON | Existing From Sion | Sion plant eqpt. as it is basis |  | S | 3.29
|  |  | SHELL |  |  |  | 1.4571/316L | 7PC-D-612/1 | D
|  |  | TUBE |  |  |  | 1.4435/317L
16 | E-312 | E12 | CONDENSER/STEAM GENERATOR | 1 | VAC/6 | 250 |  | 7PC-D-609 | B | GANSON | Existing From Sion | Sion plant eqpt. as it is basis |  | S | 2.1
|  |  | SHELL |  |  |  | C-STEEL
|  |  | TUBE |  |  |  | 1.4571/316L
|  | EQUIPEMENT LIST OF LURGI F.A DISTILLATION UNIT AT BADDI ( SHIFTED FROM SION ) | [9 empty] | Date: 30/ 12 / 2009 . Rev.02
DOC.NO- VVF-BADDI-PE-002
| ITEM Tag. No |  | DESCRIPTION | QUANTITY | PRESSURE | TEMP | MATERIAL | DRG.NO | REV. | VENDOR | SOURCE OF | Remarks | Revision
Sr.No | NEW | OLD |  | NO | ABS.(BAR) | * C |  |  |  |  | SUPLLY
17 | E-313 | E13 | FINAL CONDENSER(U-TUBE TYPE) | 1 | VAC/4 | 220 | 1.4571/316L | 7PC-D-608 | B | GANSON | Existing From Sion | Sion plant eqpt. as it is basis |  | S | 2
18 | E-314 | E14 | DISTILLATE COOLER (PLATE TYPE) | 1 | 6 | 150 | 1.4401 | 280763 | 1 | ALFA-LAVAL | Existing From Sion | Sion plant eqpt. as it is basis |  | S | 0.166
19 | E-315 | E15 | HEAT-EXCHANGER(PLATE TYPE) | 1 | 6 | 150 | 1.4401 | 280764 | 1 | ALFA-LAVAL | Existing From Sion | Sion plant eqpt. as it is basis |  | S | 0.171
20 | E-316 | E16 | FINAL CONDENSER(U-TUBE TYPE) | 1 | VAC/4 | 220 | 1.4571/316L | 7PC-D-623 | B | GANSON | Existing From Sion | Sion plant eqpt. as it is basis |  | S | 0.6
21 | E-317 | E17 | COOLER FOR PREFRACTON(PLATE) | 1 | 6 | 150 | 1.4401 | 280765 | 1 | ALFA-LAVAL | Existing From Sion | Sion plant eqpt. as it is basis |  | S | 0.29
22 | E-318/319 | E18/19 | JET CONDENSER | 2 | VAC | 100 | 1.4571/316L | 1357-509-2 |  | WIEGAND | Existing From Sion | Sion plant eqpt. as it is basis |  | S | 0.3
23 | E-320 | E20 | WCT-COOLER(PLATE TYPE) | 1 | 6 | 80 | 1.4301 | 280766 | 1 | ALFA-LAVAL | Existing From Sion | Sion plant eqpt. as it is basis |  | S | 0.175
24 | E-321 | E21 | JET CONDENSER | 1 | VAC | 100 | 1.4571/316L | 1355-509-2 |  | WIEGAND | Existing From Sion | Sion plant eqpt. as it is basis |  | S | 0.3
25 | E-322 | E22 | COOLING BUNDLE FOR HEAVY END | 1 | 6 | 250 | 1.4571 | 7PC-D-620/1/2 | E/B/C | GANSON | Existing From Sion | Sion plant eqpt. as it is basis |  | S | 0.63
RECEIVER
26 | F-301 | F1 | DISTILLATE RECEIVER | 1 | VAC | 180 | 1.4571/316L | 1PC-D-617 | B | GANSON | Existing From Sion | Sion plant eqpt. as it is basis |  | S | 0.2
[8 empty] | 1PC-D-617/1 | C
27 | F-302 | F2 | HEAVY ENDS RECEIVER | 1 | VAC | 250 | 1.4571/316L | 7PC-D-620 | E | GANSON | Existing From Sion | Sion plant eqpt. as it is basis |  | S | 0.63
[8 empty] | 7PC-D-620/1 | B
[8 empty] | 7PC-D-620/2 | C
28 | F-303 | F3 | PREFRACTION RECEIVER | 1 | VAC | 180 | 1.4571/316L | 1PC-D-616 | B | GANSON | Existing From Sion | Sion plant eqpt. as it is basis |  | S | 0.2
29 | F-304 | F4 | RESIDUE RECEIVER | 1 | VAC | 270 | 1.4571/316L | 7PC-D-619 | D | GANSON | Existing From Sion | Sion plant eqpt. as it is basis |  | S | 0.74
[8 empty] | 7PC-D-619/1 | C
[8 empty] | 7PC-D-619/2 | B
30 | F-305 | F5 | HOT WELL | 1 | Atmosperic | 60 | 1.4571/304 | D6513300017 | O | LURGI | Existing From Sion | Sion plant eqpt. as it is basis |  | S | 1
31 | F-306 | F6 | WCT-EXPANSION VESSEL | 1 | Atmosperic | 80 | C-STEEL | D6513300016 | O | LURGI | Existing From Sion | Sion plant eqpt. as it is basis |  | S | 1.2
32 | F-307 | F7 | STEAM VESSEL | 1 | 4 | 150 | C-STEEL | 1PC-D-618 | A | GANSON | Existing From Sion | Sion plant eqpt. as it is basis |  | S | 0.735
33 |  |  | Vacuum system | 1 | [6 empty] | Existing From Sion | Sion plant eqpt. as it is basis | Rev.2 30/12/09 | S | 3
34 |  |  | Dosiing Systems ( BHT & Boric Acid) | [7 empty] | Existing From Sion | Sion plant eqpt. as it is basis | Rev.2 30/12/09 | S | 0.5
35 | Thermic Fluid Pit with transfer pump in plant. Pump tag no. P-9503 |  |  | 1W | R |  | 1 m3 Pit- Civil work Dimension; 1 mt H x 1mt W X 1mt L. |  |  |  | New | Drain Pit with pumping arrangement. 1 m3 underground Pit with Pump ( Pump of 3m3/hr & 40 mtr Head, CS pump ) | Pump Ordered | R | 0.2
36 | P-301 A/B | G-1 A/B | Feed to D1/D2 | 1W+1S | [9 empty] | R | 0.3
37 | P-304 A/B | G-4 A/B | Th.oil circulation to E8 | 1W+1S | [9 empty] | R | 0.4
38 | P-305 A/B | G-5 A/B | D2 bottom to D3 | 1W+1S | [9 empty] | R | 0.35
39 | P-308 A/B | G-8 A/B | Residue transfer pump | 1W+1S | [9 empty] | R | 0.2
40 | P-309 A/B | G-9 A/B | DM water to E12 | 1W+1S | [9 empty] | R | 0.5
41 | P-311 A/B | G-11 A/B | Th.oil circulation to E11 | 1W+1S | [9 empty] | R | 0.6
42 | P-312 A/B | G-12 A/B | Th.oil circulation to D03 | 1W+1S | [9 empty] | R | 0.4
43 | P-314 A/B | G-14 A/B | C.W.circulation to E12 | 1W+1S | [9 empty] | R | 0.5
44 | P-318 A/B | G-18 A/B | Heavy end transfer pump | 1W+1S | [9 empty] | R | 0.5
45 | P-310 A/B | G-10 A/B | Tempered water pump | 1W+1S | [9 empty] | R | 0.6
46 | P-320 A/B | G-20 A/B | C.W.circulation to E20 | 1W+1S | [9 empty] | R | 0.6
47 | P-321 A | G-21 A | Hotwell pump | 1W | [9 empty] | R | 0.15
48 | G-22 | G-22 | Vacuum pump | 1W | [9 empty] | R | 0.2
49 | P-302 A/B | G-2 A/B | Main dist.transfer pump | 1W+1S | [9 empty] | R | 0.3
50 | P-303 A/B | G-3 A/B | L/E transfer pump | 1W+1S | [9 empty] | R | 0.4
51 | P-306 A/B | G-6 A/B | Feed pump to D1 | 1W+1S | [9 empty] | R | 0.5
52 | G-7 | G-7 | Main dist.booster pump | 1W | [9 empty] | R | 0.2
53 | P-313 A/B | G-13 A/B | C.W.Circulation to E-10 | 1W+1S | [9 empty] | R | 0.6
54 | P-319 A/B | G-19 A/B | Th.oil circ.to E03 | 1W+1S | [9 empty] | R | 0.7

## sweet water treatment
EQUIPMENT LIST
SWEET WATER TREATMENT & EVAPORATION PLANT AT BADDI
Sr.No | Eqpt No. Tag. No |  | Title | Working/Standby | Type | Area Code | Brief Specs. |  |  | Empty Wt. (Tons) | Source of supply | Remarks | Revision
| New | Old
1 | T-201 | SP.TK1-TK5 | Seperation Tank | 1 W | S | SW | Type : Rectangular Tank | Opearating press.: | Design pressure : | 5 | Existing Eqpt.from Sion | Sion plant equipment as it is basis.
[7 empty] | Capacity : | Operating temp : °C | Design temperature: °C
[7 empty] | Dimension : 2000 W x 10,000 L X 1600 H mm | Thickness : mm
MOC : SS 304
2 | T-202 | C-1 | 1st Treatment Tank 1 | 1 W | S | SW | Type : Cylindrivcal Tank with Conical bottom | Opearating press.: | Design pressure : | 3 | Existing Eqpt.from Sion | Sion plant equipment as it is basis.
[7 empty] | Capacity : | Operating temp : °C | Design temperature: °C
[7 empty] | Dimension : Ø3100 X 7000 mm | Thickness : mm
MOC : SS 304
3 | T-203 | C-2 | 1st Treatment Tank 2 | 1 W | S | SW | Type : Cylindrivcal Tank with Conical bottom | Opearating press.: | Design pressure : | 3 | Existing Eqpt.from Sion | Sion plant equipment as it is basis.
[7 empty] | Capacity : | Operating temp : °C | Design temperature: °C
[7 empty] | Dimension : Ø3100 X 7000 mm | Thickness : mm
MOC : SS 304
4 | T-204 | C-3 | 2nd Treatment Tank | 1 W | S | SW | Type : Cylindrivcal Tank with Conical bottom | Opearating press.: | Design pressure : | 3 | Existing Eqpt.from Sion | Sion plant equipment as it is basis.
[7 empty] | Capacity : | Operating temp : °C | Design temperature: °C
[7 empty] | Dimension : Ø3100 X 7000 mm | Thickness : mm
MOC : SS 304
5 | T-205 | C-4 | Feed Tank for Concentration Plant | 1 W | S | SW | Type : Cylindrivcal Tank with Conical bottom | Opearating press.: | Design pressure : | 3 | Existing Eqpt.from Sion | Sion plant equipment as it is basis.
[7 empty] | Capacity : | Operating temp : °C | Design temperature: °C
[7 empty] | Dimension : Ø3100 X 7000 mm | Thickness : mm
MOC : SS 304
6 | T-206 | C-5 | Oil Collection Tank from Seperation Tank | 1 W | S | SW | Type : Cylindrivcal Tank | Opearating press.: | Design pressure : | 0.7 | Existing Eqpt.from Sion | Sion plant equipment as it is basis.
[7 empty] | Capacity : | Operating temp : °C | Design temperature: °C
[7 empty] | Dimension :1900 L X 1200 W X 950 H mm | Thickness : mm
MOC : CS
7 | T-207 |  | Skimmed Oil Tank | 1 W | S | SW | Type : Rectangular Tank | Opearating press.: | Design pressure : | 1 | New | Tank drwg is available. Ordered
[7 empty] | Capacity : 3 m3 | Operating temp : °C | Design temperature: °C
[7 empty] | Dimension :3000 L X 1000 W X 1000 H mm | Thickness : mm
MOC : CS
8 | FP-201 |  | Filter Press 1 | 1 W | S | SW | Type : Plate & Frame Leaf filter | Opearating press.: | Design pressure : | 12 | Existing DINSHAW filter from Taloja plant. | Taloja plant equipment as it is basis.
[7 empty] | Capacity : | Operating temp : °C | Design temperature: °C
[7 empty] | Dimension : 5100 L X 800 W X 1900 H mm | Thickness : mm
Filter Height is including pedestrail
MOC :
9 | FP-202 |  | Filter Press 2 | 1 W | S | SW | Type : Plate & Frame Leaf filter | Opearating press.: | Design pressure : | 12 | New | Ordered Placed on Bhatwadekar. To be delivered at Baddi .
[7 empty] | Capacity : | Operating temp : °C | Design temperature: °C
[7 empty] | Dimension : Ø X mm | Thickness : mm
MOC :
10 | V-201 / E-201 / CV-201 | STAGE 1 | 1st Effect Evaporator system (A) | 1 W | S | SW | Flash Chamber |  |  | 3 | Existing Eqpt.from Sion | Sion plant equipment as it is basis.
Capacity :
Dimension : Ø 1500 X 3000 mm
MOC : CS
Evaporator Type : Shell & Tube
HTA : 50m2
[7 empty] | Dimension : | SHELL | TUBE
[7 empty] | Length (mm) | 3500 | 1500
[7 empty] | Outer Diameter (mm) | 1050 | 50 NB
[7 empty] | No. of tubes |  | 187
[7 empty] | No. of passes | 1 | 1
[7 empty] | Thickness (mm) |  | 2.11
Pitch
Operating temp (°C)
Operating Pressure ( Kg/cm2)
[7 empty] | MOC | CS | SS 304
11 | V-202 / E-202 / CV-202 | STAGE 3A | 2nd Effect Evaporator system (A) | 1 W | S | SW | Flash Chamber |  |  | 3 | Existing Eqpt.from Sion | Sion plant equipment as it is basis.
Capacity :
Dimension : Ø 1500 X 3000 mm
MOC : CS
Evaporator Type : Falling Film Shell & Tube
HTA : 50m2
[7 empty] | Dimension : | SHELL | TUBE
[7 empty] | Length (mm) | 3500 | 1500
[7 empty] | Outer Diameter (mm) | 1050 | 50 NB
[7 empty] | No. of tubes |  | 187
[7 empty] | No. of passes | 1 | 1
[7 empty] | Thickness (mm) |  | 2.11
Pitch
Operating temp (°C)
Operating Pressure ( Kg/cm2)
[7 empty] | MOC | CS | SS 304
12 | V-203 / E-203 / CV-203 | STAGE 2 | 1st Effect Evaporator system (B) | 1 W | S | SW | Flash Chamber |  |  | 3 | Existing Eqpt.from Sion | Sion plant equipment as it is basis.
Capacity :
Dimension : Ø 1500 X 3000 mm
MOC : CS
Evaporator Type : Shell & Tube
HTA : 50m2
[7 empty] | Dimension : | SHELL | TUBE
[7 empty] | Length (mm) | 3500 | 1500
[7 empty] | Outer Diameter (mm) | 1050 | 50 NB
[7 empty] | No. of tubes |  | 187
[7 empty] | No. of passes | 1 | 1
[7 empty] | Thickness (mm) |  | 2.11
Pitch
Operating temp (°C)
Operating Pressure ( Kg/cm2)
[7 empty] | MOC | CS | SS 304
13 | V-204 / E-204 / CV-204 | STAGE 3B | 2nd Effect Evaporator system (B) | 1 W | S | SW | Flash Chamber |  |  | 3 | Existing Eqpt.from Sion | Sion plant equipment as it is basis.
Capacity :
Dimension : Ø 1500 X 3000 mm
MOC : CS
Evaporator Type : Falling Film Shell & Tube
HTA : 50m2
[7 empty] | Dimension : | SHELL | TUBE
[7 empty] | Length (mm) | 3500 | 1500
[7 empty] | Outer Diameter (mm) | 1050 | 50 NB
[7 empty] | No. of tubes |  | 187
[7 empty] | No. of passes | 1 | 1
[7 empty] | Thickness (mm) |  | 2.11
Pitch
Operating temp (°C)
Operating Pressure ( Kg/cm2)
[7 empty] | MOC | CS | SS 304
14 | E-205 | M-2 | Surface Condenser | 1 W | S | SW | Type : Shell & Tube |  |  | 4 | Existing Eqpt.from Sion | Sion plant equipment as it is basis.
HTA : M2
[7 empty] | Dimension : | SHELL | TUBE
[7 empty] | Length (mm) | 4150 | 3000
[7 empty] | Outer Diameter (mm) | 850
No. of tubes
No. of passes
Thickness (mm)
Pitch
Operating temp (°C)
Operating Pressure ( Kg/cm2)
[7 empty] | MOC | CS | SS 304
15 | V-205 | Intermediate Condensate Receiver | Condensate Collection Tank | 1 W | S | SW | Type : Cylindrical Vessel | Opearating press.: 60Torr | Design pressure : F.V / 1.5 bar G | 0.5 | Existing | Existing Flash Vessel from Taloja to be used. | Rev.2
[7 empty] | Capacity : 1.2 M3 | Operating temp : 100°C | Design temperature: 120 °C |  |  |  | 20/1/2010
[7 empty] | Dimension : Ø 800 x 2200 | Thickness : mm
Thickness - :
MOC :
16 | V-206 | Final Crude Glycerin Receiver | Crude Glycerine Receiver | 1 W | S | SW | Type : Vertical Dished End | Opearating press.: | Design pressure : | 0.6 | Existing Eqpt.from Sion | Sion plant equipment as it is basis.
[7 empty] | Capacity : 1.5 M3 | Operating temp : °C | Design temperature: °C
[7 empty] | Dimension : Ø 900 x 2200 | Thickness : mm
Thickness - : mm
MOC : CS
17 | V-207 |  | Clean Condensate Collection Tank | 1 W | S | SW | Type : Cylindrical Tank | Opearating press.: | Design pressure : | 0.7 | New | Drwg is made and ordered
[7 empty] | Capacity : 2 M3 | Operating temp : °C | Design temperature: °C
[7 empty] | Dimension : Ø 1200 x 2000 | Thickness : mm
Thickness - :
MOC : CS
18 | Leackage Collection Pit |  | Filter Leackage Sweet Water collection pit | 1 W | S | SW |  | Opearating press.: | Design pressure : |  | New | Civil Work
[7 empty] | Capacity : 5 M3 | Operating temp : °C | Design temperature: °C
[7 empty] | Dimension : 2500 L x 2000 W X 1000 H mm | Thickness : mm
Civil Work
Sweet Water Treatment Area
19 | F-201 A/B |  | Duplex Filter | 1 W+S | S | SW | Type : Basket Type | Opearating press.: | Design pressure : | 0.5 | Existing Eqpt.from Sion | Sion plant equipment as it is basis.
[7 empty] | Capacity : | Operating temp : °C | Design temperature: °C
[7 empty] | Mesh Size : | Thickness : mm
Pressure drop -: Kg/Cm2
MOC :
20 | P-201 | P- 6 (F-6) | Seperated Oil Transfer Pump ( From Sepeartion tank to Oil Collection tank ) | 1 W | R | SW | Type : Centrifugal pump |  |  | 0.2 | Existing Eqpt.from Sion | Sion plant equipment as it is basis.
Capacity : M3 / Hr
Diff. Head : MLC
MOC : SS 304
21 | P-202 A/B | P7 & P8 | Sweet water Feed Pump to 1st Treatment | 1 W | R | SW | Type : Centrifugal pump |  |  | 0.3 | Existing Eqpt.from Sion | Sion plant equipment as it is basis.
Capacity : 27 M3 / Hr
Diff. Head : 50 MLC
MOC : SS
22 | P-203 |  | 1st treated water FP-1 feed pump | 1 W | R | SW | Type : Centrifugal pump |  |  | 0.231 | New | Pump ordered
Capacity : 30 M3 / Hr
Diff. Head : 60MLC
MOC : SS
23 | P-204 |  | 2nd treated water FP-2 feed pump | 1 W | R | SW | Type : Centrifugal pump |  |  | 0.231 | New | Pump ordered
Capacity : 30 M3 / Hr
Diff. Head : 60 MLC
MOC : SS
24 | P-205 | P-C7 | Filtrate Transfering Pump | 1 W | R | SW | Type : Centrifugal pump |  |  | 0.1 | Existing Eqpt.from Sion | Sion plant equipment as it is basis.
Capacity : 22 M3 / Hr
Diff. Head : 32.5 MLC
MOC : SS
25 | P-206 -I |  | Hydraulic Unit Open/Close device for FP-201 | 1 W | R | SW | Type : |  |  | 0.1 | Existing Unit of DINSHAW filter from Taloja plant. | To be shifted to Baddi
Capacity :
Diff. Head :
MOC :
26 | P-206 - II |  | Hydraulic Unit Open/Close device for FP-202 | 1 W | R | SW | Type : |  |  | 0.1 | New | Ordered Placed on Bhatwadekar. To be delivered at Baddi .
Capacity :
Diff. Head :
MOC :
27 | P-207 |  | Skimmed Oil Transfer Pump | 1 W | R | SW | Type : Centrifugal pump |  |  | 0.093 | New | Pump ordered
Capacity : 3 M3 / Hr
Diff. Head : 30 MLC
MOC : CS
28 | P-208 A/B | P-3 A/B | Sweet Water Circulation Pumps of 2nd Effect (A/B ) evaporators | 2 W | R | SW | Type : |  |  | 0.35 | Existing Eqpt.from Sion | Sion plant equipment as it is basis.
Capacity : 66.6 M3 / Hr
Diff. Head : 23 MLC
MOC : CS
29 | P-209 | G-20A | Surface Condenser Cooling Water Pump | 1 W | R | SW | Type : |  |  | 0.8 | Existing Eqpt.from Sion | Existing G-20A pump of Lurgi distillation to be used ( located near cooling tower)
Capacity : 100 M3 / Hr
Diff. Head : 50MLC
MOC : CS
30 | P-210 | P-21 | Vacuum Pump of Post Concentration | 1 W | R | SW | Type : Water ring vacuum pump |  |  | 1 | Existing Eqpt.from Sion | Sion plant equipment as it is basis.
Capacity : 165 M3 / Hr
MOC : CS
31 | P-211 | P-4 | Condensate Transfer Pump. | 1 W | R | SW | Type : |  |  | 0.25 | Existing Eqpt.from Sion | Sion plant equipment as it is basis.
Capacity : M3 / Hr
Diff. Head : MLC
MOC : CS
32 | P-212 A/B | P-4 A/B | Crude Glycerine Transfer Pump. | 1 W + 1 S | R | SW | Type : Centrifugal |  |  | 0.5 | Existing Eqpt.from Sion | Sion plant equipment as it is basis.
Capacity : 15.5 M3 / Hr
Diff. Head : 22.5 MLC
MOC : CS
33 | P-213 |  | Dirty Condensate Transfer Pump | 1 W | R | SW | Type : Centrifugal |  |  | 0.1 | New | Pump ordered
Capacity : 10 M3 / Hr
Diff. Head : 30 MLC
MOC : SS Pump with Mech. Seal
34 | P-214 |  | Clean Condensate Transfer Pump | 1 W | R | SW | Type : Centrifugal |  |  | 0.1 | New | Pump ordered
Capacity : 7 M3 / Hr
Diff. Head : 30 MLC
MOC : CS
35 | P-215 |  | Filter leackage Sweet Water Transfer Pump | 1 W | R | SW | Type : Centrifugal |  |  | 0.11 | New | Pump ordered
Capacity : 3 M3 / Hr
Diff. Head : 30 MLC
MOC : SS

## Utility
EQUIPMENTLIST
UTILITY & TANK FARM EQUIPMENT LIST FOR PLANT AT BADDI ( Shifted From Sion )
Sr.No. | EQ. NO. | Item | Workng/Standby | Type | Description | Source Of Supply | Remarks | Revision | Weight (MT)
I ) | Cooling Tower
1 | CT-9001 | Clean Cooling Tower 1 | 1 W | S | Type - Indused Draft, Capacity- 110 m3/hr | Existing | Lurgi Intercondensers - 86 M3 /hr |  | 8
| CT-9002 | Clean Cooling Tower 2 | 1 W | S | Type - Indused Draft, Capacity- 110 m3/hr | Existing | Surface condenser - 100 m3/hr
| CT-9003 | Clean Cooling Tower 3 | 1 W | S | Type - Indused Draft, Capacity- 55 m3/hr | Existing | Vapor Condensers( Spltng Tower ) - 65 m3/hr
| CT-9004 | Dirty Cooling Tower | 1 W | S | Type - Indused Draft, Capacity- 110 m3/hr | Existing | Lurgi Vac Sytem - 110 m3/hr
Total - 361 m3/hr
2 |  | Cooling Tower Pumps |  |  | Type - Centrifugal
| P-9004 | a. To Vacuum system Lurgi ( Direct type) | 1 W+1 S | R | Capacity : 110 M3 / Hr. Head - 50MLC, MOC-SS 304 | Existing | Existing Sion G-20B pump capacity 125 m3/hr & 50 mts head ( Dirty Cooling Tower ) |  | 1
| P-9001 | b. To Surface Condenser | 1 W | R | Capacity : 100 M3 / Hr. Head - 50MLC, MOC-CS | Existing | Exsiting G-20 A pump capacity 125m3/hr & 50 mts head of Lurgi Fatty Acid distln plant. |  | 1
| P-9002 A& B or P-9003 | c. To Vapor Condenser | 1 W | R | Capacity : 65 M3 / Hr. Head - 40 MLC, MOC-CS |  | Total requirement of . 180 m3/hr & 45 Mts Head . Existing pump G-21A/B capacity 130 m3/hr & 41 mts head of Sion to be used ( For Future) . Presently existing pump of 240 m3/hr & 97 mts head from Taloja to be used. | Rev.2 | 0.7
|  | d. Tempered Water System (Lurgi) | 1 W | R | Capacity : 110 M3 / Hr. Head - 30 MLC, MOC-CS | Existing |  | 30/12/09 | 1
|  | e. To E-103 of Splitter | 1 W | R | Capacity : ~5 M3 / Hr. Head - 30 MLC
3 |  | Side Stream Filter For cooling Tower | 1 W | S | Capacity : M3/Hr | New | Not to be considered for March 2010 commissioning
|  | Chemical Dosing System | 1W | R |  | New
II ) | Air
| AC-9101 | Air Compressor | 1W | R |  | Existing | Existing air compresser( 1 No) at Kutch to be shifted. | Rev.2 30/12/09 | 1.5
| PA-9101 | Process Air Receiver | 1W | S |  | Existing | Availibilty at Kutch 1 & to be shifted. |  | 1.2
| IA-9102 | Instrument Air Receiver | 1W | S |  | Existing | Availibilty at Kutch 1 & to be shifted. |  | 1.2
| AD-9101 | Dryer Unit | 1W | S |  | Existing | From existing saponification Utility | Rev.3 20/1/2010 | 0.5
III ) | N2 | Not Considered
IV) | M.P Steam
| DMP-9201 | D.M. Water plant | 1W | S | Capacity - 10 M3/hr | Existing | Plant From Sion ( ION Exchange Make to be shifted ) |  | 10
| NPP-9203 | Neutralisation Pit Transfer Pump | 1W | R |  | Existing | Existing Pump From Sion DM plant to be used. | Rev.3 20/1/2010 | 0.2
| MBP-9201 | M.B. Plant | 1W | S | Capacity : 2 M3/hr | Existing | Plant From Sion after changing Resin |  | 0.7
| DMT-9201 | D.M.Water Storage tank | 1W | S | Capacity : 100 M3 | New | New tank to be made ( 4 mt Dia & 10 Mts Height , SS tank ) |  | 4
| DMTP-9204 A | D.M. Water Transfer Pump | 1W | R | Capacity : 22 m3/hr Head : 60 mlc, SS | Existing | Existing P-4A Condensate transfer pump of CGS plant at Sion plant to be used | Rev.2 30/12/09 | 0.2
| DA-9201 | De-Aerator | 1W | S |  | Existing | From Sion to be shifted to Baddi. ( Will be used for Heating the feed water ) |  | 1.5
| MPT-9301 | M.P.Boiler Feed Water Tank | 1W | S | Capacity - 60 m3 | Existing | Existing NS1 Tank from Sion to be used. |  | 4
| BFTP-9205 A/B | Boiler Feed Transfer Pump | 1W | R | Capacity : 15 m3/hr Head : 20 mlc, SS | Existing | Existing F-4 & F-5 pump of CGS plant at Sion to be used | Rev.2 30/12/09 | 0.5
| FODT-9401 | F.O.Storage Tank ( Main Tank ) | 1W | S | Capacity : 100 M3 - 150 M3 | Existing | Existing Capacity at Baddi plant to be checked. |  | 5
|  | F.O.Day tank | 1W | S | Capacity : 20 KL | Existing | To be shifted From Taloja with New electrical heater purchase. |  | 3
| P-9402 | F.O. Transfer pump | 1W | R | Capacity : 5 m3/hr Head : 60 mlc, CS | New | Pump ordered |  | 0.2
| MPB-9301 | M.P.Boiler with Chimney | 1W | S |  | Existing | Sion arrangement to be shifted to Baddi. |  | 10
| T-9302 | Boiler condensate Tank | 1W | S | Capacity : 10 m3 CS Tank Dim'n ; 4000 L X 2500 W X 1000 H mm | New | Tank drg.made & odered |  | 1.3
| P-9301 | Boiler Condensate Transfer pump | 1W | R | Capacity :10m3/hr, Head : 30 mlc , CS | New | Pump ordered |  | 0.15
|  | Chemical Dosing system | 1W | R |  | Existing | Existing system from Sion to be shifted. |  | 0.5
| Located At ETP | Effluent Transfer Pump( P-9801) | 1W | R | Capacity : 8m3/hr, Head : 30 mlc , CI | New | New pump located at New ETP plant. | Rev.3 20/1/2010 | 0.12
V ) | H.P.Boiler
| HPB-9302 | H.P.Boiler with Chimney | 1W | S |  | Existing | Sion Boiler to be shifted to Baddi. |  | 2
|  | HSD Storage Tank | 1W | S |  |  | HSD to be procured in Barrels.
| HSDP-9403 | HSD Tranfer Pump | 1W | R |  | Existing | Existing HSD transfer pump at Sion to be used. | Rev.2 30/12/09 | 0.2
| P-9303 | Barrel Unloading pump | 1W | R | Capacity Head MOC- CS | New | New Air opearted pump for barrel unloading to day tank to be procured. Quote received |  | 0.1
| HSDT-9402 | HSD Day Tank | 1W | S |  | Existing | From Sion to be shifted to Baddi. |  | 3
| DA-9202 | De-Aerator for H.P.Boiler ( IBR ) | 1W | S | Capacity : 8 M3 | New | Ordered |  | 2.5
| MBT-9202 | M.B.Water storage tank | 1W | S |  | Existing | From Sion to be shifted to Baddi. |  | 1.2
| MBTP-9206 | M.B.Water transfer pump | 1W | R |  | Existing | Existing MB Water Transfer pump at Sion to be used. | Rev.2 30/12/09 | 0.2
VI ) | Hot Oil Heater
| TH-9501 | TPB-15 with Chimney | 1W | S |  | Existing | From Sion to be shifted to Baddi. |  | 5
|  | Thermic Fluid |  |  | Capacity : 5 KL * | Existing | Availible at Taloja.
| THET-9501 | Expansion Tank | 1W | S |  | Existing | One tank From Sion to be shifted to Baddi.( Tank nozzles & instruments to be made ) |  | 3
| THST-9501 | Thermic Fluid Storage Tank | 1W | S | Capacity : 30 KL | Existing | One tank from Sion to be shifted. |  | 5
| THPT-9501 , THP-9502 | Thermic Fluid unloading sytem at Tank farm | 1W | R |  | New | Drain tank with pumping arrangement. 1 m3 Tank with Pump ( Pump of 3 m3/hr & 50 mtr Head is available ) |  | 1.5
| TDA-9501 | De-Aerator | 1W | S |  | New | Quote from Ambekar is received / Ordered |  | 3

## Tankfarm
Tank Farm
Equipment | Description |  | Type | Dimensions |  |  |  | Weight (MT)
T-8001 | Crude Oil Storage Tank | 1W | S | Dim'n: Ø 4500 X 10000 Ht mm, SS Tank | New | New tank to be made |  | 9.2
T-8002 | CFA Storage Tank | 1W | S | Dim'n: Ø 4500 X 10000 Ht mm, SS Tank | New | New tank to be made |  | 9.2
T-8003 | DFA Storage Tank 1 | 1W | S | Dim'n: Ø 4500 X 10000 Ht mm, SS Tank | New | New tank to be made |  | 9.2
T-8004 | DFA Storage Tank 2 | 1W | S | Dim'n: Ø 4500 X 10000 Ht mm, SS Tank | New | New tank to be made |  | 9.2
T-8005 | Residue Storage Tank | 1W | S | Dim'n : Ø 2900 X 10000 Ht mm, SS Tank | New | New tank to be made |  | 6
T-8007 | Light Ends Storage Tank | 1W | S |  | Existing | Exsiting Lorry Tanker available at Sion be used ( Chk) ? | Rev.2 30/12/09 | 2.5
T-8008 | Glycerin Storage | 1W | S | Dim'n : 2500 mm L X 2500 mm W X 4000 mm Ht. | Existing | Existing square tank of FO available at Sion to be used. (Chk) ? | Rev.2 30/12/09 | 7
T-8006 | Collected Oil Storage Tank | 1W | S | Dim'n : Ø 3100 X 7800 Ht mm, SS Tank. | Existing | Existing NS2 Tank from Sion to be used. |  | 4
V-8001 | Tank Form condensate tank | 1W | S | Dim'n : Ø 1200 X 2000 Ht mm, CS Tank | Existing | Existing T-820 of Taloja to be used. | Rev.3 20/1/2010 | 0.9
P-8007 | Tank Form condensate transfer pump | 1W | R | Capacity :3m3/hr, Head : 30 mlc , CS | New | Pump ordered |  | 0.1
| Unloading Facility for Oil / CFA | 1W | S |  | New | 2 Nos.Trolley with Hose connections
P-8001 A&B | Unloading Pumps for Oil / CFA | 1W+ 1W | R | Capacity :100m3/hr, Head : 30 mlc , SS | New | Pump ordered |  | 0.255
P-8002 | Feed Pump for W&S Splitter | 1W | R | Capacity : * m3/hr, Head : mlc , SS | Existing | Existing P-104A pump located at tank farm of Sion to be used | Rev.2 30/12/09 | 0.25
P-8003 | Feed Pump for Lurgi Distillation | 1W | R | Capacity : * m3/hr, Head : mlc , SS | Existing | Existing feed pump located at tank farm of Sion to be used | Rev.2 30/12/09 | 0.25
P-8004 | Unloading Pumps for Crude Glycerin | 1W | R | Capacity :50m3/hr, Head : 30 mlc , SS | New | Pump ordered |  | 0.135
P-8005 | Residue Unloading pump | 1W | R | Capacity :10m3/hr, Head : 30 mlc , SS | New | Pump ordered. ( Common for both Residue + Collected Oil ) |  | 0.105
P-8006 A | DFA Transfer pump to Saponification plant | 1W | R | Capacity : 22 m3/hr Head : 60 mlc, SS | Existing | Existing P-4B Condensate transfer pump of CGS plant at Sion plant to be used | Rev.2 30/12/09 | 0.15
* - 20 KL FO Day Tank can be used for TPB-15 heater.
Located At Saponification Area | Condensate Collection Vessel | 1W | S | Dim'n : Ø 1200 X 2000 Ht mm, CS Tank | New | New tank to be made at Site . | Rev.3 20/1/2010 | 0.6
| Condensate Transfer Pump | 1W | R | Capacity : 5m3/hr, Head : 35 mlc , CS | Existing | Existing pump from Taloja to be used | Rev.3 20/1/2010 | 0.1
| Effluent Transfer Pump( P-9801) | 1W | R | Capacity : 5m3/hr, Head : 50 mlc , CI | New | New pump | Rev.3 20/1/2010 | 0.1

## Glycerene Treat cost summary
Cost Summary Glycerene
1324397
| CS PIPES COST INR |  | 131232
| CS VALVES COST INR |  | 85730
| SS 304 PIPES COST INR |  | 674034
| SS VALVES COST INR |  | 433401
CS Material
Sr.No | ITEM | MOC | GRADE | SIZE (NB) | SCH/CLASS | QTY (Mtr/Nos) | UNIT COST (INR) | PRICE INR) | Size (INCH | INM | Ins.(50 MM)
1 | Pipe | CS | IS-1239 | 15 | HC | 223 | 48 | 10704 | 0.5 | 111.5 | 80.5509
|  | CS | IS-1239 | 25 | HC | 271 | 98 | 26558 | 1 | 271 | 106.4014
|  | CS | IS-1239 | 40 | HC | 12 | 146 | 1752 | 1.5 | 18 | 5.2769
|  | CS | IS-1239 | 50 | HC | 168 | 204 | 34272 | 2 | 336 | 79.1532
|  | CS | IS-1239 | 100 | HC | 70 | 454 | 31780 | 4 | 280 | 43.974
|  | GI | IS-1239 | 25 | HC | 178 | 147 | 26166 | 1 | 178 | 69.8872
CS PIPES COST | [7 empty] | 131232 |  | 1194.5 | 385.2436
2 | Ball valve | CS |  | 25 | 150 | 13 | 1207 | 15691
3 | Gate valve | CS | A105 | 15 | 800 | 4 | 1300 | 5200
4 | Globe valve | CS | A105 | 15 | 800 | 5 | 1800 | 9000
|  | CS | A105 | 25 | 800 | 7 | 2288 | 16016
5 | NRV | CS | A105 | 15 | 800 | 2 | 1560 | 3120
|  | CS | A105 | 25 | 800 | 2 | 3270 | 6540
6 | Steam Trap | CS |  | 15 |  | 7 | 2347 | 16429
|  | CS |  | 25 |  | 3 | 3283 | 9849
7 | Strainer | CS |  | 40 |  | 1 | 3885 | 3885
CS VALVES COST | [7 empty] | 85730
SS Material
Sr.No | ITEM | MOC | GRADE | SIZE (INCH) | SCH/CLASS | QTY (Mtr/Nos) | UNIT COST (INR) | PRICE INR) | Size (INCH | INM | Ins.(50 MM)
1 | Pipe | SS | 304 | 25 | S40 | 81 | 460 | 37260 | 1 | 81 | 31.8026
|  | SS | 304 | 50 | S10 | 341 | 650 | 221650 | 2 | 682 | 160.6621
|  | SS | 304 | 80 | S10 | 54 | 1688 | 91152 | 3 | 162 | 30.5305
|  | SS | 304 | 100 | S10 | 199 | 1628 | 323972 | 4 | 796 | 125.0118
SS304 PIPES COST | [7 empty] | 674034 |  | 1721 | 348.0071
2 | Ball valve | SS | CF8 | 15 | 150 | 6 | 2865 | 17190
|  | SS | CF8 | 25 | 150 | 3 | 4215 | 12645
|  | SS | CF8 | 50 | 150 | 35 | 5312 | 185920
|  | SS | CF8 | 80 | 150 | 3 | 8807 | 26421
|  | SS | CF8 | 100 | 150 | 11 | 9415 | 103565
3 | NRV | SS | CF8 | 100 | 150 | 2 | 11507 | 23014
4 | Strainer | SS | 304 | 50 | 150 | 2 | 4620 | 9240
|  | SS | 304 | 100 | 150 | 2 | 20553 | 41106
5 | Sight glass | SS | 304 | 40 |  | 1 | 3100 | 3100
|  | SS | 304 | 100 |  | 2 | 5600 | 11200
SS VALVES COST | [7 empty] | 433401

## Lurgi Cost summary
Cost Summary Lurgi
14361908
| CS PIPES COST INR |  | 1075876
| CS-IBR PIPES COST INR |  | 201860
| CS VALVES COST INR |  | 1147961
| SS 304 PIPES COST INR |  | 201261
| SS 316L PIPES COST INR |  | 3879002
| SS VALVES COST INR |  | 7855948
CS Material
Sr.No | ITEM | MOC | GRADE | SIZE (INCH) | SCH/CLASS | QTY (Mtr/Nos) | UNIT COST (INR) | PRICE INR) | INM | Dia(NB) | Ins.(50 mm)
1 | Pipe | CS | IS-1239 | 0.5 | HC | 156 | 48 | 7488 | 78 | 15 | 56.3495
|  | CS | A106 | 0.75 | S80 | 104 | 205 | 21320 | 78 | 20 | 39.1997
|  | CS | IS-1239 | 1 | HC | 182 | 98 | 17836 | 182 | 25 | 71.4578
|  | CS | A106 | 1 | S80 | 84 | 230 | 19320 | 84 | 25 | 32.9805
|  | CS | A106 | 1.5 | S80 | 146 | 330 | 48180 | 219 | 40 | 64.202
|  | CS | IS-1239 | 2 | S40 | 368 | 204 | 75072 | 736 | 50 | 173.3832
|  | CS | IS-1239 | 3 | HC | 466 | 333 | 155178 | 1398 | 80 | 263.4671
|  | CS | A106 | 3 | S40 | 126 | 633 | 79758 | 378 | 80 | 71.2379
|  | CS | IS-1239 | 4 | HC | 116 | 454 | 52664 | 464 | 100 | 72.8712
|  | CS | A106 | 4 | S40 | 24 | 876 | 21024 | 96 | 100 | 15.0768
|  | CS | IS-1239 | 6 | HC | 304 | 668 | 203072 | 1824 | 150 | 238.716
|  | CS | A106 | 6 | S40 | 192 | 1541 | 295872 | 1152 | 150 | 150.768
|  | CS | IS-3589 | 8 | HC | 52 | 1521 | 79092 | 416 | 200 | 48.9996
CS PIPES COST | [7 empty] | 1075876 | 7105 |  | 1298.7093
2 | Pipe-IBR | CS-IBR | A106 | 1 | S80 | 150 | 654 | 98100 | 150 | 25 | 58.8937
|  | CS-IBR | A106 | 1.5 | S80 | 24 | 700 | 16800 | 36 | 40 | 10.5538
|  | CS-IBR | A106 | 3 | S40 | 80 | 1087 | 86960 | 240 | 80 | 45.2304
CS-IBR PIPES COST | [7 empty] | 201860 | 426 |  | 114.6779
3 | Ball valve | CS | A216 | 0.5 | 150 | 16 | 767 | 12272
|  | CS | A216 | 0.75 | 150 | 1 | 1360 | 1360
|  | CS | A216 | 1 | 150 | 18 | 1218 | 21924
|  | CS | A216 | 1.5 | 150 | 1 | 1612 | 1612
|  | CS | A216 | 1.5 | 150 | 5 | 2030 | 10150
|  | CS | A216 | 2 | 150 | 23 | 2398 | 55154
4 | Butterfly valve | CS |  | 1 | 150 | 1 | 1312 | 1312
|  | CS |  | 1.5 | 150 | 1 | 1840 | 1840
|  | CS |  | 2 | 150 | 4 | 2465 | 9860
|  | CS |  | 3 | 150 | 14 | 3360 | 47040
|  | CS |  | 4 | 150 | 3 | 4000 | 12000
|  | CS |  | 8 | 150 | 1 | 10500 | 10500
5 | Gate valve | CS | A105 | 0.5 | 800 | 22 | 1300 | 28600
|  | CS | A105 | 1 | 800 | 8 | 1451 | 11608
|  | CS | A105 | 1.5 | 800 | 3 | 3147 | 9441
|  | CS | A216 | 2 | 150 | 5 | 4625 | 23125
|  | CS | A216 | 3 | 300 | 1 | 13450 | 13450
|  | CS | A216 | 4 | 300 | 3 | 22116 | 66348
|  | CS | A216 | 6 | 300 | 2 | 30630 | 61260
|  | CS | A216 | 6 | 150 | 1 | 16875 | 16875
6 | Globe valve | CS | A105 | 0.5 | 800 | 8 | 960 | 7680
|  | CS | A105 | 0.75 | 800 | 5 | 1817 | 9085
|  | CS | A105 | 1 | 800 | 4 | 3420 | 13680
|  | CS | A105 | 1.5 | 800 | 2 | 3980 | 7960
|  | CS | A216 | 2 | 300 | 9 | 9270 | 83430
|  | CS | A216 | 2 | 150 | 4 | 5213 | 20852
|  | CS | A216 | 3 | 300 | 5 | 13700 | 68500
|  | CS | A216 | 3 | 150 | 1 | 9800 | 9800
|  | CS | A216 | 4 | 300 | 3 | 27800 | 83400
|  | CS | A216 | 6 | 300 | 5 | 34215 | 171075
|  | CS-IBR | A105 | 0.75 | 300 | 4 | 2918 | 11672
|  | CS-IBR | A105 | 1 | 800 | 5 | 4140 | 20700
|  | CS-IBR | A105 | 1.5 | 300 | 1 | 5472 | 5472
|  | CS-IBR | A216 | 3 | 300 | 3 | 13500 | 40500
7 | NRV LCV | CS | A105 | 0.5 | 800 | 7 | 700 | 4900
|  | CS | A105 | 0.75 | 800 | 1 | 1860 | 1860
|  | CS | A105 | 1 | 800 | 1 | 2285 | 2285
| NRV SCV | CS | A216 | 2 | 300 | 2 | 8820 | 17640
|  | CS | A216 | 3 | 300 | 1 | 21161 | 21161
|  | CS | A216 | 3 | 150 | 2 | 11206 | 22412
|  | CS | A216 | 4 | 300 | 1 | 25900 | 25900
|  | CS | A216 | 6 | 300 | 1 | 34800 | 34800
8 | PRV | CS |  | 2 | 150 | 2 | 4915 | 9830
9 | Steam trap | CS |  | 2 | 150 | 2 | 4212 | 8424
10 | Strainer | CS |  | 0.5 | 150 | 2 | 1560 | 3120
|  | CS |  | 0.75 | 300 | 2 | 2750 | 5500
|  | CS |  | 3 | 300 | 1 | 7326 | 7326
|  | CS |  | 4 | 150 | 1 | 6816 | 6816
11 | Sight Glass |  |  | 1.5 |  | 1 | 2250 | 2250
|  |  |  | 2 |  | 1 | 4200 | 4200
CS VALVES COST | [7 empty] | 1147961
SS Material
Sr.No | ITEM | MOC | GRADE | SIZE (INCH) | SCH/CLASS | QTY (Mtr/Nos) | UNIT COST (INR) | PRICE INR) | INM | Size(NB) | INS(50 MM)
1 | Pipe | SS | 304 | 1 | S40 | 10 | 630 | 6300 | 10 | 25 | 3.9263
|  | SS | 304 | 1.5 | S40 | 12 | 768 | 9216 | 18 | 40 | 5.2769
|  | SS | 304 | 2 | S10 | 69 | 750 | 51750 | 138 | 50 | 32.5093
|  | SS | 304 | 4 | S10 | 15 | 1508 | 22620 | 60 | 100 | 9.423
|  | SS | 304 | 6 | S10 | 15 | 1912 | 28680 | 90 | 150 | 11.7788
|  | SS | 304 | 8 | S10 | 37 | 2235 | 82695 | 296 | 200 | 34.8651
SS 304 PIPES COST | [7 empty] | 201261 | 612 |  | 97.7793
2 | Ball Valve | SS | 304 | 1 | 150 | 2 | 3622 | 7244
|  | SS | 304 | 1.5 | 150 | 5 | 3980 | 19900
|  | SS | 304 | 2 | 150 | 10 | 4520 | 45200
3 | Butterfly valve | SS | 304 | 8 | 150 | 2 | 7800 | 15600
4 | Demister | SS | 304 |  |  | 1 | 10000 | 10000
SS304 VALVES COST | [7 empty] | 97944 | INM | Size(NB) | INS(50 MM)
5 | Pipe | SS | 316L | 0.5 | S40 | 6 | 540 | 3240 | 3 | 15 | 2.1673
|  | SS | 316L | 1 | S10 | 60 | 515 | 30900 | 60 | 25 | 23.5575
|  | SS | 316L | 1 | S40 | 205 | 686 | 140630 | 205 | 25 | 80.4881
|  | SS | 316L | 1.5 | S10 | 18 | 887 | 15966 | 27 | 40 | 7.9153
|  | SS | 316L | 1.5 | S40 | 147 | 1396 | 205212 | 220.5 | 40 | 64.6418
|  | SS | 316L | 2 | S10 | 96 | 1578 | 151488 | 192 | 50 | 45.2304
|  | SS | 316L | 2 | S40 | 417 | 1858 | 774786 | 834 | 50 | 196.4695
|  | SS | 316L | 3 | S40 | 249 | 4050 | 1008450 | 747 | 80 | 140.7796
|  | SS | 316L | 4 | S40 | 60 | 6000 | 360000 | 240 | 100 | 37.692
|  | SS | 316L | 6 | S40 | 24 | 13280 | 318720 | 144 | 150 | 18.846
|  | SS | 316L | 8 | S40 | 21 | 17250 | 362250 | 168 | 200 | 19.7883
|  | SS | 316L | 16 | S40 | 12 | 42280 | 507360 | 192 | 400 | 18.846
SS316L PIPES COST | [7 empty] | 3879002 | 3032.5 |  | 656.4219
6 | Ball Valve | SS | 316L | 15 | 150 | 13 | 2764 | 195
|  | SS | 316L | 20 | 150 | 3 | 3915 | 60
|  | SS | 316L | 25 | 150 | 26 | 4612 | 650
|  | SS | 316L | 40 | 150 | 28 | 7306 | 1120
|  | SS | 316L | 50 | 150 | 51 | 11715 | 2550
|  | SS | 316L | 80 | 150 | 26 | 21230 | 2080
|  | SS | 316L | 100 | 150 | 1 | 32512 | 100
|  | SS | 316L | 200 | 150 | 1 | 55810 | 200
7 | Gate Valve | SS | 316L | 15 | 150 | 10 | 7820 | 150
|  | SS | 316L | 50 | 150 | 5 | 16233 | 250
8 | Globe valve | SS | 316L | 25 | 150 | 2 | 13060 | 50
|  | SS | 316L | 50 | 150 | 3 | 21000 | 150
9 | NRV LCV | SS | 316L | 15 | 150 | 2 | 8050 | 30
|  | SS | 316L | 40 | 150 | 2 | 13960 | 80
10 | NRV SCV | SS | 316L | 50 | 150 | 2 | 6050 | 100
|  | SS | 316L | 80 | 150 | 2 | 9500 | 160
11 | Strainer | SS | 316L | 80 | 150 | 2 | 15725 | 160
12 | Sight glass | SS | 316L | 50 |  | 1 | 4500 | 50
|  | SS | 316L | 25 |  | 1 | 2800 | 25
SS 316L VALVES COST | [7 empty] | 7758004

## Splitting tower cost summary
Cost Summary Splitting
3398869
| CS PIPES COST INR |  | 124930
| CS-IBR PIPES COST INR |  | 179444
| CS VALVES COST INR |  | 266903
| SS 316L PIPES COST INR |  | 1120362
| SS VALVES COST INR |  | 1707230
CS Material
Sr.No | ITEM | MOC | GRADE | SIZE (INCH) | SCH/CLASS | QTY (Mtr/Nos) | UNIT COST (INR) | PRICE INR) | INM | SIZE (NB) | INS(50 MM)
1 | Pipe | CS | IS-1239 | 1 | HC | 16 | 98 | 1568 | 16 | 25 | 6.282
|  | CS | IS-1239 | 2 | HC | 117 | 204 | 23868 | 234 | 50 | 55.1245
|  | CS | IS-1239 | 3 | HC | 38 | 333 | 12654 | 114 | 80 | 21.4844
|  | CS | IS-1239 | 6 | HC | 130 | 668 | 86840 | 780 | 150 | 102.0825
CS PIPES COST | [7 empty] | 124930 | 1144 |  | 184.9735
2 | Pipe -IBR | CS-IBR | A106 | 1 | S80 | 18 | 654 | 11772 | 18 | 25 | 7.0672
|  | CS-IBR | A106 | 1.5 | S80 | 134 | 700 | 93800 | 201 | 40 | 58.9252
|  | CS-IBR | A106 | 4 | S40 | 36 | 2052 | 73872 | 144 | 100 | 22.6152
CS-IBR PIPES COST | [7 empty] | 179444 | 363 |  | 88.6076
3 | Ball valve | CS | CWS | 1 | 150 | 2 | 1207 | 2414
|  | CS | CWS | 2 | 150 | 4 | 2399 | 9596
4 | Butterfly valve | CS | CWS | 3 | 150 | 3 | 2856 | 8568
5 | PSV | CS |  | 3 | 150 | 1 | 45000 | 45000
6 | Globe valve | CS-IBR | A105 | 1 | 300 | 4 | 4140 | 16560
|  | CS-IBR | A105 | 1.5 | 300 | 7 | 8500 | 59500
|  |  | A216 | 4 | 300 | 3 | 36955 | 110865
7 | Steam trap |  |  | 2 | 150 | 2 | 5300 | 10600
8 | Moisture trap |  |  | 1.5 | 150 | 1 | 3800 | 3800
CS VALVES COST | [7 empty] | 266903
SS Material
Sr.No | ITEM | MOC | GRADE | SIZE (INCH) | SCH/CLASS | QTY (Mtr/Nos) | UNIT COST (INR) | PRICE INR) | INM | SIZE (NB) | INS(50 MM)
1 | Pipe | SS | 304 | 3 | S10 | 30 | 1688 | 50640 | 90 | 80 | 16.9614
|  | SS | 316L | 0.5 | S10 | 18 | 410 | 7380 | 9 | 15 | 6.5019
|  | SS | 316L | 1 | S10 | 160 | 515 | 82400 | 160 | 25 | 62.82
|  | SS | 316L | 1.5 | S40 | 25 | 1396 | 34900 | 37.5 | 40 | 10.9935
|  | SS | 316L | 2 | S10 | 134 | 1410 | 188940 | 268 | 50 | 63.1341
|  | SS | 316L | 2 | S40 | 56 | 1558 | 87248 | 112 | 50 | 26.3844
|  | SS | 316L | 3 | S10 | 193 | 1578 | 304554 | 579 | 80 | 109.1183
|  | SS | 316L | 4 | S10 | 16 | 4800 | 76800 | 64 | 100 | 10.0512
|  | SS | 316L | 6 | S10 | 25 | 11500 | 287500 | 150 | 150 | 19.6313
SS316L PIPES COST | [7 empty] | 1120362 | 1469.5 |  | 325.5961
2 | Ball Valve | SS | CF3M | 0.5 | 150 | 10 | 2764 | 27640
|  | SS | CF3M | 1 | 150 | 14 | 4612 | 64568
|  | SS | CF3M | 2 | 150 | 30 | 11715 | 351450
|  | SS | CF3M | 3 | 150 | 23 | 21230 | 488290
|  | SS | CF3M | 4 | 150 | 1 | 32512 | 32512
|  | SS | CF3M | 6 | 150 | 2 | 42260 | 84520
3 | Gate valve | SS | CF3M | 1 | 150 | 2 | 11160 | 22320
|  | SS | CF3M | 2 | 150 | 2 | 16233 | 32466
|  | SS | CF3M | 3 | 150 | 1 | 25437 | 25437
4 | Globe valve | SS | CF3M | 0.5 | 150 | 1 | 5300 | 5300
|  | SS | CF3M | 1 | 150 | 3 | 7550 | 22650
|  | SS | CF3M | 1 | 1500 | 1 | 12000 | 12000
|  | SS | CF3M | 1.5 | 1500 | 2 | 15675 | 31350
|  | SS | CF3M | 2 | 1500 | 4 | 25310 | 101240
|  | SS | CF3M | 3 | 1500 | 3 | 45160 | 135480
5 | NRV | SS | CF3M | 1.5 | 900 | 3 | 26500 | 79500
|  | SS | CF3M | 2 | 900 | 2 | 31260 | 62520
|  | SS | CF3M | 3 | 900 | 1 | 39050 | 39050
6 | PSV | SS |  | 2 | 150 | 1 | 6500 | 6500
7 | Pul dampner | SS |  | 1.5 | 150 | 1 | 5000 | 5000
|  | SS |  | 2 | 150 | 2 | 6500 | 13000
7 | Strainer | SS | 316L | 2 | 150 | 3 | 9800 | 29400
|  | SS | 316L | 3 | 150 | 1 | 15725 | 15725
|  | SS | 316L | 4 | 150 | 1 | 19312 | 19312
SS VALVES COST | [7 empty] | 1707230

## Material Cost summary
FATTY ACID PLANT BADDI PIPING COST
Total piping INM
Sr No. | Item Description | Cost |  | Sr.no | MOC | Lurgi | Splitting | Glycerine | Total
1 | Pipe Cost (INR) | 7588001 |  | 1 | CS | 7105 | 1144 | 1194.5 | 9443.5
| CS Pipes | 1713342 |  | 2 | SS | 3645 | 1469.5 | 1721 | 6835.5
| SS Pipes | 5874659 |  | 3 | IBR | 426 | 363 | 0 | 789
2 | Fittings Cost @ 50% (INR) | 3794000.5 | 12709901.675
| CS Fittings | 856671 |  | Insulation
| SS Fittings | 2937329.5 |  | Sr.no | MOC | Lurgi | Splitting | Glycerine | Total
3 | Gaskets 10 % (INR) | 758800.1 |  | 1 | CS | 1298.7093 | 184.9735 | 385.2436 | 1868.9264
4 | Stud Bolt @ 7.5% (INR) | 569100.075 |  | 2 | SS | 754.2012 | 325.5961 | 348.0071 | 1427.8044
5 | Valves Cost (INR) | 11497173 |  | 3 | IBR | 114.6779 | 88.6076 | 0 | 203.2855
| CS Valves | 1500594
| SS Valves | 9996579
6 | Total Piping Cost (INR) | 23448274.575

## Cheema boiler
Cheema boiler 2 TPH Baddi to Guwahati shifting
Sr.no. | Description | Amount | Tax amount
A. | Boiler package dismantling with loading | 1000000 | 145000
Furnace
Boiler
APH
Cyclone
Petcoke bunker
ID fan
FD fan
Ash system
Ductings
B. | Transportation (Baddi to Guwahati) | 600000 | 87000
C. | Other equipment dismantling & loading | 300000 | 43500
Petcoke feeding system
Wet scrubber
TF expansion tank
Dearater
D. | Re-erection whole unit at Guwahati | 1500000 | 217500
E. | IBR approval charges of piping | 1000000 | 145000
F. | Engineering of OSBL & IBR piping | 800000 | 116000
G. | Material cost | 700000 | 175000
| Non IBR piping | 300000
| IBR piping | 400000
H. | Service cost | 400000 | 58000
| Non IBR piping | 200000
| IBR piping | 200000
I. | Insulation cost | 1000000 | 145000
Non IBR piping
IBR piping
Equipments
J. | Cheema boiler supervision charges | 300000 | 43500
K. | Refractory cost | 500000 | 72500
l. | Refurbishing cost | 700000 | 101500
| Equipments | 500000
| SM items | 200000
M. | Material handling and packeging cost | 400000 | 58000
| Total (Material + Services) | 9200000 | 1407500 | 10607500
|  | W/O TAX | ONLY TAX | WITH TAX

## 2.5 MKcal heater
2.5 Mkcal/Hr petcoke boiler Baddi to Guwahati shifting
Sr.no. | Description | Amount | Tax amount
A. | Petcoke boiler package dismantling with loading | 1500000 | 217500
Furnace
Radiant coil
Convection coil
Expansion tank
Storage tank
APH
Cyclone
ID fan
FD fan
Ash system
Ductings
Pumps
B. | Transportation (Baddi to Guwahati) | 1500000 | 217500
C. | Other equipment dismantling & loading | 300000 | 43500
Petcoke feeding system
D. | Re-erection whole unit at Guwahati | 2495000 | 361775
| Crane 175-200 MT for equipment erection (3 SFT) | 495000 | 71775
F. | Engineering | 1000000 | 145000
G. | Material cost | 2000000 | 500000
| Piping | 1200000 | 300000
| Bellow seal valve | 800000 | 200000
H. | Service cost piping (Fabricaion & Erection) | 650000 | 94250
I. | Insulation cost | 1500000 | 217500
Piping
Equipments
J. | Supervision charges | 500000 | 72500
K. | Refractory cost | 500000 | 72500
l. | Refurbishing cost | 700000 | 101500
| Equipments | 500000
| SM items | 200000
M. | Material handling and packeging cost | 400000 | 58000
N. | Thermic fluid drums (70 kl) | 500000 | 125000
O. | Thermic fluid transportation | 900000 | 130500
P. | Thermic fluid for top up (3 Kl) | 1200000 | 300000
| Total (Material + Services) | 15645000 | 2657025 | 18302025
|  | W/O TAX | ONLY TAX | WITH TAX

## Tank farm summary
Tank farm cost summary
Sr.no | Description | Amount | Tax Amount
MATERIAL
A. | Tank Material cost | 67539149 | 16884787.25
| 4.75 M.Dia. X 30 M.Ht.CS - 8 Nos | 12191520.8
| 4 M.Dia. X 30 M.Ht.CS - 6 Nos | 7656491.4
| 4 M.Dia. X 30 M.Ht.SS 304 -8 Nos | 47091136.8
| Unloading trolley | 600000
B. | New Equipments/SM Items | 3100000 | 775000
| Loading pumps | 800000
| Unloading pumps | 600000
| Tank circulation pumps | 1000000
| Valves | 400000
| Strainers | 200000
| Steam traps | 50000
| Spectacle blind/End blind flanges | 50000
C. | Piping | 2000000 | 500000
| Material unloading with trolly piping | 500000
| Material loading piping | 500000
| Tank interconnecting piping | 1500000
SERVICES
A. | Engineering charges | 1500000 | 217500
B. | TPI inspection charges | 1500000 | 217500
C. | Tank fabrication services | 32611707.5 | 4728697.5875
| 4.75 M.Dia. X 30 M.Ht.CS - 8 Nos | 10038640
| 4 M.Dia. X 30 M.Ht.CS - 6 Nos | 6620605.5
| 4 M.Dia. X 30 M.Ht.SS 304 -8 Nos | 15752462
| Unloading trolley | 200000
D. | Piping fabrication services | 1000000 | 145000
E. | Insulation | 58800000 | 8526000
| 4.75 M.Dia. X 30 M.Ht.CS - 8 Nos | 24000000
| 4 M.Dia. X 30 M.Ht.CS - 6 Nos | 13200000
| 4 M.Dia. X 30 M.Ht.SS 304 -8 Nos | 21600000
| Total | 168050856.5 | 31994484.8375 | 200045341.3375
|  | W/O TAX | ONLY TAX | WITH TAX

## 4.75 m Dia x 30 m Ht.
4.75 mtrs.Dia. X 30 mtrs.Ht. CS tank consting
Sr.no | Description | Size | Qty | Unit | Rate | Amount | Remarks
A. | Plates
1 | Shell plate (10 mm thk.-3 nos course) | 10 mm thk. x 6.3 m x 1.5 m | 5934.56 | Kgs | 40 | 237382.4
2 | Shell plate (8 mm thk.-6 nos course) | 8 mm thk. x 6.3 m x 1.5 m | 8901.9 | Kgs | 40 | 356076
3 | Shell plate (6 mm thk.-8 nos course) | 6 mm thk. x 6.3 m x 1.5 m | 8901.8 | Kgs | 40 | 356072
4 | Shell plate (5 mm thk.-3 nos course) | 5 mm thk. x 6.3 m x 1.5 m | 2960.96 | Kgs | 40 | 118438.4
5 | Bottom plate (10 mm thk.) | 10 mm thk. x 6.3 m x 1.5 m | 1500 | Kgs | 40 | 60000
6 | Top roof plate (5 mm thk.) | 5 mm thk. x 6.3 m x 1.5 m | 741.82 | Kgs | 40 | 29672.8
7 | Anchor chair plate (32 mm thk.) | 32 mm thk. x 6.3 m x 1.5 m | 2373.84 | Kgs | 40 | 94953.6
8 | Guset plate/pad plate (5 mm thk.) | 5 mm thk. x 6.3 m x 1.5 m | 370.12 | Kgs | 40 | 14804.8
9 | Central drum/Bottom sump | 6 mm thk. | 300 | Kgs | 40 | 12000
B. | Structural material |  | 2000 | Kgs | 40 | 80000
1 | Curb angle (18.84 Mtrs) | 75 x 75 x 8 mm thk.
2 | Wind gurder channel (2 Nos) | ISMC 100
3 | Top roof supporting channel | ISMC 100
4 | Hand railing pipe | 40 NB GI. | 36 | Mtrs | 220 | 7920
C. | Nozzle pipe & flanges
1 | Manhole (2 Nos) 10 mm thk. | 600 NB (2 m x 1 m) | 200 | Kgs | 40 | 8000
2 | On shell (6 Nos) | 150 NB | 1 | Mtrs | 1540 | 1540 | Pipe,Sch.40,smls
3 | On shell (2 Nos) | 100 NB | 0.3 | Mtrs | 876 | 262.8 | Pipe,Sch.40,smls
4 | On shell (2 Nos) | 80 NB | 0.3 | Mtrs | 633 | 189.9 | Pipe,Sch.40,smls
5 | On shell (8 Nos) | 50 NB | 1.2 | Mtrs | 307 | 368.4 | Pipe,Sch.40,smls
6 | Flange A 105,sorf,150# | 600 NB | 2 | Nos | 15000 | 30000
7 | Flange A 105,sorf,150# | 150 NB | 6 | Nos | 540 | 3240
8 | Flange A 105,sorf,150# | 100 NB | 2 | Nos | 360 | 720
9 | Flange A 105,sorf,150# | 80 NB | 2 | Nos | 330 | 660
10 | Flange A 105,sorf,150# | 50 NB | 8 | Nos | 155 | 1240
11 | Blind flange A 105,150 # | 600 NB | 1 | Nos | 20000 | 20000
12 | Stud and nut | 1 1/4" x 175 mm | 20 | Nos | 220 | 4400
D. | Steam coil 50 NB
1 | Pipe,SS 304,Sch.40,erw | 50 NB | 55 | Mtrs | 893 | 49115 | 3.91 kgs/m
2 | Elbows,SS 304,Sch.40,erw | 50 NB | 30 | Nos | 530 | 15900 | 0.710 kgs/elbow
3 | SS 304 angle | 60 x 60 x 6mm | 12 | Mtrs | 1242 | 14904 | 5.40 kgs/m
4 | SS 304 Clamp (u bolt with 2 nuts) | 50 NB | 30 | Nos | 150 | 4500 | 0.140 kgs/pcs.
5 | Flange,sorf,ss 304,150# | 50 NB | 2 | Nos | 790 | 1580 | 2.3 kgs/pcs.
|  |  |  | Total |  | 1523940.1
Total weight
Sr.no | Description | Qty | Unit
A | Plates
1 | 10 mm thk. | 7634.56 | Kgs
2 | 8 mm thk. | 8901.9 | Kgs
3 | 6 mm thk. | 9201.8 | Kgs
4 | 5 mm thk. | 4072.9 | Kgs
5 | 32 mm thk. | 2373.84 | Kgs
B | Structural steel | 2000 | Kgs
1 | Hand railing | 36 | Mtrs
2 | Nozzle pipe & Flanges | 1000 | Kgs
C. | SS coil & structural | 400 | Kgs
| Total | 35621 | Kgs
Services
Sr.no | Description | Qty | Unit | Rate | Amount
3 | Fabrication and erection of CS | 32185 | Kgs | 25 | 804625
4 | Structural steel fabrication and erection | 2000 | Kgs | 25 | 50000
5 | Hand railing | 36 | mtrs | 300 | 10800
6 | Sand blasting and painting | 484 | m2 | 450 | 217800
7 | Nozzle fab & erection |  |  |  | 0
| 600 NB | 2 | Nos | 5000 | 10000
| 150 NB | 6 | Nos | 1400 | 8400
| 100 NB | 2 | Nos | 100 | 200
| 80 NB | 2 | Nos | 800 | 1600
| 50 NB | 8 | Nos | 600 | 4800
8 | SS coil fabrication and erection | 130 | INM | 336 | 43680
9 | SS structural fab ere. | 65 | Kgs | 45 | 2925
10 | Instrumentation |  | 1 | Au | 100000
|  |  | Total |  | 1254830
Summary
Sr.no | Description | Amount
1 | Material | 1523940.1
2 | Services | 1254830
| Total amount | 2778770.1

## 4 m Dia x 30 m Ht.
4 mtrs.Dia. X 30 mtrs.Ht. CS tank consting
Sr.no | Description | Size | Qty | Unit | Rate | Amount | Remarks
A. | Plates
1 | Shell plate (10 mm thk.-3 nos course) | 10 mm thk. x 6.3 m x 1.5 m | 4450.92 | Kgs | 40 | 178036.8
2 | Shell plate (8 mm thk.-6 nos course) | 8 mm thk. x 6.3 m x 1.5 m | 7121.52 | Kgs | 40 | 284860.8
3 | Shell plate (6 mm thk.-8 nos course) | 6 mm thk. x 6.3 m x 1.5 m | 7121.44 | Kgs | 40 | 284857.6
4 | Shell plate (5 mm thk.-3 nos course) | 5 mm thk. x 6.3 m x 1.5 m | 2220.72 | Kgs | 40 | 88828.8
5 | Bottom plate (10 mm thk.) | 10 mm thk. x 6.3 m x 1.5 m | 1500 | Kgs | 40 | 60000
6 | Top roof plate (5 mm thk.) | 5 mm thk. x 6.3 m x 1.5 m | 741.82 | Kgs | 40 | 29672.8
7 | Anchor chair plate (32 mm thk.) | 32 mm thk. x 6.3 m x 1.5 m | 2373.84 | Kgs | 40 | 94953.6
8 | Guset plate/pad plate (5 mm thk.) | 5 mm thk. x 6.3 m x 1.5 m | 370.91 | Kgs | 40 | 14836.4
9 | Central drum/Bottom sump | 6 mm thk. | 300 | Kgs | 40 | 12000
B. | Structural material |  | 1800 | Kgs | 40 | 72000
1 | Curb angle (18.84 Mtrs) | 75 x 75 x 8 mm thk.
2 | Wind gurder channel (2 Nos) | ISMC 100
3 | Top roof supporting channel | ISMC 100
4 | Hand railing pipe | 40 NB GI. | 30 | Mtrs | 220 | 6600
C. | Nozzle pipe & flanges
1 | Manhole (2 Nos) 10 mm thk. | 600 NB (2 m x 1 m) | 200 | Kgs | 40 | 8000
2 | On shell (6 Nos) | 150 NB | 1 | Mtrs | 1540 | 1540 | Pipe,Sch.40,smls
3 | On shell (2 Nos) | 100 NB | 0.3 | Mtrs | 876 | 262.8 | Pipe,Sch.40,smls
4 | On shell (2 Nos) | 80 NB | 0.3 | Mtrs | 633 | 189.9 | Pipe,Sch.40,smls
5 | On shell (8 Nos) | 50 NB | 1.2 | Mtrs | 307 | 368.4 | Pipe,Sch.40,smls
6 | Flange A 105,sorf,150# | 600 NB | 2 | Nos | 15000 | 30000
7 | Flange A 105,sorf,150# | 150 NB | 6 | Nos | 540 | 3240
8 | Flange A 105,sorf,150# | 100 NB | 2 | Nos | 360 | 720
9 | Flange A 105,sorf,150# | 80 NB | 2 | Nos | 330 | 660
10 | Flange A 105,sorf,150# | 50 NB | 8 | Nos | 155 | 1240
11 | Blind flange A 105,150 # | 600 NB | 1 | Nos | 20000 | 20000
12 | Stud and nut | 1 1/4" x 175 mm | 20 | Nos | 220 | 4400
D. | Steam coil 50 NB
1 | Pipe,SS 304,Sch.40,erw | 50 NB | 50 | Mtrs | 893 | 44650 | 3.91 kgs/m
2 | Elbows,SS 304,Sch.40,erw | 50 NB | 26 | Nos | 530 | 13780 | 0.710 kgs/elbow
3 | SS 304 angle | 60 x 60 x 6mm | 12 | Mtrs | 1242 | 14904 | 5.40 kgs/m
4 | SS 304 Clamp (u bolt with 2 nuts) | 50 NB | 26 | Nos | 150 | 3900 | 0.140 kgs/pcs.
5 | Flange,sorf,ss 304,150# | 50 NB | 2 | Nos | 790 | 1580 | 2.3 kgs/pcs.
|  |  |  | Total |  | 1276081.9
Total weight
Sr.no | Description | Qty | Unit
A | Plates
1 | 10 mm thk. | 6150.92 | Kgs
2 | 8 mm thk. | 7121.52 | Kgs
3 | 6 mm thk. | 7421.44 | Kgs
4 | 5 mm thk. | 3333.45 | Kgs
5 | 32 mm thk. | 2373.84 | Kgs
B | Structural steel | 1800 | Kgs
1 | Hand railing | 30 | Mtrs
2 | Nozzle pipe & Flanges | 1000 | Kgs
C. | SS coil & structural | 380 | Kgs
| Total | 29611.17 | Kgs
Services
Sr.no | Description | Qty | Unit | Rate | Amount
3 | Fabrication and erection of CS | 26401.17 | Kgs | 25 | 660029.25
4 | Structural steel fabrication and erection | 1800 | Kgs | 25 | 45000
5 | Hand railing | 30 | mtrs | 300 | 9000
6 | Sand blasting and painting | 484 | m2 | 450 | 217800
7 | Nozzle fab & erection |  |  |  | 0
| 600 NB | 2 | Nos | 5000 | 10000
| 150 NB | 6 | Nos | 1400 | 8400
| 100 NB | 2 | Nos | 100 | 200
| 80 NB | 2 | Nos | 800 | 1600
| 50 NB | 8 | Nos | 600 | 4800
8 | SS coil fabrication and erection | 130 | INM | 336 | 43680
9 | SS structural fab ere. | 65 | Kgs | 45 | 2925
10 | Instrumentation |  | 1 | Au | 100000
|  |  | Total |  | 1103434.25
Summary
Sr.no | Description | Amount
1 | Material | 1276081.9
2 | Services | 1103434.25
| Total amount | 2379516.15

## 4 m x 30 m Ht.SS
4 mtrs.Dia. X 30 mtrs.Ht. SS tank consting
Sr.no | Description | Size | Qty | Unit | Rate | Amount | Remarks
A. | Plates
1 | Shell plate (10 mm thk.-3 nos course) | 10 mm thk. x 6.3 m x 1.5 m | 4543.32 | Kgs | 210 | 954097.2
2 | Shell plate (8 mm thk.-6 nos course) | 8 mm thk. x 6.3 m x 1.5 m | 7269.36 | Kgs | 210 | 1526565.6
3 | Shell plate (6 mm thk.-8 nos course) | 6 mm thk. x 6.3 m x 1.5 m | 7269.28 | Kgs | 210 | 1526548.8
4 | Shell plate (5 mm thk.-3 nos course) | 5 mm thk. x 6.3 m x 1.5 m | 2220.72 | Kgs | 210 | 466351.2
5 | Bottom plate (10 mm thk.) | 10 mm thk. x 6.3 m x 1.5 m | 1500 | Kgs | 210 | 315000
6 | Top roof plate (5 mm thk.) | 5 mm thk. x 6.3 m x 1.5 m | 757.22 | Kgs | 210 | 159016.2
7 | Anchor chair plate (32 mm thk.) | 32 mm thk. x 6.3 m x 1.5 m | 2373.84 | Kgs | 210 | 498506.4
8 | Guset plate/pad plate (5 mm thk.) | 5 mm thk. x 6.3 m x 1.5 m | 378.61 | Kgs | 210 | 79508.1
9 | Central drum/Bottom sump | 6 mm thk. | 310 | Kgs | 210 | 65100
B. | Structural material |  | 1800 | Kgs | 40 | 72000
1 | Curb angle (18.84 Mtrs) | 75 x 75 x 8 mm thk.
2 | Wind gurder channel (2 Nos) | ISMC 100
3 | Top roof supporting channel | ISMC 100
4 | Hand railing pipe | 40 NB GI. | 30 | Mtrs | 220 | 6600
C. | Nozzle pipe & flanges
1 | Manhole (2 Nos) 10 mm thk. | 600 NB (2 m x 1 m) | 200 | Kgs | 210 | 42000
2 | On shell (6 Nos) | 150 NB | 1 | Mtrs | 1800 | 1800 | Pipe,Sch.40,smls
3 | On shell (2 Nos) | 100 NB | 0.3 | Mtrs | 1550 | 465 | Pipe,Sch.40,smls
4 | On shell (2 Nos) | 80 NB | 0.3 | Mtrs | 1260 | 378 | Pipe,Sch.40,smls
5 | On shell (8 Nos) | 50 NB | 1.2 | Mtrs | 893 | 1071.6 | Pipe,Sch.40,smls
6 | Flange A 105,sorf,150# | 600 NB | 2 | Nos | 20000 | 40000
7 | Flange A 105,sorf,150# | 150 NB | 6 | Nos | 2075 | 12450
8 | Flange A 105,sorf,150# | 100 NB | 2 | Nos | 1600 | 3200
9 | Flange A 105,sorf,150# | 80 NB | 2 | Nos | 1100 | 2200
10 | Flange A 105,sorf,150# | 50 NB | 8 | Nos | 790 | 6320
11 | Blind flange A 105,150 # | 600 NB | 1 | Nos | 24000 | 24000
12 | Stud and nut | 1 1/4" x 175 mm | 20 | Nos | 220 | 4400
D. | Steam coil 50 NB
1 | Pipe,SS 304,Sch.40,erw | 50 NB | 50 | Mtrs | 893 | 44650 | 3.91 kgs/m
2 | Elbows,SS 304,Sch.40,erw | 50 NB | 26 | Nos | 530 | 13780 | 0.710 kgs/elbow
3 | SS 304 angle | 60 x 60 x 6mm | 12 | Mtrs | 1242 | 14904 | 5.40 kgs/m
4 | SS 304 Clamp (u bolt with 2 nuts) | 50 NB | 26 | Nos | 150 | 3900 | 0.140 kgs/pcs.
5 | Flange,sorf,ss 304,150# | 50 NB | 2 | Nos | 790 | 1580 | 2.3 kgs/pcs.
|  |  |  | Total |  | 5886392.1
Total weight
Sr.no | Description | Qty | Unit
A | Plates
1 | 10 mm thk. | 6243.32 | Kgs
2 | 8 mm thk. | 7269.36 | Kgs
3 | 6 mm thk. | 7579.28 | Kgs
4 | 5 mm thk. | 3356.55 | Kgs
5 | 32 mm thk. | 2373.84 | Kgs
B | Structural steel | 1800 | Kgs
1 | Hand railing | 30 | Mtrs
2 | Nozzle pipe & Flanges | 1000 | Kgs
C. | SS coil & structural | 380 | Kgs
| Total | 30032.35 | Kgs
Services
Sr.no | Description | Qty | Unit | Rate | Amount
3 | Fabrication and erection of ss | 26822.35 | Kgs | 65 | 1743452.75
4 | Structural steel fabrication and erection | 1800 | Kgs | 25 | 45000
5 | Hand railing | 30 | mtrs | 300 | 9000
7 | Nozzle fab & erection |  |  |  | 0
| 600 NB | 2 | Nos | 5000 | 10000
| 150 NB | 6 | Nos | 1400 | 8400
| 100 NB | 2 | Nos | 100 | 200
| 80 NB | 2 | Nos | 800 | 1600
| 50 NB | 8 | Nos | 600 | 4800
8 | SS coil fabrication and erection | 130 | INM | 336 | 43680
9 | SS structural fab ere. | 65 | Kgs | 45 | 2925
10 | Instrumentation |  | 1 | Au | 100000
|  |  | Total |  | 1969057.75
Summary
Sr.no | Description | Amount
1 | Material | 5886392.1
2 | Services | 1969057.75
| Total amount | 7855449.85

## New utilities
New utility requirement at Guwahati
Sr.no. | Description | Amount | Tax amount
A. | N2 Plant | 3000000 | 750000
| Piping material with Services | 200000 | 29000
B. | Air Compressor | 2000000 | 500000
| Piping material with Services | 150000 | 21750
C. | ETP | 10000000 | 2500000
D. | Cooling tower clean-350 M3/Hr. x 2 Nos | 750000 | 187500
| Piping material with Services | 500000 | 72500
E. | Cooling tower Dirty-110 M3/Hr. | 250000 | 62500
| Piping material with Services | 300000 | 43500
F. | Chimney (Common) | 6000000 | 1500000
| Total | 23150000 | 5666750 | 28816750
|  | W/O TAX | ONLY TAX | WITH TAX

## MP boiler& Fuel feeding
MP Boiler & fuel feeding system Baddi to Guwahati shifting
Sr.no. | Description | Amount | Tax amount
A. | Boiler package with fuel feeding system dismantling with loading | 3000000 | 435000
B. | Transportation (Baddi to Guwahati) | 5200000 | 754000
C. | Other equipment dismantling & loading | 800000 | 116000
D. | Re-erection whole unit at Guwahati | 3500000 | 507500
E. | IBR approval charges with IBR material | 4500000 | 652500
F. | Engineering of OSBL & IBR piping | 1100000 | 159500
G. | Material cost | 800000 | 200000
| Non IBR piping | 800000
H. | Piping fabrication & Erection services | 4200000 | 609000
IBR/Non IBR piping
I. | Insulation cost | 1400000 | 203000
Non IBR piping
IBR piping
Equipments
J. | Thermax & other vendor supervision charges | 1000000 | 145000
K. | Refurbishing cost | 1200000 | 174000
| Equipments | 600000
| SM items | 600000
L. | Material handling and packeging cost | 1500000 | 217500
M. | Crane hiring charges | 800000 | 116000
| Total (Material + Services) | 28200000 | 4173000 | 32373000
|  | W/O TAX | ONLY TAX | WITH TAX