## Sheet1
Talent Management - CMB
| 3rd August, 2012 | In attendance: Hoshi Press, Gitanjali Diwan, Rhiju Bhowmick, Charles Carvalho
| Name of initiative | Discussion | Activities | Person responsible | Timelines
A) | Training
1 | · Functional Training | Need to identify functional training needs of employees in the CMB function and conduct those trainings based on the budgets available, availability of trainers etc. | 1) Gather data from Dubai HR regarding the roles and responsibilities of the CMB function there. Organize roles and responsibility clarification sessions. 2) Map areas that overlap between Oleo and CMB to identify functions that will benefit from common functional training. 3) Meet Radhesh to understand trainings planned for Oleo and discuss possibility of jointly conducting training for areas that overlap (as identified in 2 above) | Charles and Gitanjali | 10th August
2 | · Mentoring & Coaching | Identification of vendors and associated costs. | To be planned and executed once structural issues are sorted out as detailed. | Charles | NA
3 | · 360 degree feedback
4 | · Segregation of employees
B) | Management Trainee program
1 | · B School hiring in March-Apr | Possibility of visiting b-schools that are of good quality but not on the radar of our competitors due to various reasons. Introducing basic psychometrics like MBTI, 16 PF etc which can be used to assess quality and fit of hire. Deciding what sort of roles are to be offered. E.g. whether directly offer a marketing position or first sales and then marketing. Also, explore the option of offering summer internships and making pre-placement offers to suitable candidates. | 1) Shortlist second tier b-schools where we could get a day 0 or day 1 slot. 2) Finalize vendors for psychometric and get budget approvals 3) Decide the number of MTs to be taken and profiles to be offered | Recruitment head and Charles | After joining of recruitment head
2 | · Set quality standards
3 | · Introduce Psychometric testing
C) | Talent quality Review
1 | · Review and assessments | Possibly introduce a performance improvement plan for underperformers. Also, decide on sterner measures including termination for repeat under performers i.e. those who are rated 1 and 2 for 2 successive years during the final review. | Decided to keep this pending until structure finalized and KRA's are sorted out | NA | NA
2 | · Clean out KRAs & KPIs
3 | · Recognize talent
D) | Salary benchmarking
1 | · Annual benchmarking of compensation | Find out if budgets available for salary surveys or need additional approval. Initiate process and timelines | 1) Budget for survey 2) Finalizing vendors 3) Inputs to recruitment team | Anuradha | 2012-11-01
2 | · Inputs to hiring and revision