## Sheet1
REBUILD TECHNOLOGIES SERVICES PVT LTD
Micro Schedule for D2D25 Foundation Repair work
Sr No | Activity | Duration | Date | Tentative Start time | Tentative Finish Time | Status
1 | Registration and Safety Induction |  | 2016-05-10 |  |  | Completed
2 | Preparation of Support | 1 Day | 2016-05-10 | 9:30 | 17:00 | Completed
3 | Preparation of Share Key and Reinforcement | 1 Day | 2016-05-12 | 9:30 | 17:00 | Completed
4 | Fixing of Support | 1.5 hrs. | 2016-05-14 | 4.3 | 6
5 | Breaking of Column | 5 hrs. | 2016-05-14 | 6 | 11.05
6 | Cleaning of Columns | 2 Hrs | 2016-05-14 | 9.3 | 11.3
7 | Polymer Modified Mortar | 4 Hrs | 2016-05-14 | 12.3 | 16.3
8 | Fixing of Grout Nozzles. | 3 hrs. | 2016-05-14 | 20.3 | 23.3
9 | Epoxy Grouting | 24 Hrs | 15-05-2016 to 16/05/2016 | 0.3 | 23.3
10 | Fixing of Reinforcement | 3 hrs. | 2016-05-17 | 6.3 | 9.3
11 | Cutting of Nozzles | 1 Hrs | 2016-05-17 | 23.45 | 0.45
12 | Preparation of Shuttering | 4 Hrs | 2016-05-17 | 21.3 | 1.3
13 | Application of Bonding Agent | 1 Hrs | 2016-05-18 | 1.3 | 2.3
14 | Pouring of Micro concrete | 30 Hrs | 18-05-2016 | 3 | 10.3
15 | De-shuttering & removing Temporary Supports. | 2Hrs | 2016-05-18 | 1 | 3
16 | Hand Over |  | 2016-05-18 |  | 4
Note - All required materials available at Site.