## Summary
Costing: VEGA ETS at Hydrogenation Plant Baddi (Considering MCT Sion Equipments)
Feasibility is being explored for producing VEGA ETS at Baddi hydrogenation plant. The baddi hydrogenation plant is currently operating with MP steam. The hydrogenator will operate for the reaction through circulation mode using TF heat exchanger. TF piping with temperature control system - primary will need to be incorporated. Condenser unit, vacuum / nitrogen purging system to be incorporated. Existing V701- 13KL hydrogenator, V700- 8KL Discharge Tank as Bleacher, E706 cooler, AMA filter, Candle filter, Flaker will be used as is basis. The expected capacity of VEGA ETS production with this set up will be 6.75 MT per day considering 1.5 batch/day. Annual production will be 2362.5 MT. The detailed first cut cost is provided in the table below.
|  |  |  | 09.06.16 | 02.06.16
1 | New Equipments cost |  | Rs. Lakh | 0 | 0
2 | Asset transfer cost of relocated equipments |  | Rs. Lakh | 36 | 36.007
3 | 08 KL MCT bleacher vessel, HE-2nos & pumps shifting fom Sion
a | Dismantle HE-2nos at sion for dispatch to Baddi |  | Rs. Lakh | 0.2 | 4
b | transportation from sion to baddi |  | Rs. Lakh | 3 | 4
c | Crane cost at Sion - 1 shifts |  | Rs. Lakh | 0 | 0.75
d | Crane cost at Baddi - 1 shifts |  | Rs. Lakh | 0.75 | 0.75
4 | Mechanical costing
a | Mechanical material |  | Rs. Lakh | 12.7 | 37.0824
b | Mechanical service |  | Rs. Lakh | 10.64 | 20.02
c | Insulation Supply |  | Rs. Lakh | 3.91 | 4.3484
d | Insulation service |  | Rs. Lakh | 1.68 | 1.8636
5 | Refurbushing of existing equipments (on need basis) |  | Rs. Lakh | 1.8 | 3.8
6 | Commissioning consummables |  | Rs. Lakh | 5 | 5
7 | Instrumentation cost - Materials |  | Rs. Lakh | 6.86 | 8.93
8 | Instrumentation cost - Services |  | Rs. Lakh | 1 | 3
9 | Civil cost - Materials |  | Rs. Lakh | 2 | 4.74
10 | Civil cost - Services |  | Rs. Lakh | 1.5 | 3.16
11 | Electrical cost - Materials |  | Rs. Lakh | 2 | 4
12 | Electrical cost - Services |  | Rs. Lakh | 1 | 2
13 | Thermic fluid Cost - Hitherm 600 |  | Rs. Lakh | 3.3 | 2.2
14 | Weighing, Bagging & stitching system |  | Rs. Lakh | 0 | 0
15 | Multimill |  | Rs. Lakh | 2 | 2
| Total |  | Rs. Lakh | 95.34 | 147.6514
|  | Cash Flow |  | 59.34 | 111.6444 | without taxes
Based on batch size of 4.5 MT & 1.5 batch per day, the annual production capacity will be 2362.5 MT

## ETS Baddi_Instrument
Instrumentation costing for Vega ETS @Loop reactor Baddi
Sr. No. | Tag No. | Type of Instrument | AI/AO | Description | Size | Remarks | Qty | unit Cost | Cost
1 | FT 301 | Flow Transmitter | AI | V-701 | 25NB | At Actual Site 40 NB present/ Display card faulty | 1 | 15000 | 15000
2 | FCV 301 | Control Valve | AO | V-701 | 25 NB | 40 NB Present at site/ Servicing required/Loc: baddi plant | 1 | 30000 | 30000
3 | FCV 301 | Control Valve | AO | E-705 TF control valve | 80 NB | Available in Plant C302 -for TF line after TF secondary loop Project TCV-3411 Samson Servicing required Loc : Taloja Plant/Considered trim set change of valve-Sizing required. | 1 | 55000 | 55000
4 | TT | Temp Transmitter | AI | E-705, |  | TT available at taloja 3 no's, TW & RTD new Procurement required | 3 | 9000 | 27000
5 | LT | Level Transmitter | AI | V-700/ V701 |  | cancelled.--as per instruction of Anandrao sir | 2 | 0 | 0
6 | PG | Pressure gauge | L | various loc-Pump outlet, E710 |  | Not working/ New Proc./ Checking required | 8 | 3500 | 28000
7 | TG |  | L | various loc-E705, E710 |  | Not working/ New Proc./ Checking required | 6 | 7000 | 42000
8 | LT | Level Transmitter |  | V-715 |  | New Procurement-Material service/Non cotact type radar or Capillary type required. | 1 | 200000 | 200000
9 |  | Instrument cable |  |  |  | Single pair /3 core power cable to controller /Power JB | 1 | 65000 | 65000
10 |  | cable tray & structure steel |  |  |  |  | 1 | 35000 | 35000
11 |  | Junction box |  |  |  | new procurement for Power | 1 | 7000 | 7000
12 |  | cable gland & misc. |  |  |  |  | 1 | 30000 | 30000
13 |  | Fitting material & Cu tube |  |  |  | High pressure/High temp suitable fitting material | 1 | 25000 | 25000
14 |  | Misc. items/Inline TW/accessories |  |  |  |  | 1 | 25000 | 25000
15 |  | Controller & Indicators |  |  |  | With Mounting | 4 | 8000 | 32000
16 |  | Service for Instrumentation Erection |  |  |  | Service cost for Inst Erection installation | 1 | 100000 | 100000
17 |  | N2 PRV system |  |  |  | New Procurement |  |  | 70000
[8 empty] | Total | 786000

## Mech.sum
Summary
Sr.no. | Description | Amount | Tax
1 | Material | 1268848.35 | 317212.0875
2 | Services | 1064570 | 154362.65
3 | Insulation | 558200 | 80939
|  | 2891618.35 | 552513.7375 | 3444132.0875
|  | W/O tax | only tax | With tax

## Material
Material | MOC | Size | Qty | Unit | Rate | Amount | Remark | Fittings 50% | Gasket 10% | Stud & nut 7.5% | Total | CS PIPE
Pipe | CS A106 | 4" | 30 | M | 1000 | 30000 | TF circulation | 15000 | 3000 | 2250 | 50250 | 4 | 30 | 120 | 33.3574
|  | 3" | 200 | M | 694 | 138800 | TFS/TFR | 69400 | 13880 | 10410 | 232490 | 3 | 200 | 600 | 207.306
|  | 2" | 30 | M | 345 | 10350 | Drain | 5175 | 1035 | 776.25 | 17336.25 | 2 | 30 | 60 | 28.269
|  | 1" | 100 | M | 165 | 16500 | vent | 8250 | 1650 | 1237.5 | 27637.5 | 1 | 100 | 100 | 86.0634
| CS IS1239 | 3" | 18 | M | 390 | 7020 | CW to E-710 | 3510 | 702 | 526.5 | 11758.5 | 3 | 18 | 54
|  | 2" | 10 | M | 270 | 2700 | drain | 1350 | 270 | 202.5 | 4522.5 | 2 | 10 | 20
|  | 1.5" | 10 | M | 220 | 2200 | Drain | 1100 | 220 | 165 | 3685 | 1.5 | 10 | 15
|  | 1" | 24 | M | 130 | 3120 | CW to V700 | 1560 | 312 | 234 | 5226 | 1 | 24 | 24
|  | 1/2" | 60 | M | 70 | 4200 | Misc | 2100 | 420 | 315 | 7035 | 1 | 60 | 60
| SS304 | 4" | 18 | M | 1550 | 27900 | Vacuum | 13950 | 2790 | 2092.5 | 46732.5 |  | 482 | 1053
|  | 3" | 0 | M | 1260 | 0 | Feed to pump | 0 | 0 | 0 | 0
|  | 2" | 10 | M | 350 | 3500 | Feed to reactor | 1750 | 350 | 262.5 | 5862.5
|  | 1.5" | 20 | M | 300 | 6000 | Product to flaker | 3000 | 600 | 450 | 10050 | SS PIPE
|  | 1" | 40 | M | 630 | 25200 | N2 | 12600 | 2520 | 1890 | 42210 | 4 | 18 | 72 | 12.0991
| SS316L | 4" | 30 | M | 6000 | 180000 | E-708 location at boiler house | 90000 | 18000 | 13500 | 301500 | 3 | 0 | 0
|  | 3" | 6 | M | 5335 | 32010 | transfer line to V700 | 16005 | 3201 | 2400.75 | 53616.75 | 2 | 10 | 20 | 5.0256
| New Piping Material cost |  |  |  |  | 489500 |  | 244750 | 48950 | 36712.5 | 819912.5 | 1.5 | 20 | 30 | 9.423
| Available Sion + Taloja |  |  |  |  | 320002.34 |  | 26597.54 | 0 | 9268.27 | 355868.15 | 1 | 40 | 40 | 16.8358
| Final Required material cost |  |  |  |  | 169497.66 |  | 218152.46 | 48950 | 27444.23 | 464044.35 | 4 | 30 | 120 | 25.819
[12 empty] | 3 | 6 | 18 | 4.7115
Valve | Bellow seal | 4" | 5 | Nos | 53400 | 267000 | [6 empty] | 124 | 300
|  | 3" | 5 | Nos | 26000 | 130000 | [5 empty] | Steam Tracing |  | 310
|  | 1" | 4 | nos | 6100 | 24400
| SS 316L | 4" | 4 | Nos | 40000 | 160000 | [5 empty] | Valve
|  | 3" | 1 | Nos | 25000 | 25000 | [5 empty] | 4 | 6 | 24
|  | 1" | 2 | Nos | 21500 | 43000 | [5 empty] | 3 | 5 | 15
| SS304 | 4" | 1 | Nos | 22200 | 22200 | [5 empty] | 1 | 4 | 4
|  | 3" | 2 | Nos | 12450 | 24900 | [5 empty] | 4 | 4 | 16
|  | 2" | 6 | Nos | 6200 | 37200 | [5 empty] | 3 | 2 | 6
|  | 1" | 4 | Nos | 2640 | 10560 | [5 empty] | 1 | 2 | 2
| CS gate/NRV | 3" | 4 | Nos | 7500 | 30000 | [5 empty] | 4 | 1 | 4
|  | 2" | 13 | Nos | 5600 | 72800 | [5 empty] | 3 | 2 | 6
|  | 1.5" | 2 | Nos | 5472 | 10944 | [5 empty] | 2 | 8 | 16
|  | 1" | 2 | Nos | 1540 | 3080 | [5 empty] | 1 | 4 | 4
|  | 1/2" | 20 | Nos | 1100 | 22000 | [5 empty] | 3 | 4 | 12
[6 empty] | 0 | [5 empty] | 2 | 13 | 26
Trap | CS | 1/2" | 10 | Nos | 3000 | 30000 | [5 empty] | 1.5 | 2 | 3
Strainer | CS | 4" | 1 | Nos | 22000 | 22000 | [5 empty] | 1 | 2 | 2
|  | 2" | 1 | Nos | 2500 | 2500 | [5 empty] | 0.5 | 20 | 10
| SS304 | 3" | 1 | Nos | 12000 | 12000 | [7 empty] | 150
|  | 2" | 1 | Nos | 5800 | 5800 | [5 empty] | Trap
| SS316L | 4" | 0 | Nos | 45000 | 0 | [5 empty] | 1 | 10 | 10
[6 empty] | 0 | [7 empty] | 160
Vessel trim |  |  | 1 | AU | 100000 | 100000
Misc material | (SV/FV/Hoses) |  | 1 | AU | 150000 | 150000
Steam Tracing | SS304 | 12.5 mm | 310 | M | 160 | 49600 | [5 empty] | Equipment erection
Total valve cost | [5 empty] | 1254984 | [5 empty] | N2 plant | 0
Available at Sion and Taloja | [5 empty] | 450180 | [5 empty] | V700 | 0
Final amount required against valve | [5 empty] | 804804 | [5 empty] | Exchanger 2 nos | 5
[12 empty] | Storage tank | 5
[12 empty] | Water tank | 0
[12 empty] | Pump 5 nos | 3
13

## Required material
Material | MOC | Size | Qty | Unit | Rate | Amount | Remark | Fittings 50% | Gasket 10% | Stud & nut 7.5% | Total
Pipe | CS A106 | 4" | 30 | M | 1000 | 30000 | TF circulation | 15000 | 3000 | 2250 | 50250
|  | 3" | 200 | M | 694 | 138800 | TFS/TFR | 69400 | 13880 | 10410 | 232490
|  | 2" | 30 | M | 345 | 10350 | Drain | 5175 | 1035 | 776.25 | 17336.25
|  | 1" | 100 | M | 165 | 16500 | vent | 8250 | 1650 | 1237.5 | 27637.5
| CS IS1239 | 3" | 18 | M | 390 | 7020 | CW to E-710 | 3510 | 702 | 526.5 | 11758.5
|  | 2" | 10 | M | 270 | 2700 | drain | 1350 | 270 | 202.5 | 4522.5
|  | 1.5" | 10 | M | 220 | 2200 | Drain | 1100 | 220 | 165 | 3685
|  | 1" | 24 | M | 130 | 3120 | CW to V700 | 1560 | 312 | 234 | 5226
|  | 1/2" | 60 | M | 70 | 4200 | Misc | 2100 | 420 | 315 | 7035
| SS304 | 4" | 18 | M | 1550 | 27900 | Vacuum | 13950 | 2790 | 2092.5 | 46732.5
|  | 3" | 0 | M | 1260 | 0 | Feed to pump | 0 | 0 | 0 | 0
|  | 2" | 10 | M | 350 | 3500 | Feed to reactor | 1750 | 350 | 262.5 | 5862.5
|  | 1.5" | 20 | M | 300 | 6000 | Product to flaker | 3000 | 600 | 450 | 10050
|  | 1" | 40 | M | 630 | 25200 | N2 | 12600 | 2520 | 1890 | 42210
| SS316L | 4" | 30 | M | 6000 | 180000 | E-708 location at boiler house | 90000 | 18000 | 13500 | 301500
|  | 3" | 6 | M | 5335 | 32010 | transfer line to V700 | 16005 | 3201 | 2400.75 | 53616.75
|  |  |  | Required Material cost |  | 489500 |  | 244750 | 48950 | 36712.5 | 819912.5
|  |  |  | Sion material cost |  | 104492.34 | SS316 ,ERW,Sch.40 | 16597.54 |  | 9268.27 | 130358.15
|  |  |  | Taloja material cost |  | 215510 |  | 10000 |  |  | 225510
[8 empty] | Required cost |  |  | 689554.35
Material | MOC | Size | QTY. | Sion | Taloja | Req. Qty. | Unit | Rate | Amount | Remark
Valve | Bellow seal | 4" | 5 |  |  | 5 | Nos | 53400 | 267000
|  | 3" | 5 |  |  | 5 | Nos | 26000 | 130000
|  | 1" | 4 |  |  | 4 | nos | 6100 | 24400
| SS 316L | 4" | 4 | 4 |  | 0 | Nos | 40000 | 0 | Gate valve,150#/SS316
|  | 3" | 1 | 1 |  | 0 | Nos | 25000 | 0 | Ball valve ,150#
|  | 1" | 2 | 2 |  | 0 | Nos | 21500 | 0 | Ball valve ,150#/SS 316 (gate v-2 nos avail.
| SS304 | 4" | 1 |  | 1 | 0 | Nos | 22200 | 0 | gate valve,150#
|  | 3" | 2 | 2 |  | 0 | Nos | 12450 | 0 | Ball valve ,150#-SS304/SS316L
|  | 2" | 6 | 6 |  | 0 | Nos | 6200 | 0
|  | 1" | 4 | 4 |  | 0 | Nos | 2640 | 0
| CS gate/NRV | 3" | 4 |  |  | 4 | Nos | 7500 | 30000
|  | 2" | 13 |  | 2 | 11 | Nos | 5600 | 61600 | Gate valve,150#
|  | 1.5" | 2 |  |  | 2 | Nos | 5472 | 10944
|  | 1" | 2 |  |  | 2 | Nos | 1540 | 3080
|  | 1/2" | 20 |  | 20 | 0 | Nos | 1100 | 0 | 800#,SW,gate
[6 empty] | 0 |  |  | 0
Trap | CS | 1/2" | 10 | 10 |  | 0 | Nos | 3000 | 0
Strainer | CS | 4" | 1 |  | 1 | 0 | Nos | 22000 | 0 | Y type,150#
|  | 2" | 1 |  |  | 1 | Nos | 2500 | 2500
| SS304 | 3" | 1 |  | 1 | 0 | Nos | 12000 | 0 | SS316,Y-type,150#
|  | 2" | 1 |  | 1 | 0 | Nos | 5800 | 0 | SS304,Y-type,150#
| SS316L | 4" | 0 |  |  | 0 | Nos | 45000 | 0
[6 empty] | 0 |  |  | 0
Vessel trim |  |  | 1 |  |  | 1 | AU | 100000 | 100000
Misc material | (SV/FV/Hoses) |  | 1 |  |  | 1 | AU | 150000 | 150000
Steam Tracing | SS304 | 12.5 mm | 310 | 152 |  | 158 | M | 160 | 25280
[7 empty] | Total |  | 804804

## Services
Mechanical execution costing for VEGA ETS @ Baddi Hydrogenation unit
Sr No. | Description | Qty | Unit | Rate | Total
A | Piping
1 | SS 316L Pipe Fabriction and erection | 300 | INM | 348 | 104400
2 | Steam tracing fabriction and erection | 310 | RNM | 190 | 58900
3 | CS pipe fabrication and erection | 1053 | INM | 210 | 221130
4 | SS shoe support Fab and erection | 100 | IND | 147 | 14700
5 | CS shoe support fab and erection | 300 | IND | 126 | 37800
6 | Spring support erection | 4 | Nos | 2500 | 10000
7 | Trunion support Fab and erection | 4 | Nos | 6000 | 24000
8 | SS Modification | 60 | IND | 588 | 35280
9 | CS Modification | 50 | IND | 378 | 18900
10 | Valve installation | 160 | IND | 126 | 20160
11 | DP test | 300 | IND | 31.5 | 9450
12 | Radiography | 100 | IND | 336 | 33600 | 10% Random
13 | Dismentling of SS pipe | 100 | INM | 225 | 22500
14 | Dismentling of CS pipe | 100 | INM | 120 | 12000
15 | Erection of rotary equipment | 3 | MT | 6500 | 19500
16 | Erection of static equipment | 10 | MT | 4725 | 47250
17 | Existing V700 dismantling@ Sion and shifting @ Baddi | 0 | AU | 130000 | 0
18 | Dismentling and shifting of rotary euipment | 0 | MT | 6000 | 0
19 | Material Unloading | 1 | AU | 35000 | 35000
20 | Manpower supply | 1 | AU | 15000 | 15000
21 | Detail Engineering | 1 | AU | 300000 | 300000
22 | Chemical cleaning | 1 | AU | 0 | 0 | Not consider
23 | Pipe support | 1 | MT | 15000 | 15000
24 | Material Inspection | 1 | AU | 0 | 0 | Not consider
25 | Dismantling of existing Equipment | 2 | MT | 5000 | 10000
1064570
| Service charges 14.5% |  |  |  | 154362.65
| Total |  |  |  | 1218932.65
B | Insulation
1 | Removal of insulation | 0 | AU | 75000 | 0
2 | LRB 50mm with 24swg aluminum cladding | 100 | m2 | 800 | 80000
3 | LRB 80 mm with 24swg aluminum clading | 60 | m2 | 1120 | 67200
5 | LRB 120 mm with 24 swg aluminum cladding | 300 | m2 | 1250 | 375000
6 | LRB 150 mm with 24 swg aluminum cladding | 0 | m2 | 1350 | 0
7 | LRB 170 mm with 22 swg aluminum cladding | 5 | m2 | 1500 | 7500
8 | Aluminum foil 0.1 mm thk | 100 | m2 | 135 | 13500
9 | Scaffolding | 200 | m2 | 75 | 15000
558200
| Service charges 14.5% |  |  |  | 80939
| Total |  |  |  | 639139

## Sion stock
Stock Statement of Sion Plant as on 31.03.2016
Plant Code | Material Code | Material Description | Closing Stock | UOM | Closing Value | Curr
101 | 1304795 | BOLT & NUT MS 1/2"X1.1/2" | 20.112 | KG | 1570.75 | INR
101 | 1304796 | BOLT & NUT MS 1/2"X2" | 17.4 | KG | 1230.92 | INR
101 | 1304798 | BOLT & NUT MS 1/2"X2.1/2" | 11.5 | KG | 647.94 | INR
101 | 1304812 | BOLT & NUT MS 3/4"X4.1/2" | 4.872 | KG | 270.59 | INR
101 | 1304813 | BOLT & NUT MS 3/4"X5" | 9.199 | KG | 367.98 | INR
101 | 1304814 | BOLT & NUT MS 3/4"X6" | 10.128 | KG | 597.5 | INR
101 | 1304832 | BOLT & NUT MS 5/8"X3.1/2" | 10.981 | KG | 616.64 | INR
101 | 1304833 | BOLT & NUT MS 5/8"X4" | 69.05 | KG | 3965.95 | INR
9268.27
101 | 1304538 | ELBOW SS304 1" R=1.5D SMLS SCH40 | 12 | NOS | 748.8 | INR
101 | 1304622 | ELBOW CS 1.1/2" R=1.5D SMLS | 5 | NOS | 333.32 | INR
101 | 1304627 | ELBOW CS 3" R=1.5D SMLS SCH40 | 4 | NOS | 927.68 | INR
101 | 1304662 | ELBOW CS 90D 4" SMLS SCH40 | 2 | NOS | 692.64 | INR
101 | 1304690 | ELBOW CS TO ASTM 234 WPB 2" R=1.5D SCH40 | 4 | NOS | 373.65 | INR
101 | 1304716 | ELBOW SS316L 4" R=1.5D ERW SCH40 | 4 | NOS | 4840 | INR
101 | 1304772 | ELBOW SS304L 2" R=1.5D ERW SCH10 | 1 | NOS | 428.48 | INR
8344.57
101 | 1308420 | PIPE ASTMA312TP316 BE 4" ERW SCH40 | 24.99 | M | 104492.34 | INR
101 | 1306516 | TUBE SS304 SMLS 3/8"X1.2" | 152 | M | 25201.29 | INR
129693.63
101 | 1306148 | SPECTACLE BLIND SS304 3MM THK - 50 NB | 24 | NOS | 8252.94 | INR
101 | 1316529 | SPECTACLE BLIND SS304 3MM THK - 40 NB | 2 | NOS | 0.02 | INR
8252.96
101 | 1312069 | VALVE BALL SS A351 CF3M FE 3" 150# | 2 | NOS | 0.02 | INR
101 | 1312077 | VALVE BALL SS FE 1/2" | 6 | NOS | 0.06 | INR
101 | 1312083 | VALVE BALL SS304 1" | 45 | NOS | 0.07 | INR
101 | 1312085 | VALVE BALL SS304 1.1/2" | 22 | NOS | 0.02 | INR
101 | 1312089 | VALVE BALL SS304 2" | 8 | NOS | 0.08 | INR
101 | 1312090 | VALVE BALL SS304 3" | 1 | NOS | 0.01 | INR
101 | 1312101 | VALVE BALL SS316 1" | 6 | NOS | 0.06 | INR
101 | 1312102 | VALVE BALL SS316 2" | 3 | NOS | 0.03 | INR
101 | 1312178 | VALVE GLOBE CS FE 3" 300# | 1 | NOS | 1 | INR
101 | 1312349 | VALVE GATE SS316 FE 4" 10KG/CM2 | 8 | NOS | 304200 | INR
101 | 1312353 | VALVE GATE SS316L 1" 150# | 2 | NOS | 0.02 | INR
304201.37
101 | 1310151 | STEAM TRAP 1/2" THERMODYNAMIC | 3 | NOS | 0.03 | INR
101 | 1310155 | STEAM TRAP BPT21 SE 1/2" THERMOSTATIC | 7 | NOS | 21064.84 | INR
21064.87
101 | 1306245 | FLANGE SS316 4" 150# | 12 | NOS | 0.01 | INR

## Taloja stock
Taloja available material stock
Material | MOC | Size | Req.Qty | Taloja Qty. | To be ordered qty. | Unit | Rate | Amount | Remark
Pipe | CS A106 | 4" | 30 |  | 30 | M | 1000 | 30000
|  | 3" | 200 |  | 200 | M | 694 | 138800
|  | 2" | 30 |  | 30 | M | 345 | 10350
|  | 1" | 100 |  | 100 | M | 165 | 16500
| CS IS1239 | 3" | 18 |  | 18 | M | 390 | 7020
|  | 2" | 10 |  | 10 | M | 270 | 2700
|  | 1.5" | 10 |  | 10 | M | 220 | 2200
|  | 1" | 24 |  | 24 | M | 130 | 3120
|  | 1/2" | 60 |  | 60 | M | 70 | 4200
| SS304 | 4" | 18 |  | 18 | M | 1550 | 27900
|  | 3" | 0 |  | 0 | M | 1260 | 0
|  | 2" | 10 | 10 | 0 | M | 350 | 0 | SS316L,Sch.40
|  | 1.5" | 20 |  | 20 | M | 300 | 6000
|  | 1" | 40 |  | 40 | M | 630 | 25200
| SS316L | 4" | 30 | 30 | 0 | M | 6000 | 0
|  | 3" | 6 | 6 | 0 | M | 5335 | 0
273990