## Sheet1
Task Name | Duration | Start | Finish |  | Status
Project- Symphony (JBP) |  |  |  |  | 2016-09-07
JBP Shutdown |  | 2016-08-15 | 2016-09-10
Complete material receipt at site - Civil/Mechnical/Electrical/Inst | 41 | 2016-06-25 | 2016-08-05
Shutdown on 14th August
Flushed partition near spiral stair case & Near Nauta floor | 2 | 2016-08-08 | 2016-08-10 | 2016-08-30
Flush door lintel civil work | 5 | 2016-07-29 | 2016-08-03
Flush Door (Main entry, sterilizer area)- 10 No.'s | 12 | 2016-08-08 | 2016-08-20 | 2016-09-01
PVC Curtain for sterilizer powder unloading point & RM stores entry | 6 | 2016-07-29 | 2016-08-04
Door Interlocking facility | 5 | 2016-08-20 | 2016-08-25 | 2016-09-03
Removing of existing epoxy - Silo and Nauta (380 sq. m) | 5 | 2016-08-15 | 2016-08-20
SS Screw conveyors for Sterilized talc dispensing on shifter | 5 | 2016-08-20 | 2016-08-25 | 2016-09-01 |  | SS grill to be fixed in the hopper+Resting platform to be increased
Powder filling machine screw feeder | 10 | 2016-08-20 | 2016-08-30 | 2016-09-03
Change control and validation of SS screw conveyors and powder filling mahine screws |  | 2016-08-20 | 2016-08-25
Filling machine canopy work | 14 days | 2016-08-30 | 2016-09-04 | 2016-09-03 |  | Critical- To be finished by 10th without fail. Agreed with contractor
PU Flooring and Coving work across facility- Sterilizer | 7 | 2016-08-20 | 2016-08-27
PU Flooring and Coving work across facility- Silo | 7 | 2016-08-15 | 2016-08-22
PU Flooring and Coving work across facility- Nauta Mixer | 7 | 2016-08-26 | 2016-09-02
PU Flooring and Coving work across facility in Microlab | 7 | 2016-08-26 | 2016-09-02
Epoxy coating in Filling and Packing areas | 3 | 2016-08-31 | 2016-09-03
GI partition and emergency door repairing work | 1 | 2016-08-08 | 2016-08-09
Pass box brick wall, plaster and false ceiling & Interlocking | 12 | 2016-08-15 | 2016-08-27 | 2016-09-03
Change room in Visitor entry | 7 | 2016-09-01 | 2016-09-08 |  |  | Critical- To be finished by 10th without fail. Agreed with contractor
Employee change room entry door to be replaced with removed door from spiral staircase entry | 7 | 2016-09-01 | 2016-09-08 |  |  | Critical- To be finished by 10th without fail. Agreed with contractor
Change control of Pass box interlocking
Painting in Sterilizer area | 4 | 2016-08-28 | 2016-09-01
Painting in manufacturing, filling, packing and FG | 6 | 2016-09-01 | 2016-09-07
Installation of ACP sheet on sterilizer roof | 10 | 2016-08-15 | 2016-08-25 | 2016-09-08 |  | Critical- To be finished by 10th without fail. Agreed with contractor
Removal of double skin partition and false ceiling of existing Microlab | 2 | 2016-08-20 | 2016-08-22
AHU slab Cut Out- 3-4 nos and brick work plaster & incasing | 3 | 2016-08-20 | 2016-08-23
Removal of microlab equipments | 1 | 2016-08-20 | 2016-08-21
Miscellaneous work like brick work, slab, plaster needed to reduce door height | 7 | 2016-08-20 | 2016-08-27
AHU of Micro Lab as per Classification class "C" or ISO -7,Particles Count 10,000/CFt of 0.5MIC, Temp. Not more than 25°C, RH 45-50. Modification of existing AHU duct as per requirement | 8 | 2016-08-23 | 2016-08-31 |  |  | Critical- To be finished by today
Change control and validation of AHU
PU flooring in Microlab | 7 | 2016-08-26 | 2016-09-02
Equipment placement | 0 | 2016-09-03 | 2016-09-03 |  |  | OEM support on the day
GMP partition for Microlab | 1 | 2016-09-03 | 2016-09-04
False ceiling of New lab | 2 | 2016-09-04 | 2016-09-06 |  |  | Critical- To be finished by today
Painting of Microlab | 3 | 2016-09-04 | 2016-09-07 |  |  | Critical- To be finished by today
Validation of microlab & equipments | 3 | 2016-09-08 | 2016-09-11 |  |  | This activtiy need to be completed in 3 days max
AHU shed for Lab | 10 | 2016-07-21 | 2016-07-31
Mechanical Activities
Side grip conveyor for check weigher- H1 line | 5 | 2016-09-04 | 2016-09-09 |  |  | Installtion done, commissioning planned during plant run
Perfume pump area improved infrastructure by modification (SS supports for pump) | 5 | 2016-08-20 | 2016-08-25
GMP staircase in manufacturing area | 6 | 2016-09-02 | 2016-09-08 |  |  | Critical- To be finished by tomorrow
Material lift work | 14 days | 2016-07-22 | 2016-08-11
Change control and validation of Material lift (If required)
Electrical Activities
Modification/capacity Enhancement of existing dust collector with additional dust extraction points in silo area and replacement of Non-Woven Needle felt Polyester filters with Pleated filters with return hood along with HDEP filters | 10 | 2016-08-15 | 2016-08-25
Change control and validation of Dust collection system
Air Curtains-3 Phase and Single Phase (Sterilizer RM netry shutter, Opposite old ETP RM stores) | 7 | 2016-08-08 | 2016-08-15
Covering of all Electrical cable trays in Nauta, Silo, Filling and Sterilizer (All areas) | 7 | 2016-08-08 | 2016-08-15 |  |  | Critical- To be finished by today
Dressing of all the cabling in all areas | 5 | 2016-08-15 | 2016-08-20 |  |  | U/P
Exhaust fan in Packing area | 5 | 2016-08-15 | 2016-08-20
Micro Lab Electrical work Supply & Installation | 8 | 2016-08-23 | 2016-08-31
Micro Lab Bio safety cabinet with validation Protocol | 10 | 2016-08-31 | 2016-09-10
Micro Lab Vertical Autoclave with validation Protocol | 8 | 2016-08-31 | 2016-09-08
Instrumentation Activities
Perfume dosing system automation items required Mass flow meter, PLC, HMI, View panel, control panel, Dot matrix printer, power supply, connectivity cable etc | 10 | 2016-08-08 | 2016-08-18
Change control and validation of Perfume dosing system
Fixing up of level switches and VFD's in the filling machines | 10 | 2016-08-19 | 2016-08-29
Change control and validation of Level switches + VFD's
Dressing of all the cabling, pneumatics in all areas | 5 | 2016-08-15 | 2016-08-20
Insulation of Sterlizer-1 | 5 | 2016-09-05 | 2016-09-10
Dressing of all the cabling, pneumatics in Sterilizer-1 | 5 | 2016-09-05 | 2016-09-10
Preparations for Production startup- | 3
C&S | 1 | 2016-09-08 | 2016-09-08 |  |  | Sectional inspection
Swabbing | 1 | 2016-09-09 | 2016-09-09 |  |  | 7:00 | 10:00
Fumigation | 1 | 2016-09-09 | 2016-09-09 |  |  | 11:00 | 15:00
Environment monitoring | 1 | 2016-09-09 | 2016-09-09 |  |  | 15:00 | 17:00
Environment monitoring analysis | 1 | 2016-09-09 | 2016-09-09 |  |  | 17:00
Clearance for production | 3 | 2016-09-12
Startup | 1 | 2016-09-13
300000
Formulas:
Finish = [Start]+26
Finish = [Start]+5+7
Start = [Start, row above]-10
Start = [Start, row above]