## Concept note
| Concept Note of VVF Sewree Pipeline & bitumen facility |  | 26.05.2016
| Process plants | Capacity | Remarks
1 | Cross-country pipeline from Hey Bunder Jetty to VVF Sewree tanks | Initially only one line will be layed for Bitumen transfer & costing is for one line. However, 3 lines are considered for civil design. One 200 NB CS line for Bitumen transfer, One 200 NB CS line for transfer of Oil or lubricants & one 150 NB SS304 line for special fluid transfer application. | All 3 lines will be overhead installed at 7M elevation. Whereever there is road crossing, pipes will be underground. As per the fundamentals of Piping Engineering, for transfer of hot oil (in this case Bitumen at 150 oC), expansion loop is considered to take care of stress due to thermal expansion and at the same time, stress induced failure of piping is avoided. Bitumn pipe will be heated using 14barg steam tracing & insulation.
2 | Existing tanks to be converted to Bitumen storage tanks | Initially only one Tank No 7 will be used for Bitumen Storage and costing is for the same.Tank No 7-(Dia=10.6M, H=16.4M, Cap=1371KL), No agitator, With insulation, CS with SS cladding; However, phasewise all below tanks will also be converted for Bitumen storage. Tank No 6-(Dia=11M, H=29.7M, Cap=2811KL), No agitator, No insulation, Full SS tank Tank No 69-(Dia=9.99M, H=34.13M, Cap=2685.6KL), With agitator, No insulation, CS with SS cladding Tank No 12-(Dia=4.88M, H=29.95M, Cap=563.4KL), No agitator, No insulation, Full MS tank Tank No 13-(Dia=4.88M, H=29.95M, Cap=563.4KL), No agitator, No insulation, Full MS tank | Tank No 7 is initially converted for Bitumen storage. Circulation pump and MP Steam Exchanger will be provided for maintaining temperature in tank & while loading into tanker. Each tank will be provided with radar LT, Temp gauge & transmitter, insulation (if required) and new vent system.
| Utilities | Capacity | Remarks
3 | Power | DG requirment | Existing
4 | Thermic fluid heater | 1 Million kcal/h | From Baddi, will be installed in future. However this is not considered in this costing.
5 | N2 Plant | 20 NM3/h | Existing
6 | Air compressor | 200 CFM | Existing to be used
7 | Fire Protection System | for fire hazard | Existing to be added as required
8 | Tank Dyke wall | for spill containment | New
9 | Tanker loading system with pumps | Capacity to be defined | New
Special points to be noted
1 | 500M length is considered from Jetty to VVF premices and pipe will be overhead. Bitumen pipe will be 14barg steam traced.
2 | Whereever there is road crossing, pipe will be undrground in trench
3 | All tanks should be with new vent system
4 | All bitumen lines flushing from Jetty to storage tank is VVF responsibility. Pigging may be done as required.
5 | Since bitumen pipe lines cleaning is difficult, once bitumen is passed through these lines, the same lines use for another oil like fatty acid/alcohol/palm oil is not possible.
6 | Storage tank cleaning can be done with solvent and tank can be used for storing another product if required in future.

## Summary
FINAL COSTING SHEET: VVF Sewree Pipeline & Bitumen Facility |  |  | 26.05.2016 | R-0
Sr. No. | Facility | Cost, Lacs | Basis | Remarks
1 | Civil work (supply+service) | 164.2423 | Civil costing sheet attached
2 | New Equipment cost | 22 | Mechanical costing sheet attached
3 | Mechanical material | 45.8249 | Mechanical costing sheet attached
4 | Mechanical services | 59.132 | Mechanical costing sheet attached
5 | Insulation (supply+services) | 18.882 | Mechanical costing sheet attached
6 | Instrumentation (supply+service) | 7.265 | Costing sheet attached
7 | Electricals (supply+service) | 3 | appx.
8 | Total | 320.3462
9 | Contingency@5% | 16.0173
10 | Taxes | 67.2727
11 | Total budgetary Cost | 403.6362

## Equipment
Equipment cost for bitumin tanks
Sr.no. | Description | Moc | size (NB) | Quantity | Unit | Rate | Amount | Service | Remark
1 | Heat exchanger | CS |  | 1 | NOS | 700000 | 700000 | MPS/Thermic fluid
2 | Agitator | SS 304 | 500 | 0 | NOS | 350000 | 0 | Bitumen | Flame froof motors
3 | Gear/Lobe pump for tank circulation | CS |  | 1 | NOS | 1500000 | 1500000 | Bitumen | Flame froof motors
4 | Heat exchanger for Tanker loading | CS |  | 0 | NOS | 400000 | 0 | Bitumen
5 | Gear/Lobe pump for tanker loading | CS |  | 0 | NOS | 300000 | 0 |  | Flame froof motors
[5 empty] | Total |  | 2200000
[5 empty] | Tax@25% |  | 550000
[5 empty] | Total Amount |  | 2750000

## Material
25.05.2016
Material cost of new 1 nos Above ground cross country line fabrication and erection at sewree
Sr.no. | Material discreption | Moc | size (NB) | Quantity | Unit | Rate | Amount | Remark
New 1 nos lines (200 NB CS LINE/50 NB CS STEAM LINE)
1 | Pipe | A106,smls,sch.40,BE | 200 | 680 | mtrs | 2700 | 1836000 | 200 NB- 1 nos line (With 30 nos expansion loops)
2 | Pipe | A106,smls,sch.80,BE, IBR | 15 | 2850 | mtrs | 345.6 | 984960 | 200 NB 1 nos line (steam tracing)
3 | Pipe | A106,smls,sch.40,BE, IBR | 25 | 100 | mtrs | 654 | 65400
4 | Pipe | A106,smls,sch.40,BE, IBR | 50 | 680 | mtrs | 702 | 477360
5 | Elbow 90 d. | A106,smls,sch.40,BE | 200 | 78 | nos | 1900 | 148200
6 | Elbow 90 d. | CS,sw,3000#,IBR | 15 | 400 | nos | 120 | 48000
7 | Elbow 90 d. | CS,sw,3000#,IBR | 25 | 50 | nos | 65 | 3250
8 | Elbow 90 d. | CS,sch.40,smls,IBR | 50 | 80 | nos | 425 | 34000
9 | Equal tee | CS,sw,3000#,IBR | 15 | 100 | nos | 120 | 12000
10 | Half coupling | CS,sw,3000#,IBR | 15 | 50 | nos | 120 | 6000
11 | Half coupling | CS,sw,3000#,IBR | 25 | 30 | nos | 140 | 4200
12 | End cap | CS,sw,3000#,IBR | 25 | 30 | nos | 140 | 4200
13 | Flange | A105,sorf,150# | 200 | 12 | nos | 1200 | 14400
14 | Flange | A105,blrf,150# | 200 | 1 | nos | 1200 | 1200
15 | Flange | A105,sorf,300#,IBR | 15 | 120 | nos | 120 | 14400
16 | Flange | A105,sorf,300#,IBR | 50 | 10 | nos | 1122 | 11220
17 | Flange | A105,blrf,300#,IBR | 50 | 1 | nos | 1300 | 1300
18 | Valve | Gate,CS,150#,F/E | 200 | 2 | nos | 26000 | 52000
| Valve | Motor operated | 200 | 2 | nos | 130000 | 260000
19 | Valve | Gate,A105,sw,800#,IBR | 15 | 80 | nos | 2128 | 170240
20 | Valve | Gate,300 #,CS,F/E | 50 | 4 | nos | 9900 | 39600
21 | NRV | CS,150 #,F/E | 200 | 1 | nos | 26000 | 26000
22 | Steam trap | CS,A105 IBR | 15 | 40 | nos | 1450 | 58000
23 | Gasket | CAF 120 | 200 | 15 | nos | 140 | 2100
24 | Gasket | CAF 120 | 15 | 100 | nos | 20 | 2000
25 |  |  | 50 | 15 | nos | 40 | 600
26 | Fastner |  | 3/4 x 110 mm | 120 | nos | 50 | 6000
27 | Fastner |  | 1/2 x 65 mm | 200 | nos | 15 | 3000
28 |  |  | 5/8 x 90 mm | 40 | nos | 19 | 760
29 | Other system piping | [5 empty] | 183600 | 10% of pipe cost
30 | Structral support |  | ISMB 250 | 2000 | kgs | 45 | 90000
31 |  |  | ISA 75 x 75 x 8 mm | 500 | kgs | 45 | 22500
[5 empty] | Total |  | 4582490
[5 empty] | Tax@25% |  | 1145622.5
[5 empty] | Total amount |  | 5728112.5

## Services
25.05.2016
Piping fabrication and erection cost of 1 nos above ground line
Sr.no. | Services | Quantity | Unit | Rate | Amount
IBR services
1 | Fab and erection of cs piping | 3360 | INM | 550 | 1848000
2 | Radiography | 1 | AU | 40000 | 40000
3 | Charges for fitting and welding | 700 | IND | 550 | 385000
4 | Preliminary drawing approval | 1 | AU | 40000 | 40000
5 | Support fabrication and ere charges | 1 | AU | 40000 | 40000
6 | IBR approval charges | 1 | AU | 40000 | 40000
7 | As-built approval charges | 1 | AU | 40000 | 40000
8 | Valve erection charges | 1 | AU | 25000 | 25000
9 | IBR inspector site visit charges | 1 | AU | 20000 | 20000
NON IBR services
1 | Fab and erection of cs piping | 5500 | INM | 160 | 880000
2 | modification of cs piping | 100 | IND | 378 | 37800
5 | Fabrication and fixing of cs shoe support | 650 | IND | 126 | 81900
6 | Radiography | 1200 | IND | 341.25 | 409500
7 | D . P. Test | 1000 | IND | 31.5 | 31500
8 | Valve Fixing | 200 | IND | 126 | 25200
9 | Fabrication and erection of M.S. pipe support | 2.5 | MT | 14700 | 36750
10 | Material Unloading -Hydra | 40 | MT | 787.5 | 31500
11 | Material unloading-manual | 2 | MT | 525 | 1050
12 | Engineering | 1 | AU | 1750000 | 1750000
13 | TPI material inspection | 1 | AU | 150000 | 150000
|  |  | Total |  | 5913200
|  |  | Tax@14.5% |  | 857414
|  |  | Total amount |  | 6770614
Insulation
Sr.no. | Description | Quantity | Unit | Rate | Amount | Remark
Material and application (Perlite)
1 | 200 nb cs line (90 mm thk.) | 680 | RMT | 1800 | 1224000 | 1 nos line insulation
2 | 50 nb cs line (50 mm thk.) with cladding | 680 | RMT | 940 | 639200
3 | Debris removal | 5 | NOS | 5000 | 25000
|  |  | Total |  | 1888200
|  |  | Tax@14.5% |  | 273789
|  |  | Total amount |  | 2161989

## civil estimate
4324231.73
Civil cost summary
Sr. No. | Subject | AGPL Cost
1 | Civil cost - Pipeline Installation | 12000000
2 | Civil cost - Tank Dyke Wall | 4324231.73
3 | Civil cost - foundations for 1 Pump | 100000
Total |  | 16424231.73

## inst
Instrumentation costing for Bitumen Storage facilty-T07 tank
Sr no | Type of Instrument | Description | AI AO | Qty | Unit Cost | Cost | Remark
1 | Control valve | Tank Steam Heating HE101/102 WCB body IBR 2" line size | AO | 1 | 80000 | 80000 | IBR control valve (HE inside tank)
3 | Radar Level Transmitter | Flameproof protection radar LT 4 wire | AI | 1 | 160000 | 160000 | 230 Vac supply considered /tank Ht.17 mtr
4 | Temp TX (With RTD &TW) | for T-7/ across HE | AI | 3 | 12000 | 36000
5 | PRS control valve | 18 Bar to 12 bar steam Cage guided valve 2" line | L | 1 | 100000 | 100000 | IBR control valve
7 | Pressure gauge | Across HE / PRS/ tank Pump outlet | L | 5 | 3500 | 17500
8 | Temp gauge | Across HE / PRS/ tank Pump outlet |  | 4 | 7500 | 30000 | Gas filled type temp gauges considered
10 | Cable/jb | 3 core cable/ 1 pair cable |  | 400 | 70 | 28000 | Power JB for Future 3 tanks
11 | cable tray & structure steel |  |  | 1 | 25000 | 25000 | Local indicators installation at site
12 | Controllers & Indictors | Flameproof protection field mounted |  | 6 | 15000 | 90000
13 | Fitting material & Cu tube |  |  | 1 | 25000 | 25000
14 | cable gland/JB |  |  | 1 | 15000 | 15000
15 | Misc. |  |  | 1 | 20000 | 20000
16 | Service cost |  |  | 1 | 100000 | 100000
[5 empty] | Total | 726500 | In Words: Seven Lacs twenty six thousand five hundred only.
Note
1. No Instrumentation for condensate system.
2. No Instrumentation considered for Steam coil inside tank
3. No UPS supply is considered for controllers, as it is not available in existing setup of Sewree.
4. Local controllers used for Level indication and control valve operation.( i.e. Past history/ Trends will not be available.