## Sheet1 (hidden)
Sr No | Date | Originating Dept. | MOC No. | Subject | Status | MOC co-ordinator | Technical services co ordinator | Benefit observation and MOC closure status
2012-2013
1 | 2012-04-02 | Instrument | I/U/1/12-13 | To implement the automation in fire water system. To change the main pump start set point, provide DCS trends, auto level control for fire water tank,audible alarm for pump start/stop. |  |  | surya | completed
|  | (Utility) |  |  | Completed
2 | 2012-04-03 | Operation | O/DFA/2/12-13 | To preheat the SPD distillate which enters C-502, thus increasing the feed temperature thus increasing the reflux and recovery at same reflux ratio and same reboiler load. | Preheater installed. Control Loop balance
|  | (SPD & S-5) |  |  |  |  | govind
3 | 2012-05-14 | Instrument | I/SPL/3/12-13 | Pump indication & operation should be from DCS instead of field thus decreasing the time delay in startup/shutdown. | Completed |  | varsha | completed
(CGS)
4 | 2012-11-29 | Electrical | E/U/4/12-13 | In FAP, cooling tower operates with 2 fans. Fan ON/OFF control temperature settings to be changed. This will save power in winter season and low load conditions.
|  | (FAP Utility) |  |  | Completed |  | surya
5 | 2012-11-29 | Electrical | E/FAP/5/12-13 | Motors of 01G14 A/B pumps run on very high current. This causes very high vibrations on site of the pumps. One motor should be changed to higher rating and foundation should be strengthened mechanical and also with civil material.
|  | (FAP stripper) |  |  | completed |  | snehil | completed
2013-2014
6 | 2013-03-25 | Utility | M/U/1/13-14 | To replace the pump at effluent pit of DM plant with the existing pump of Glycerin plant. Old pump is under maintenance for long period. It is beyond repairable | Open | Mr.Vijay Patil | surya
(Old Boiler)
7 | 2013-04-18 | Operation | O/DFA/2/13-14 | To utilize the C-303 generated steam in other areas instead venting it to maintain pressure which goes to precon. To carry out this, existing vent line should be diverted to DFA LP steam header and can be used in tankfarm tracing also. |  |  | govind
|  | (Section -3) |  |  | Completed
8 | 2013-04-23 | Mechanical | M/SPL/3/13-14 | To give individual NRVs to the pumps P-106 A & B in both the discharge line instead of single NRV in the common discharge line to prevent any damage to the pumps | Open |  | varsha
|  | (Splitting) |  |  | PO Placed.
9 | 2013-04-20 | Mechanical | M/DFA/4/13-14 | To povide nylon net around the C-303 Direct cooling tower upto 5ft height to eliminate drift losses. Also to provide extra manual valves above all on-off valves to control flow and maintain hot well level | Nylon net provided. Manual valve yet to install |  | govind
(DFA)
10 | 2013-04-23 | Operation | O/DFA/5/13-14 | To disconnect existing overflow line of C-303 direct cooling tower line and connect the overflow line to common drain line of Jutasama building. | Open |  | govind
(Section-3)
11 | 2013-05-25 | Instrument | I/SPL/6/13-14 | To relocate lurgi splitting tower interface level chamber and its isolation valve for easy operation,maintenance and online calibration during running plant | Open |  | varsha
(Splitting)
12 | 2013-08-02 | Tankfarm | M/TF/7/13-14 | To provide stand by pump for tanker loading to minimize demurrage and detention of vehicle and modification of discharge line of P-830 A/B | Open | Mr Ramchandra Jadhav | varsha
(Mechanical)
13 | 2013-08-01 | Tankfarm | M/TF/8/13-14 | To provide circulation line to T-807 which is used for blending of DFA C8-C10 | Open | Mr Ramchandra Jadhav | varsha
(Mechanical)
14 | 2013-07-10 | Tankfarm | M/TF/9/13-14 | To provide MP steam line to tanks in tankfarm 5 | Open | Mr Ramchandra Jadhav | varsha
(Mechanical)
15 | 2013-07-10 | Tankfarm | M/TF/10/13-14 | Relocating loading point in front of loading bay | open | Mr Ramchandra Jadhav | varsha
(Mechanical)
16 | 2013-06-27 | Utility | M/U/11/13-14 | Hot water from VAM outlet to be bypassed to generator coils by installing 3 way control valve at inlet of PHE | open | Mr Vijay Patil | surya
|  | (Mechanical) |  | Installing 2-way control valve /ON-OFF valve to allow cooling water bypass VAM
17 | 2013-08-28 | Operation | M/DFA/12/13-14 | Relocating alfalaval MP steam line from common header to its steam | open | Mr.Dinesh Danav | govind
|  | (Mechanical) |  | inlet line so to avoid uses of MP steam to tracing
18 | 2013-09-02 | Utility | I/U/13/13-14 | Installing NG saving system on TP-45C | open | Mr.Sachin Lohar | surya
(TP-45C)
19 | 2013-09-05 | Operation | M/DFA/14/13-14 | Relocating section -5 MP steam header from 3rd to 6th floor | open | Mr.Dinesh Danav | govind
(Mechanical)
20 | 2013-09-05 | Operation | M/DFA/15/13-14 | Installation of spiral heat exchanger in C-402 res. Line | open | Mr.Dinesh Danav | govind
(Mechanical)

## Sheet2 (hidden)
Under Implementation after approval
Forwarded for approval
Under Progress
Completed
MOC Status as on: |  |  | 21.10.13
Sr No | Date | Originating Dept. | MOC No. | Subject | Status | MOC co-ordinator | Technical services co ordinator | estimated cost RS (Lac)
2013-2014 | [7 empty] | -
6 | 2013-03-25 | Utility (Old Boiler) | M/U/1/13-14 | To replace the pump at effluent pit of DM plant with the existing pump of Glycerin plant. Old pump is under maintenance for long period. It is beyond repairable | Pump Ready. To be installed. This pump used at other place. Other pump being ready. Spares indented. | Mr.Vijay Patil | surya | -
10 | 2013-04-23 | Operation (Section 3) | O/DFA/5/13-14 | To disconnect existing overflow line of C-303 direct cooling tower line and connect the overflow line to common drain line of Jutasama building. | Forwarded for approval 1.11.13 |  | surya | 0.63
12 | 2013-08-02 | Tankfarm (Mechanical) | M/TF/7/13-14 | To provide stand by pump for tanker loading to minimize demurrage and detention of vehicle and modification of discharge line of P-830 A/B | Forwarded for approval on 19.9.13. Approved. Given for implementation on 14.10.13 | Mr Ramchandra Jadhav | varsha | 8.5
13 | 2013-08-01 | Tankfarm (Mechanical) | M/TF/8/13-14 | To provide circulation line to T-807 which is used for blending of DFA C8-C10 | Approved. Given to Mech on 16.9.13 | Mr Ramchandra Jadhav | varsha | 3.3
14 | 2013-07-10 | Tankfarm (Mechanical) | M/TF/9/13-14 | To provide MP steam line to tanks in tankfarm 5 | Forwarded for approval 1.11.13 | Mr Ramchandra Jadhav | varsha | 9.03
15 | 2013-07-10 | Tankfarm (Mechanical) | M/TF/10/13-14 | Relocating loading point in front of loading bay | Forwarded for approval on 19.9.13. Approved. Given for implementation on 14.10.13 | Mr Ramchandra Jadhav | varsha | 0.92
17 | 2013-08-28 | Operation (Mechanical) | M/DFA/12/13-14 | Relocating alfalaval MP steam line from common header to its steam inlet line so to avoid uses of MP Steam to tracing | Forwarded fpr approval on 1.10.13. Approved on 1.10.13. Given to implement to Mech Dept on 2.10.13 | Mr.Dinesh Danav | surya | 0.7
18 | 2013-09-02 | Utility (TP 45C) | I/U/13/13-14 | Installing NG saving system on TP-45C | Forwarded for approval on 19.9.13. Temp installed on 16.9. Benefit to establish. Approved for trial. Acceptance of Unit after saving validation by PKD & Mr Sanghvi. | Mr.Sachin Lohar | surya | 88
19 | 2013-09-05 | Operation (Mechanical) | M/DFA/14/13-14 | Relocating section -5 MP steam header from 3rd to 6th floor | Forwarded fpr approval on 1.10.13. Approved on 1.10.13. Given to implement to Mech Dept on 2.10.13 | Mr.Dinesh Danav | surya | 0.82
25 |  |  | M/FA/21/13-14 | Hydrogen recovery from Alcohol plant | Forwarded for approval on 19.9.13. Back with comment. Forwarded for approval on 28.9.13. Forwarded to CFO on 15.10.13 | Mr.Rajendra Jain | Snehil | 58 | Capex
26 | 27.9.13 |  | M/FA/22/13-14 | To run Sec 3 & Sec 4 in series | Acapex forwarded on 21.10.13 | Mr.Rajendra Jain | snehil |  | Capex
27 |  |  | M/HYD/23/13-14 | 10% capacity increase in H2 Generation | Chilled water line to HX104 MOC forwarded on 1.10.13. Back with comment. Forwarded on 7.10.13. Approved. Given to Mech on 9.10.13. chilled water tapping taken. To be connected by hoze | Mr G Birkodi |  | 0.15
|  |  |  | Consultant charges for Improvements |  |  |  | 3 | Rough Est
|  |  |  | Conversion of Drawings in soft copy |  |  |  | 1 | Rough Est

## MOC status
MOC Status as on: |  |  |  | Under study
Under approval/ Under Hold
under implementation
B&C Pending
Closed/ Cancelled
Capex-under progress
Sr No | Date | Originating Dept. | MOC No. | Subject | Work Status | Coordinator | Document location | Remark
2016-2017
66 | 2016-04-02 | Flaker | M/DFA/1/16-17 | Chilled water to flaker | Completed | Lakhan
67 | 2016-06-04 | GDP | M/GDP/2/16-17 | Thermic fluid FT and TT relocation | Under implementaion | Amey
68 | 2016-06-08 | FAP | M/FAP/03/16-17 | 03D3 calandria feed from pump discharge | Completed | Amey
69 | 2016-07-14 | GDP | M/GDP/4/16-17 | Alfa laval- GDP cooling tower inter connection | Completed | Amey
70 | 2016-07-14 | Utility | M/U/5/16-17 | Side stream filter to CPP cooling tower | Under implementaion | Amey
71 | 2016-07-15 | Utility | M/U/6/16-17 | N2 plant from sion to taloja | Under implementaion | Lakhan |  | Space not available, as per discussion Mr. P.Kale will initiate papers to transfer N2 plant to talaja, letter MOC will be discussed again
72 |  | FAP | M/FAP/7/16-17 | Fatty alcohol mixing tank | Under implementaion | Amey |  | Civil work completed & mechanical work is in progress
73 | 2016-09-10 | DFA | M/DFA/'8/16-17 | Flaker metal detector | Cancelled | Lakhan |  | Due to urgency budget is apporved directly hence MOC requirement is over
74 | 2016-09-15 | Utility | M/U/9/16-17 | DM water line extension to Coal heater WHRU | Completed | Lakhan
75 | 2016-10-07 | Hydrogen | M/Hyd/10/16-17 | Chemical dosing provision to H2 compressor | Under approval | Lakhan
76 | 2016-11-12 | Utility | M/U/11/16-17 | Hot air to CHP | Under implementaion | Lakhan
77 | 2016-11-26 | Utility | M/U/12/16-17 | GT lube oil pump | Completed | Amey
78 |  | GDP | M/GDP/13/16-17 | GDP chiller for syndate | Completed | Lakhan
79 | 2017-02-07 | CGS | M/CGS/14/16-17 | Settling tank for skimming | Completed | Amey