## Sheet1
Project management- OTIFQ within budget
100%, Have ensured the projects are completed in given timeframe and budget, and spliting tower insulation remmoving and re fixing with in timmely,and Dfa spliting shutdown LIC -8 new control valve and pipe line fabrcation&erection works started at 01.05.2016 with timely completed and handed over at dated 05.05.2016,and Dfa HYD plant supper flex vegacid project timely completed with trail and handed over with any issues, and Noodle plant caustic day tank removed with pipe line dismantling and re erection tank with modified of the pipe line timely completed & handed over dated 14.09.2016 due to floor and foundation damaged after trail resolving issues, and caustic tank farm to dfa tankfarm caustic transfer pipe line fixing activities completed after trail & handed over dated at 14.10.2016 these plan of the purpose cautic storage in tank no-8008, and Durty cooling tower,stretcher, pipe fabrication erction &commissioning timely completed dated at 12.12.2016 with out any issuese
Note on A3: Murali Pillai: These mentiond all project management related all activities completed with under allotted R& M budjet for the anual