## Sheet1
Sr.No. | Name of Project | Customer | Last months status | Current Month status | Target date | Project Timeline
1 | Thiamethoxam 14.10+ Lambda cyhalothrin 10.6 SC | Insecticides India Ltd | Ratio screening for Lambda EC is ongoing. | Emulsion concentration of Lambda cyhalothrin is prepared by using combination of castor oil ethoxylate+LA 7EO+Calcium dodecyl benzene sulphonate.SC formulation of Thiamethoxam is prepared,Physicochemical properties are ongoing by mixing EC of Lambda and SC of Thiamethoxam. | 30th June | 6 months
2 | Lambda cyhalothrin 5% and 10% CS | Insecticides India Ltd and Generic customers | Reactions to develop CS formulation is ongoing | Globule formulation is observed in cs formulation.Reactions are ongoing to avoid globule formation by process modification and using proper emulsifiers and dispersant . | 30th June | 6 months
3 | Hexaconazole 5% EC | Indofil Ltd | Received blank samples from Indofil.Will start the project after getting crude oil ethoxylates from Esteem. | Recipe development is ongoing using crude oil ethoxylates C12-14. and CABS.Initial results are encouraging. | 30th June | 3 months
4 | Propiconazole 25% EC |  |  | Recipe development is ongoing with LA 10EO(Crude oil C12-14) and CABS and getting good stable emulsion.Further screening is ongoing to get desired properties. | 30th May | 3 months
5 | Dichorovas 76% EC | Saberao/Coromondal International | Project will start at Taloja lab after getting required crude oil ethoxyaltes also will initiate with existing LA ethoxylates and CABS after getting required solvents. | Waiting for solvent C9.PO raised. | 30th June | 3 months
6 | Glyphosate 41% SL | Saberao/Coromondal International | Waiting for APG standard sample from customer according to which we will develop blend of APG and then will start work on Glyphosate SL formulation | Received standard(Benchmark)sample from customer(Agnique BL 7055 from BASF).Analysis of received sample is ongoing.Reverse enginerring is ongoing to find out percentage of APG and diluents used to make standard sample. | 30th June | 3 months
Pipeline Projects
1 | Chlorpyriphos 20% EC | Chemminova | Project will start after getting actives (marketing team to arrange technicals)
2 | Pendimethalin 30% EC | Chemminova
3 | Dimethoate 30%EC | Chemminova
4 | Quinalphos 25% EC | Chemminova