## Shutdown motor
FATTY ALCOHOL PLANT MOTOR LIST
PREVENTIVE MAINTEANCE PLAN 2016-17 FOR ALL PLANT MOTORS DURING SHUTDOWN
Sr. No. | Description | Tag. No. | KW | 2016-04-11 | 2016-05-11 | 2016-06-11 | 2016-07-11 | 2016-08-11 | 2016-09-11 | 2016-10-11 | 2016-11-11 | 2016-12-11 | 2017-01-11 | 2017-02-11 | 2017-03-11
1 | Liquid wing vaccum pump | 01G12A | 11 | 2016-05-11: 14.05 | 1
2 | Liquid wing vaccum pump | 01G12B | 11 | 2016-04-11: 4.04 | 1
3 | Reactor drain out pump | 01G13A | 15 | 2016-05-11: 14.05 | 1
4 | Reactor drain out pump | 01G13B | 15 | 2016-05-11: 14.05 | 1
5 | Circulation Pump | 01G19A | 15 | 2016-04-11: 4.04 | 1
6 | Circulation Pump | 01G19B | 15 | 2016-04-11: 4.04 | 1
7 | H2 Compressor | 02G1 | 435 | 2016-04-11: 4.04 | 1
8 | Make up comressor-2 | 02G1A | 475 | 2016-04-11: 4.04 | 1
9 | Fan Motor | 02G1A-MG2 | 3 | 2016-04-11: 4.04 | 1
10 | Aux.lub oil pump | 02G1AG1 | 2.2 | 2016-04-11: 4.04 | 1
11 | Aux.lub oil pump | 02G1AG2 | 2.2 | 2016-04-11: 4.04 | 1
12 | Lubricator | 02G1AG3 | 1.1 | 2016-04-11: 4.04 | 1
13 | H2 Compressor main lub oil pump | 02G1G1 | 1.5 | 2016-04-11: 4.04 | 1
14 | H2 Compressor Aux.lub oil pump | 02G1G2 | 1.5 | 2016-04-11: 4.04 | 1
15 | H2 Compressor lubricator | 02G1G3 | 0.25 | 2016-04-11: 4.04 | 1
16 | Recycle Compressor | 02G3 | 330 | 2016-04-11: 4.04 | 1
17 | Recycle Comp. main lub oil pump | 02G3G1 | 1.1 | 2016-04-11: 4.04 | 1
18 | Recycle Comp. Aux. lub oil pump | 02G3G2 | 1.1 | 2016-04-11: 4.04 | 1
19 | Recycle Compressor lubricator | 02G3G3 | 0.25 | 2016-04-11: 4.04 | 1
20 | HP wax ester feed pump | 02G5A | 250 | 2016-05-11: 16.05 | 1
21 | HP wax sealing pump motor | 02G5AG1 | 0.75 | 2016-04-11: 4.04 | 1
22 | HP wax ester feed pump | 02G5B | 250 | 2016-05-11: 16.05 | 1
23 | HP wax sealing pump motor | 02G5BG1 | 0.75 | 2016-04-11: 4.04 | 1
24 | HP wax ester feed pump | 02G5C | 250 | 2016-05-11: 16.05 | 1
25 | HP wax sealing pump motor | 02G5CG1 | 0.75 | 2016-04-11: 4.04 | 1
26 | WR Vaccum pump | 03G16A | 11 | 2016-05-11: 16.05 | 1
27 | Pump for Distillate | 03G2A | 37 | 2016-04-11: 4.04 | 1
28 | Pump for Distillate | 03G2B | 37 | 2016-04-11: 4.04 | 1
29 | Product pump | 04G5A | 7.5 | 2016-04-11: 4.04 | 1
30 | Product pump | 04G5B | 7.5 | 2016-04-11: 4.04 | 1
31 | Terpered cooling water pump | 05G10A | 90 | 2016-04-11: 6.04 | 1
32 | Terpered cooling water pump | 05G10B | 90 | 2016-04-11: 6.04 | 1
33 | DM water pump | 05G3A | 4 | 2016-04-11: 5.04 | 1
34 | DM water pump | 05G3B | 4 | 2016-04-11: 5.04 | 1
35 | Cooling water pump | 05G9D | 30 | 2016-04-11: 5.04 | 1
36 |  | 05G9C | 160 | 2016-04-11: 5.04 | 1
37 | Cooling water pump | 05G9E | 30 | 2016-04-11: 5.04 | 1
38 |  | 05G9F | 30 | 2016-05-11: 16.05 | 1
39 | Deassor water pump | 05U1G3 | 4 | 2016-04-11: 5.04 | 1
40 | C.T.Unit with fans | 05U2G1A | 22 | 2016-04-11: 5.04 | 1
41 | C.T.Unit with fans | 05U2G1B | 22 | 2016-04-11: 5.04 | 1
42 | Froced draft fan bioler 5TPH | 07U1G1A | 18.5 | 2016-06-11: 7.08 | 1
43 | Froced draft fan bioler 3TPH | 07U1G1B | 11 | 2016-06-11: 7.08 | 1
44 | F.D.Fan | 10G01A | 75 | 2016-06-11: 7.08 | 1
45 | F.D.Fan | 10G01B | 75 | 2016-06-11: 7.08 | 1
46 | F.D.Fan | 10G01C | 160 | 2016-06-11: 7.08 | 1
47 | Recycle H2 Compressor | 10G02 | 9.3 | 2016-05-11: 16.05 | 1
48 | BWF pumps | 10G04A | 22 | 2016-05-11: 14.05 | 1
49 | BWF pumps | 10G04B | 22 | 2016-05-11: 14.05 | 1
50 | Recycle compressor | C-103A | 3.7 | 2016-05-11: 14.05 | 1
51 | Recycle compressor | C-103B | 3.7 | 2016-05-11: 14.05 | 1
52 | I.D. Fan | F-101 | 22 | 2016-04-11: 5.04 | 1
53 | F.D. Fan | F-102 | 7.5 | 2016-04-11: 5.04 | 1
54 | BFW Pump | P-101A | 18.5 | 2016-05-11: 16.05 | 1
55 | BFW Pump | P-101B | 18.5 | 2016-05-11: 16.05 | 1
56 | Linde Dosing Pump-1 |  | 2.2 | 2016-05-11: 16.05 | 1
57 | Linde Dosing pump-2 |  | 0.37 | 2016-05-11: 16.05 | 1
58 | Post cooler chain conveyor |  | 5.5 | [12 empty] | 0
59 | Rotoform Ist pastillator |  | 2.2 | [12 empty] | 0
60 | Steel belt conveyor |  | 7.5 | [12 empty] | 0
61 | Metal Detector motor |  | 0.37 | [12 empty] | 0
62 | stiching machine motor pastilator plant' |  | 0.37 | [12 empty] | 0
63 | Belt conveyor past. Ground floor |  | 0.37 | [12 empty] | 0
64 | steel belt conveyor blower |  | 7.5 | [12 empty] | 0
65 | Feed Pump | 14G02A | [13 empty] | 0
0
FATTY ACID PLANT MOTOR LIST | [15 empty] | 0
Sr. No. | Description | Tag. No. | KW | 2016-04-11 | 2016-05-11 | 2016-06-11 | 2016-07-11 | 2016-08-11 | 2016-09-11 | 2016-10-11 | 2016-11-11 | 2016-12-11 | 2017-01-11 | 2017-02-11 | 2017-03-11
1 | Circulation Pump | P-705A | 55 | 2016-09-11: 27.09 | 1
2 | Circulation Pump | P-705B | 55 | 2016-09-11: 27.09 | 1
3 | D.M. Water Pump | P-706B | 3.7 | 2016-09-11: 27.9 | 1
4 | D.M.Water transfer pump | P-908 | 5.5 | 2016-09-11: 27.09 | 1
5 | k3 CT Pump | P-35 | 55 | 2016-09-11: 27.09 | 1
6 | C12/C14 transfer pump | P-809 | 15 | 2016-09-11: 27.09 | 1
0
SAPONIFICATION PLANT MOTOR LIST | [15 empty] | 0
Sr. No. | Description | Tag. No. | KW | 2016-04-11 | 2016-05-11 | 2016-06-11 | 2016-07-11 | 2016-08-11 | 2016-09-11 | 2016-10-11 | 2016-11-11 | 2016-12-11 | 2017-01-11 | 2017-02-11 | 2017-03-11
1 | Cooling water pump-4 | 20P05A | 18.5 | [12 empty] | 0
2 | Hot well pump -2 | P-206.3 | 30 | [12 empty] | 0
3 | New flaker extract pump |  | 7.5 | 2016-04-11: Plant not running
4 | Post Con feed pump | P-168.1A | 1.5 | 2016-04-11: Plant not running
5 | Post Con feed pump | P-168.1B | 5.5 | 2016-04-11: Plant not running
6 | Post Con 1st effect evaporator circulation pump. | P-168.2 | 11 | 2016-04-11: Plant not running
7 | Post Con 2nd effect evaporator circulation pump. | P-168.3 | 11 | 2016-04-11: Plant not running
8 | Condensate pump | P-168.4 | 2.2 | 2016-04-11: Plant not running
9 | Crude Glycerin transfer pump | P-168.5 | 1.5 | 2016-04-11: Plant not running
10 | Vacuum Pump | P-168.7 | 15 | 2016-04-11: Plant not running
11 |  | P-168.11 |  | 2016-04-11: Plant not running
0
CAPTIVE POWER PLANT MOTOR LIST | [15 empty] | 0
Sr. No. | Description | Tag. No. | KW | 2016-04-11 | 2016-05-11 | 2016-06-11 | 2016-07-11 | 2016-08-11 | 2016-09-11 | 2016-10-11 | 2016-11-11 | 2016-12-11 | 2017-01-11 | 2017-02-11 | 2017-03-11
1 | AUX.AIR FAN 2 | P-1001 A | 2.2 | 2016-12-11: 29 | 1
2 | AUX.AIR FAN 2 | P-1001 B | 2.2 | 2016-12-11: 29 | 1
3 | AUX.AIR FAN 1 | P-1002 | 1.5 | 2016-12-11: 29 | 1
4 | SAF FD-01 | P-1009 | 7.5 | 2016-12-11: 29 | 1
5 | STARTUP VENT S24 | P-1014A |  | 2016-12-11: 27 | 1
6 | STEAM SUPPLY S25 | P-1014B |  | 2016-12-11: 28 | 1
7 | CT FAN-1 | P-1016A | 15 | 2016-12-11: 28 | 1
8 | CT FAN-2 | P-1016B | 15 | 2016-12-11: 29 | 1
9 | GULLOTINE DAMPER G5_01 | P-1003 |  | 2016-12-11: 29 | 1
10 | GULLOTINE DAMPER G5_02 | P-1004 |  | 2016-12-11: 28 | 1
11 | GULLOTINE DAMPER G5_03 | P-1005 |  | 2016-12-11: 27 | 1
12 | FAF BLOWER | P-1000 | 110 | 2016-12-11: 28 | 1
GLYCERIN PLANT MOTOR LIST | [15 empty] | 0
Sr. No. | Description | Tag. No. | KW | 2016-04-11 | 2016-05-11 | 2016-06-11 | 2016-07-11 | 2016-08-11 | 2016-09-11 | 2016-10-11 | 2016-11-11 | 2016-12-11 | 2017-01-11 | 2017-02-11 | 2017-03-11
1 | BATCH BLEACHER AGITATOR | AG7106 | 3.7 | 2016-08-11: 26 | 1
2 | ATFD STIRRER | AG7110 | 7.5 | 2016-08-11: 26 | 1
3 | CRUDE RECIRCULATION PUMP | P-7101 | 11 | 2016-08-11: 23 | 1
4 | DEODERIZER DRYER RECIRCULATION PUMP | P-7102 | 2.2 | 2016-08-11: 24 | 1
5 | FEED PUMP | P-7103 | 2.2 | 2016-08-11: 24 | 1
6 | DISTILLATE PUMP | P-7106 | 5.5 | 2016-08-11: 24 | 1
7 | BLEACHER FEED PUMP | P-7107 | 3.7 | 2016-08-11: 24 | 1
8 | SUB STANDARD GLYCERINE TRANSFER PUMP | P-7108 | 2.2 | 2016-08-11: 24 | 1
9 | PITCH PUMP | P-7110 | 3.7 | 2016-08-11: 24 | 1
10 | INTERMEDIATE DISTILLED GLYCERINE X-MER PUMP | P-7111 | 2.2 | 2016-08-11: 23 | 1
11 | FLASH VESSEL-II | P-7112 | 2.2 | 2016-08-11: 23 | 1
12 | X-FER PUMP FROM ATFD RECEIVER | P-7113 | 3.7 | 2016-08-11: 24 | 1
13 | INTERMEDIATE REFINED GLYCERINE X-FER PUMP | P-7117 | 5.5 | 2016-10-11: 2 | 1
14 | FIRST STAGE FLASH PUMP | P-7118 | 3.7 | 2016-08-11: 23 | 1
15 | SECOND STAGE FLASH PUMP | P-7119 | 3.7 | 2016-08-11: 23 | 1
16 | ATFD FEED PUMP | P-7120 | 3.7 | 2016-08-11: 23 | 1
17 | HOT OIL X-FER PUMP FOR E-101 | P-7122 | 7.5 | 2016-08-11: 23 | 1
18 | HOT OIL X-FER PUMP FOR E-102 | P-7123 | 2.2 | 2016-08-11: 23 | 1
19 | HOT OIL FOR ATFD | P-7124 | 2.2 | 2016-08-11: 23 | 1
20 | SCRUBBER DISCHARGE PUMP | P-7125 | 15 | 2016-08-11: 24 | 1
21 | SCRUBBER CIRCULATION PUMP | P-7121 | 3.7 | [12 empty] | 0
22 | WATER CHILLING PLANT-1 | CH7000A | 55 | 2016-08-11: 24 | 1
23 | WATER CHILLING PLANT-2 | CH7000B | 55 | 2016-08-11: 24 | 1
24 | SCRUBBER CIRCULATION PUMP | P-7126A | 3.7 | 2016-08-11: 24 | 1
25 | SCRUBBER CIRCULATION PUMP | P-7126B | 9.3 | 2016-08-11: 24 | 1
26 | Cooling water pump-2 | 20P03B | 110 | 2016-08-11: 24 | 1
|  |  |  | 2016-12-11: Total Done | 100
|  |  |  | 2016-12-11: Planned | 111
|  |  |  | 2016-12-11: Percentage | 90.0901
Note on C76: Author: Motor not in use

## shutdown other work
CPP SHUTDOWN
SR. NO | DATE | JOB DESCRIPTION | JOB DONE BY
1 | 20/11/16 | Prepare a list connected feeders to CPP MCC | PWN
2 | 25/11/16 | G.T turned off. Protection parameter switch set to INACTIVE mode. | RNP/GTC
3 | 26/11/16 | GT shutdown work | RNP/BHP
1. Starting motor connection disconnect
2. Air blower connection disconnect
3. All motor's termination check
4. Cleaning of Alternator
4 | 26/11/16 | CPP blower P-1008 vibration reading taken beacause of high noise. Bearing replaced on 29/11/16 | DLK/BHP
VERTICAL HORIZONTAL
CPP BLOWER DE 3.4A, 1.97 5.0, 5.67D
NDE 5.8D, 7.73D 9.8D, 2.60A
5 | 27/11/16 | GT shutdown work | RNP/BHP
1. Alternator T.B check and clean
2. Starting motor clean and brush connection tightning
3. Oil heater and space heater checking along with connection tightness
4. ESP blower & ESP check and tightning
5. Cleaning of Air blower motor and Filter
6. Rotor excitor cleaning and tightning of connection.
6 | 27/11/16 | Temporary supply given to; | RSG/DLK/RANA
1. UPS-1 FROM CHP 4F3 MCC116
2. PDB FROM CHP 3F5 MCC116
7 | 28/11/16 | CPP PMCC Breaker Feeder 8F2 P.M done. | AVV
8 | 28/11/16 | CPP MCC Incomer-2 Breaker P.M done. | AVV/RNP
9 | 28/11/16 | P-1012 A,B Motor overhauling. 30Kw, ABB make, 2900 rpm, | RSM
Bearing replaced 6211 C3, 6212 C3.
10 | 28/11/16 | CPP MCC Cleaning of all Panels, Busbars tighness | RSG/DLK/TOM/RANA/RNP
11 | 28/11/16 | UPS Battery, Discharge battery, UPS-2 AND 110V Battery bank voltage checked . | RSG/DLK/TOM/RANA/RNP
12 | 28/11/16 | CPP MCC Charged after shutdown work. | RSM/DLK
13 | 29/11/16 | CB 52-1, 2, 3, 4 backside and frontside cleaning, connection tightning | SAL
Battery charger, NGR panel, RTCC panel cleaning
14 | 29/11/16 | P-1017A Motor bearing replaced. Bearing 6307 ZZC3, 6308ZZC3 | RSG
15 | 30/11/16 | P-1012 C Motor overhauling. 30Kw, ABB make, 2900 rpm, | RSM
Bearing replaced 6211 C3, 6212 C3.
16 | 29/11/16 | P-1012 A,B,C No Load(Decouple) trial and vibration readings taken | RSM
VERTICAL HORIZONTAL
P-1012A DE 2.4, 0.98 4.2A, 0.96
NDE 4.1A, 1.01 3.2A, 0.88
P-1012B DE 2.3, 0.41 1.8, 0.46
NDE 1, 0.26 1.2A, 0.30
P-1012C DE 1.4, 0.83 3.3A, 0.57
NDE 3.3A, 0.38 4.1A, 0.43
17 | 29/11/16 | P-1008 1.5Kw ,2830 rpm, CG make Motor Bearing replaced 6205ZZC3, 6205ZZC3 | RSM
18 | 30/11/16 | P-1017B Motor bearing replaced. Bearing 6307 ZZC3, 6308ZZC3 | AVV
19 | 30/11/16 | CPP PDB-1F4 connection given from CHP PMCC | SAL
20 | 30/11/16 | Temporary supply given to New Utility MCC from NEW PMCC BUS C 18R2 Feeder. | RANA/RNP
20 | 30/11/16 | NEW PMCC Bus A all panels cleaning
21 | 30/11/16 | CPP UPS-1, UPS-2 Voltage checked.(Refer sheet no 2 for readings) | AVV/RSK/DLK
22 | 30/11/16 | Following Circuit Breakers P.M Done | SAL/BHP/AVV/CPP/RANA/TOM/RNP
1. 02G1A (FEEDER 8F1)
2. APFC PANEL 1 (FEEDER 1F1)
3. TR-3 INCOMER (FEEDER 2F2)
4. 5th HARMONIC
5. APFC 1
6. TR-3 52-16 electrical spring charging problem.After checking motor shaft gear quarter pin was broken ,so temporary arrangement done by putting S.S pin(needle).Trial taken twice, Breaker found Ok.
23 | 30/11/16 | NEW APFC 1&2 Cleaning with vacuum cleaner. While charging panel 1F1 Breaker did not start, on checking control fuse was blown out, NS 4A control fused changed. Service indication didn't turn on so breaker racked out, again breaker racked in and manually charged the breaker. | DLK/RSG/AVV
24 | 30/11/16 | Installtion of cooling duct for 02G1A VFD panel
25 | 2016-01-12 | P-1017A Bearing replaced 6308ZZC3, 6307 ZZC3 | CPP