## Sheet2
Schedule for Temporary Monsoon at Taloja Year 2017-18
S.No | Activity | Starting Date | Completion Date | Days | Completion Date
1 | Obtaining current year requirements from various users dept. | 04.03.2016 | 15.03.2016 | 12
2 | Finalization shed requirement with plant head. | 16.03.2016 | 21.03.2016 | 6
3 | Submission of letter to MIDC for permission as per our requirement. | 22.03.2016 | 23.03.2016 | 2
4 | Receiving Approval letter from MIDC. | 24.03.2016 | 04.04.2016 | 12 | On request to MIDC
5 | Submission of agreement copy & plot plan drawing with Measurement sheet to MIDC |  | 05.04.2016 | 1
6 | Raise PRF for service purchase order. |  | 01.04.2016 | 1
7 | Release purchase order for services | 01.04.2016 | 11.04.2016 | 10
8 | Receiving deposit & rent demand letter from MIDC. | 18.04.2016 | 21.04.2016 | 4
9 | Demand draft for MIDC Deposit & Rent. | 21.04.2016 | 23.04.2016 | 3
10 | To start receiving material (Bamboo & Tarpaulins) | 16.04.2016 | 18.04.2016 | 3 | Start from 12.04.2017
11 | Start of Monsoon shed Constructions. | 18.04.2016 | 01.06.2016 | 42 | Start from 15.04.2017
12 | MIDC approved period for monsoon shed. | 15.06.2016 | 15.11.2016 | 150
13 | Removing of Sheds | 01.11.2016 | 15.11.2016 | 15 | 10.11.2016
14 | Application of release Deposit amount from MIDC. |  | 15.11.2016 | 1 | 12.11.2017