## 02D25
VVF (INDIA) LIMITED
Date : 07/03/2016
RISK ASSESSMENT
Foundation checking of 02D25
Sr. No. | Activity | Subactivity | Risk | Safety Precautions | Remark
1 | Preparation of work | Isolation of steam lines and condensate lines | If lines are hot, may cause burns. Ensure before work | Isolate steam and condensate lines. Provide temporary heat resistant cloth for tubing.
|  | Surrounding area LEL for H2 to be checked | No risk | Checked for traces of hydrogen present in surrounding area by LEL meter and found 0%
|  | Providing hot permit of the work | No risk | Ensure that all operators have proper knowledge of work and know the risk associated with it
2 | Hammering on foundation by Chisel. | Activity to be followed on given location | Electric spark generation | Avoid metal to metal contact during work | Job should be done under continuous supervision
|  | Carrying out activity | No risk | Provision of fire water hose, fire extinguisher and fire blankets as required | Emergency services should be kept ready
In case of any emergency & abnormality, stop the work in safe manner & inform to the control room
Prepared by: |  |  | Checked By: | Approved by:
| Vikas Jadhav |  | Pradeep Soste | Mr. Rajendra Jain
|  |  | Rajesh Dighe | Mr. Aniruddha Bansod
**Supervision by |  |  | Satish Adake
Fatty Alc. Shift incharge
Civil Engineer
Contract supervisor

## 01E8
VVF (INDIA) LIMITED
Date : 05/01/2016
RISK ASSESSMENT
Shiftng of 01E8 heat exchanger( floor G to location)
Sr. No. | Activity | Subactivity | Risk | Safety Precautions | Remark
1 | Preparation of work | Arrangement of crane | No risk | Barricade the surrounding area and ensure enough space is provided for proper functioning of crane
|  | Providing cold permit of the work | No risk | Ensure that all operators have proper knowledge of work and know the risk associated with it
2 | Lifting of 01E8 | Attachment of SLINGS (LIFTING TOOL S & TACKLES) to heat exchanger | Failure of SLINGS, D- SHACKLES, BELTS | To be use - tested/valid lifting tools & tackles of adeqaute capacity.
|  | Lifting towards third floor | Colliding with 03D4 or process lines on 3rd floor | Shifting should be done under supervsion and instruction provied by supervisor
3 | Positioning of 01E8 on its location | By using lifting tools and tackles | Collision with other process lines | Special precaution for first residue line and 04D1 feed line near/below HE as it is online
Will be carried out under supervision ** & instructions
Chain pulleys to be fixed to concrete beams only
Use of certified blocks, slings & belts according to load of the job (2.8 Tn)
In case of resting of the equipment - rest support of HE on concrete beams
Care should be taken not touch to 03D3 to 03F2 line and 04D1 feed line while shifting.
Blinds on only thermic fluid lines to be removed if required, after positioning of the exchanger in its location
In case of any emergency & abnormality, stop the work in safe manner & inform to the control room
Prepared by: |  |  | Checked By: | Approved by:
| Vikas Jadhav |  | Pradeep Soste | Mr. Rajendra Jain
Mr. Aniruddha Bansod
**Supervision by
Fatty Alc. Shift incharge
Maintenance Engineer
Contract supervisor
Give all the necessary instructions to maintenance person alongwoth the contract person

## 03D3
VVF (INDIA) LIMITED
Date : 20/03/2017
RISK ASSESSMENT
Hot work for 03D3 modification
Sr. No. | Activity | Hazards /Risk | Safety Precautions | Additional control
1 | To ensure risk free environment for hot work | To remove fire hazard | Plant area will be checked and ensured for free of H2 | Proper isolation and purging with N2
2 | Welding and cutting | Fire risk due to Spreading of hot welding flux or sparks on line insulation, equipment insulation, etc | 1. Line or equipment insulation is to be cleaned with water 2.housekeeping to be done for cleaning spilled oil. | Use of Fire blanket with continuous water pouring on it to be implemented during hot work.
|  | welding current leakage | welding machine and job piece to be properly earthened | welding machine to be located at safe distance
|  | eyes irritation and burn injury | use of welding face shield | Keep eye drop and medical aid box in plant to handle irritation etc.
In case of any emergency & abnormality, stop the work in safe manner & inform to the site controller and control room
| Prepared by: | Shubham s mane.
| in presence of | Mr. Vikas jadhav
| Supervision by | Fatty Alc. Shift incharge
|  | Maintenance Engineer | Checked By: | Approved by:
|  | Contract supervisor | Pradeep Soshte | Mr. Rajendra Jain
Mr. Aniruddha Bansod
VVF (INDIA) LIMITED
Date : 20/03/2017
RISK ASSESSMENT
Vessel entry for 03D3 modification
Sr. No. | Activity | Risk | Safety Precautions | Additional control
1 | Vessel entry | Breakage of safety harness power failure of lifting motar | To be use - tested/valid lifting tools & tackles of adeqaute capacity. | 2nd life line to be provided
|  | Oxygen deficiency | Insure Oxygen mole % in confined space of column by O2 meter | We will provide fresh air in column before starting work
|  | Burn injury | Ensure column inside temperature at ambient temp before vessel entry . | Keep first aid box in plant.
|  | Skin & eye irritation due to contact with Alcohol | We will wash the column internals with jet water | Keep first aid box in plant.
|  | risk of injury while handling packing materials | Use proper handgloves | Keep first aid box in plant.
In case of any emergency & abnormality, stop the work in safe manner & inform to the control room
| Prepared by: | Shubham s mane. | Checked By: | Approved by:
| in presence of | Mr. Vikas jadhav | Pradeep Soshte | Mr. Rajendra Jain
Mr. Aniruddha Bansod
| **Supervision by | Fatty Alc. Shift incharge
Maintenance Engineer
Contract supervisor
VVF (INDIA) LIMITED
Date : 20/03/2017
RISK ASSESSMENT
Shiftng of spool piece for 03D3 (shell)
Sr. No. | Activity | Risk | Safety Precautions | Additional control
1 | Arrangement of crane | No risk | Barricade the surrounding area and ensure enough space is provided for proper functioning of crane
|  | No risk | Ensure that all operators have proper knowledge of work and know the risk associated with it
2 | Lifting of shell piece | Failure of SLINGS, D- SHACKLES, BELTS | To be use - tested/valid lifting tools & tackles of adequate capacity.
|  | Colliding with section 4 feed line on 5th floor | Shifting should be done under supervision | we will purge the section 4 line with nitrogen and isolate it before starting work
3 | Positioning of shell on its location | Collision with other process lines | Use of certified blocks, slings & belts according to load of the job
Shifting should be done under supervision
In case of any emergency & abnormality, stop the work in safe manner & inform to the control room
| Prepared by: | Shubham s mane.
| in presence of | Mr. Vikas Jadhav
| **Supervision by | Fatty Alc. Shift in charge | Checked By: | Approved by:
|  | Maintenance Engineer | Pradeep Soshte | Mr. Mahendra Jain
|  | Contract supervisor |  | Mr. Aniruddha Bansod
VVF (INDIA) LIMITED
Date : 21/03/2017
RISK ASSESSMENT
Radiography and stress analysis
Sr. No. | Activity | Risk | Safety Precautions | Additional control
1 | Radiography for leak detection | Risk of skin cancer . | 1) Use radiography suite . 2)Radiography will be conducted by skilled persons in a safe manner to avoid any risk. | Barricade work area before starting Radiography & never stand in the path of x-ray beam
2 | stress analysis | Electrical heater current leak | Electrical heater & job piece need to be properly earthened
|  | Burn injury | Use leather hand gloves while working. | Hot surface tag need to be provide at job site
In case of any emergency & abnormality, stop the work in safe manner & inform to the control room
| Prepared by: | Shubham s mane.
| in presence of | Mr.vikas jadhav
| **Supervision by | Fatty Alc. Shift in charge | Checked By: | Approved by:
|  | Maintenance Engineer | Pradeep Soshte | Mr. Mahendra Jain
|  | Contract supervisor |  | Mr. Aniruddha Bansod
VVF (INDIA) LIMITED
Date : 21/03/2017
RISK ASSESSMENT
Work at height for 03D3 modification
Sr. No. | Activity | Risk | Safety Precautions | Additional control
1 | Work at height for (03D3) modification | Falls from height | Use safety harness with lifeline | Ensure operator trained to work at height.
|  | Being hit by falling object | 1)Areas where there is a risk of a falling object needs to be clearly indicated 2)Materials, tools must not be thrown down from height. | use ppes properly
|  | Carrying of material | 1)On a ladder - the person and anything they are taking up should not exceed the highest load stated on the ladder. 2) Do not lift high load by rope | On a ladder where you must carry something you must have one free hand to grip the ladder
|  | Slip risk by Inappropriate use of ladders | Ladders only to be used for low risk work
In case of any emergency & abnormality, stop the work in safe manner & inform to the control room
| Prepared by: | Shubham s mane.
| in presence of | Mr.vikas jadhav
| **Supervision by | Fatty Alc. Shift in charge | Checked By: | Approved by:
|  | Maintenance Engineer | Pradeep Soshte | Mr. Mahendra Jain
|  | Contract supervisor |  | Mr. Aniruddha Bansod