## Slide 1: Part C IDP: Business Priority Projects
Status update as of December 2016

## Slide 2: Project Details
Group work to systematise Ordering cum Planning process, to bring down inventory levels, improve data collection/cleanup system to represent correct numbers
Project Team:
  Rayomand Mirzan
  Ranajeet Desai
  Riju Mukherjee
  Vikas Gaikwad

## Slide 3: Project Deliverables
Reduction in Inventory of RM & PM by 1day as against the FY 2015-16 achievement.
i.e, For RM :- 19.7 Days as against 18.1days
PM:- 16.1 Days as Against 17.2 Days
Inventory Days 205-16 Data |  |  | 
MONTH | RM | PM | Mean
Mar-16 | 20.0 | 16.0 | 18.0
FEB-16 | 17.0 | 14.0 | 15.5
JAN-16 | 13.0 | 8.0 | 10.5
DEC-15 | 17.0 | 16.0 | 16.5
NOV-15 | 21.0 | 17.0 | 19.0
OCT-15 | 18.0 | 22.0 | 20.0
SEP-15 | 17.0 | 17.0 | 17.0
AUG-15 | 21.0 | 20.0 | 20.5
JUL-15 | 22.0 | 22.0 | 22.0
JUN-15 | 17.0 | 15.0 | 16.0
MAY-15 | 14.0 | 21.0 | 17.5
APR-15 | 20.0 | 18.0 | 19.0
AVG. | 18.1 | 17.2 | 17.6

## Slide 4: Current Status and Completion Date
Inventory Days 2015-16 |  |  | 
MONTH | RM | PM | Mean
Apr-15 | 20.0 | 18.0 | 19.0
May-15 | 14.0 | 21.0 | 17.5
Jun-15 | 17.0 | 15.0 | 16.0
Jul-15 | 22.0 | 22.0 | 22.0
Aug-15 | 21.0 | 20.0 | 20.5
Sep-15 | 17.0 | 17.0 | 17.0
Oct-15 | 18.0 | 22.0 | 20.0
Nov-15 | 21.0 | 17.0 | 19.0
Dec-15 | 17.0 | 16.0 | 16.5
Jan-16 | 13.0 | 8.0 | 10.5
Feb-16 | 17.0 | 14.0 | 15.5
Mar-16 | 20.0 | 16.0 | 18.0
AVG. | 18.1 | 17.2 | 17.6
RM inventory has increased, while PM inventory has reduced YOY
Inventory Days 2016-17 |  |  | 
MONTH | RM | PM | Total
Apr-16 | 17.0 | 17.0 | 17.0
May-16 | 19.8 | 17.6 | 18.7
Jun-16 | 19.8 | 15.3 | 17.6
Jul-16 | 21.9 | 15.0 | 18.5
Aug-16 | 19.7 | 12.7 | 16.2
Sep-16 | 22.8 | 17.3 | 20.1
Oct-16 | 25.8 | 15.5 | 20.7
Nov-16 | 22.6 | 15.5 | 19.1
Dec-16 | 18.0 | 15.8 | 16.9
Jan-17 | 16.0 | 19.0 | 17.5
Feb-17 | 15.0 | 15.0 | 15.0
Mar-17 | 18.0 | 17.0 | 17.5
AVG. | 19.7 | 16.1 | 18.0

## Slide 5: Challenges in completion of the project
Plan cancellation/changes on frequent basis does hurt the inventory. Material brought if not produced remains as an inventory at the month end. From the statement its clearly visible that RM inventory which comes from far off destinations is taking a hit whereas PM inventory which is local and can be re-scheduled with changes and has shown an improvement
Measurement method for calculation of inventory days in case of plan
cancellations

## Slide 6: Support required to complete the project
Firm production line plan for 30days.
Measurement method for cancelled plan to be corrected. Currently inventory for plan cancelled but considered for production in next month is considered. This should not apply if production taken in 2nd half of next month. Similarly plan cancellation during the 2nd half of a given month should also not be considered as by then the material has moved for the 1st half of next month