|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Micro Schedule for D2D25 Foundation Repair work** | | | | | | |
| **Sr No** | **Activity** | **Duration** | **Date** | **Tentative Start time** | **Tentative Finish Time** | **Status** |
| 1 | Registration and Safety Induction |  | 5/10/2016 |  |  | **Completed** |
| 2 | Preparation of Support | 1 Day | 5/10/2016 | 9:30 | 17:00 | **Completed** |
| 3 | Preparation of Share Key and Reinforcement | 1 Day | 5/12/2016 | 9:30 | 17:00 | **Completed** |
| 4 | Fixing of Support | 1.5 hrs. | **5/14/2016** | **4.30** | 6.00 |  |
| 5 | Breaking of Column | 5 hrs. | 5/14/2016 | 6.00 | 11.05 |  |
| 6 | Cleaning of Columns | 2 Hrs | 5/14/2016 | 9.30 | 11.30 |  |
| 7 | Polymer Modified Mortar | 4 Hrs | 5/14/2016 | 12.30 | 16.30 |  |
| 8 | Fixing of Grout Nozzles. | 3 hrs. | 5/14/2016 | 20.30 | 23.30 |  |
| 9 | Epoxy Grouting | 24 Hrs | 15-05-2016 to 16/05/2016 | 0.30 | 23.30 |  |
| 10 | Fixing of Reinforcement | 3 hrs. | 5/17/2016 | 6.30 | 9.30 |  |
| 11 | Cutting of Nozzles | 1 Hrs | 5/17/2016 | 23.45 | 0.45 |  |
| 12 | Preparation of Shuttering | 4 Hrs | 5/17/2016 | 21.30 | 1.30 |  |
| 13 | Application of Bonding Agent | 1 Hrs | 5/18/2016 | 1.30 | 2.30 |  |
| 14 | Pouring of Micro concrete | 30 Hrs | 18-05-2016 | 3.00 | 10.30 |  |
| 15 | De-shuttering & removing Temporary Supports. | 2Hrs | 5/18/2016 | 1.00 | 3.00 |  |
| 16 | Hand Over |  | **5/18/2016** |  | **4.00** |  |
| Note - All required materials available at Site. | | | | | | |

**RCC Road work near WB -1**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Sr. No** | **Activity** | **Start Date** | **Completion Date** | **Remarks** |
| 1. | Breaking of Damaged RCC Road Panel and cleaning surface | 14.03.2017 | 16.03.2017 | By Poclain, Tractor Compressor – Excavator machine |
| 2. | Steel bending, cutting ,placing and binding etc. | 14.03.2017 | 17.03.2017 |  |
| 3. | Form work for Paneling | 16.03.2017 | 17.03.2017 |  |
| 4 | PCC for Breaking area | 16.03.2017 | 17.03.2017 |  |
| 5. | Casting of concrete (RMC) | 17.03.2017 | 19.03.2017 |  |
| 6 | Groove Cutting | 20.03.2017 | 20.03.2017 |  |
| 7. | Curing | 20.03.2017 | 10.04.2017 |  |
| 8. | Gap/ Grove Filling | 11.04.2017 | 11.04.2017 | Road reopen for movement from 11.04.2017 |

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Schedule for Temporary Monsoon at Taloja Year 2016-17** | | | | | |
| **S.No** | **Activity** | **Starting Date** | **Completion Date** | **Days** | **Completion Date** |
| 1 | Obtaining current year requirements from various users dept. | 04.03.2016 | 15.03.2016 | 12 |  |
| 2 | Finalization shed requirement with plant head. | 16.03.2016 | 21.03.2016 | 6 |  |
| 3 | Submission of letter to MIDC for permission as per our requirement. | 22.03.2016 | 23.03.2016 | 2 |  |
| 4 | Receiving Approval letter from MIDC. | 24.03.2016 | 04.04.2016 | 12 | On request to MIDC |
| 5 | Submission of agreement copy & plot plan drawing with Measurement sheet to MIDC |  | 05.04.2016 | 1 |  |
| 6 | Raise PRF for service purchase order. |  | 01.04.2016 | 1 |  |
| 7 | Release purchase order for services | 01.04.2016 | 11.04.2016 | 10 |  |
| 8 | Receiving deposit & rent demand letter from MIDC. | 18.04.2016 | 21.04.2016 | 4 |  |
| 9 | Demand draft for MIDC Deposit & Rent. | 21.04.2016 | 23.04.2016 | 3 |  |
| 10 | To start receiving material (Bamboo & Tarpaulins) | 16.04.2016 | 18.04.2016 | 3 | Start from 12.04.2017 |
| 11 | Start of Monsoon shed Constructions. | 18.04.2016 | 01.06.2016 | 42 | Start from 15.04.2017 |
| 12 | MIDC approved period for monsoon shed. | 15.06.2016 | 15.11.2016 | 150 |  |
| 13 | Removing of Sheds | 01.11.2016 | 15.11.2016 | 15 | 10.11.2016 |
| 14 | Application of release Deposit amount from MIDC. |  | 15.11.2016 | 1 | 12.11.2017 |